## DDR # 04
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 4
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / MEHDI / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 413 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 3.5833
RIG REP.: |  | JAVED IQBAL / KHALID |  |  | MD/TVD @ 06:00HRS: |  | 434 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 117
2017-12-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 26" |  | BIT No. |  | 2 | 2 | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 15.92
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 413 |  | SIZE (IN) |  | 26 | 26 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 853.42
DEPTH, MD (M) | 353 | 413 | TVD @ 00:00HR (M) |  | 413 |  | MANUFACTURER |  | BAKER | BAKER | 26"PDC BIT |  |  | 26 |  |  | 7 5/8 REG |  | 0.57 |  |  | PITS (BBL) | 855
MW IN (SG) | 1.12 | 1.12 | DAILY PROGRESS (M) |  | 117 |  | TYPE |  | TD509S | TD509S | BITSUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 1.08 | 0.5 |  | ACT. SYS (BBL) | 1724.34
MW OUT (SG) | 1.12 | 1.12 | INST. ROP (M/HR) |  | 4.98 |  | SERIAL NO. |  | 5278922 | 5278922 | SHOCK SUB |  |  | 12 | 2.75 |  | 7 5/8 REG |  | 4.16 | 2 |  | RESV. SYS (BBL) | 920
ECD (SG) | 1.1246 | 1.1246 | AVG. ROP (M/HR) |  | 5.57 |  | IADC CODE |  | S423 | S423 | 2X11" DCS |  |  | 11 | 3 |  | 7 5/8 REG |  | 18.32 | 8.18 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 96.8 | 96.8 | AVG. WOB (TON) |  | 6 |  | NOZZLES |  | 9X14 | 9X14 | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.34 | 1 |  | KILL MW (SG)
µ FUNNEL (SEC) | 80 | 83 | AVG. RPM SURFACE |  | 118 |  | DEPTH IN (M) |  | 47 | 47 | 1X11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.2 | 4.11 |  | TOTAL | 2644.34
PV | 17 | 19 | AVG. RPM DOWNHOLE |  | 118 |  | DEPTH OUT (M) |  |  |  | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.23 | 1 |  | DIESEL (LTR)
YIELD POINT | 30 | 33 | FLOWRATE (GPM) |  | 900 |  | METERAGE (M) |  | 366 | -47 | 6X9.5" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 55.58 | 17.95 |  | RIG TANK | 100000
GEL ST. | 16/40 | 15/45 | PRESSURE (PSI) |  | 1325 |  | RPM SURF. |  | 90-120 | 90-110 | X-OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.3 |  | CAMP TANK | 22200
WL (ml/30 min.) | 10 | 10 | TORQ. ON-BTM (KLB-FT) |  | 8 |  | RPM BTM. |  | 90-120 | 90-110 | D.JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 5.15 | 1.15 |  | CONSUMED | 8700
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4 |  | WOB (TON) |  | 1-12 | 1-11 | 3X8" DCs |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 27.85 | 6.22 |  | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  | 88 |  | AVG. ROP (M/HR) |  | 6.4825 | -1.3251 | X-OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 0.17 |  | TOTAL | 122200
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  | 89 |  | BIT ROT HRS. |  | 56.46 | 35.47 | 15 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.41 | 10.3 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 87 |  | K-REVS IN 24 HRS |  | 148.75 | 73.77 | [11 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 359.01 | 212.82 | [11 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 10.1 | 10.3 | [11 empty] | CONSUMED | 147658
NaCl (mg/l) | 495 | 495 | JAR | 45.85 | NMDC |  | JET VELOCITY (M/SEC) |  | 63.8 | 64.5 | [11 empty] | RECEIVED | 252658
CHLORIDES | 300 | 300 | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) |  | 1.35 | 1.35 | [11 empty] | TOTAL | 345000
CALCIUM | 100 | 100 | 8" DCS |  | STAB - 2 |  | HSI |  | 1.4 | 1.7 | [11 empty] | POB
OIL% |  |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 268.56 |  |  | MPCL | 4
SAND % | 0.5 | 0.5 | BHA ROT. HRS |  | 67.87 |  | BIT No. 2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 49 |  |  | MPCL SERV | 14
SOLIDS % | 4.98 | 4.98 | ON BOTTOM HRS |  | 56.48 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 34 |  |  | SECURITY
M.B.T. | 20 | 20 | CIRC. HRS |  | 69.17 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  |  | 110 |  | 0.5 | [8 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 38857.1625 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 210 |  | 0.5 | [8 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1668513.2148 | SHAKER-3 | 1 X 80 | 2 X 50 |  | 9 5/8" PRODUCTION CSG |  |  |  | 323 |  | 1 | [8 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 9.244% | MUD CLEANER | 3 X 200 |  |  | 7" LINER |  |  |  | 409 |  | 0.25 | [8 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI | 342
FIRE DRILL |  |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43093 | 43093.2604 | 6.25 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED AHEAD 26" HOLE SECTION FROM 296M TO 334M. REAMED AT EACH CONNECTION.
43093.2604 | 43093.2917 | 0.75 | DRL | PT-P | CIR | CIRCULATE BOTTOMS UP / CLEAN HOLE PRIOR TO TOTCO SURVEY.
43093.2917 | 43093.3229 | 0.75 | DRL | PT-P | S | P/BACK TO 323M & RECORDED TOTCO DEVIATION SURVEY ON SLICKLINE. (DEV: 1.0° @ 323M).
43093.3229 | 43094 | 16.25 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED AHEAD 26" HOLE SECTION FROM 334 M TO 413M. REAMED AT EACH CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43094 | 43094.0625 | 1.5 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED AHEAD 26" HOLE SECTION FROM 413 M TO 421M.
43094.0625 | 43094.1042 | 1 | DRL | PT-P | CIR | CIRCULATE BOTTOMS UP / CLEAN HOLE PRIOR TO TOTCO SURVEY.
43094.1042 | 43094.1354 | 0.75 | DRL | PT-P | S | P/BACK TO 409M & RECORDED TOTCO DEVIATION SURVEY ON SLICKLINE. (DEV: 0.25° @ 409M).
43094.1354 | 43094.25 | 2.75 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED AHEAD 26" HOLE SECTION FROM 421 M TO 434M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHINJI (80% SANDSTONE 20% & CLAYSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 26" HOLE SECTION
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 26" HOLE SECTION FROM 296M TO 413M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 26" HOLE SECTION.
REMARKS
..0