## DDR#40
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 40
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 39.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 4RR2 |  | BHA NO. |  |  | 8 | IN (M) |  | 2305 |  | OUT (M) |  |  | STRING (BBL) | 1.8
CHECK TIME | 10:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2426
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.11629 |  | PITS (BBL) | 903
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TFH519S |  | BIT SUB (F.V) |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.08 | 0.34888 |  | ACT. SYS (BBL) | 3330.8
MW OUT (SG) | 2.06 | 2.06 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E260745 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.31 | 0.74622 |  | RESV. SYS (BBL) | 795
ECD (SG) | 2.07 | 2.07 | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL) | 700
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 5 X 16 |  | STRING STAB |  |  | 17.375 | 3.1875 |  | 7 5/8 REG |  | 2.36 | 0.76237 |  | KILL MW (SG) | 2.15
µ FUNNEL (SEC) | 65 | 67 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2305 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.54 | 5.9891 |  | TOTAL | 4125.8
PV | 37 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.19 | 0.70745 |  | DIESEL (LTR)
YIELD POINT | 26 | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.78 | 11.8814 |  | RIG TANK | 77861
GEL ST. | 12/29 | 13/25 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.95 | 0.30689 |  | CAMP TANK | 15771
WL (ml/30 min) | 7 | 7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.49 | 4.1288 |  | CONSUMED | 8219
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | DRILLING JAR |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 9.58 | 2.1392 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.42 | 4.1132 |  | TOTAL | 93632
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X/OVER |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.4 | 8.4486 |  | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 151500
KCl (mg/l) | 30800 | 30800 | JAR | 46.56 | STAB - 1 | 46.56 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 151500
CHLORIDES (mg/l) | 28000 | 28000 | 5 1/2" HWDPS | 46.56 | STAB - 2 | 46.56 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 560000
HARDNESS (mg/l) | 320 | 320 | 9 1/2" DCS | 46.56 | STAB - 3 | 46.56 | HSI | [14 empty] | POB
SAND % | 0.2 | 0.2 | 8" DCS | 46.56 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.45 |  |  | MPCL | 8
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 46.56 |  | BIT NO. 4RR2 |  | 1-2-FC-A-X-I-DL-LOG |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 35
SOLIDS % | 34.67 | 34.67 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 10 | 10 | CIRC. HRS |  | 30.38 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 125
DAILY WELL COST (US$) |  | 38374.94 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3870648.7392 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 19.44% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43628 | 43628.0104 | 0.25 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43628.0104 | 43628.0208 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43628.0208 | 43628.1667 | 3.5 | DRL | PT-P | WT | CONDUCTED WIPER TRIP FROM 2420M TO 2000M. DURING POOH FOR WIPER TRIP, OBSERVED & CLEARED TIGHT SPOTS @ 2333M - 2331M & 2299M WITH CIRCULATION.
43628.1667 | 43628.3958 | 5.5 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD.
43628.3958 | 43628.4167 | 0.5 | DRL | PT-P | S | DROPPED TOTCO & CHASED WITH MUD. P/BACK TO 2410M & ALLOWED TIME TO RECORD DEVIATION SURVEY.
43628.4167 | 43628.4271 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43628.4271 | 43628.6146 | 4.5 | EVAL | PT-P | POOH | POOH FROM 2420M TO 1600M & OBSERVED HOLE SWABBING.
43628.6146 | 43628.8438 | 5.5 | EVAL | PT-P | RW | PUMPED OUT FROM 1600M TO 559M (9 5/8" CASING SHOE). CLEARED TIGHT SPOT @ 879M, 761M & 747M BY REAMING.
43628.8438 | 43628.8646 | 0.5 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43628.8646 | 43628.9271 | 1.5 | EVAL | PT-P | POOH | POOH FROM 559M TO 215M (TOP OF BHA).
43628.9271 | 43628.9375 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43628.9375 | 43629 | 1.5 | EVAL | PT-P | BHA | POOH FROM 215M TO 63M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43629 | 43629.0833 | 2 | EVAL | PT-P | BHA | POOH FROM 63M TO SURFACE. FOUND 1ST & 3RD S. STAB FULLY BALLED UP AND 2ND S. STAB & BIT PARTIALLY BALLED UP. L/D D. JAR & 3 X S. STAB.
43629.0833 | 43629.125 | 1 | EVAL | PT-P | RU | R/U W/L LOGGING GEARS. MEANWHILE MONITORED WELL THRU TRIP TANK.
43629.125 | 43629.1979 | 1.75 | EVAL | PT-P | W/L | PJSM. R/U & M/U LOGGING TOOLS. FUNCTION TESTED & CALIBRATED SAME. MEANWHILE MONITORED WELL THRU TRIP TANK.
43629.1979 | 43629.25 | 1.25 | EVAL | PT-P | W/L | RIH LOGGING TOOLS & RECORDING OF W/L LOGS (BHC-LDL-GR-PPC-GPIT) IS IN PROGRESS. MEANWHILE MONITORED WELL THRU TRIP TANK.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RECORDING WIRELINE LOGS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO CONDITION MUD. PERFORMED WIPER TRIP FROM 2420M TO 2000M. CIRCULATED TO CONDITION MUD. DROPPED TOTCO. POOH FROM 2420M TO 1600M. PUMPED OUT FROM 1600M TO 559M. POOH FROM 559M TO 63M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RECORD SLB W/L LOGS AS PER PROGRAM. PERFORM CONDITION TRIP PRIOR CASING & CEMENT JOB.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14