## DDR # 400
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 400
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 399.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1085
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 401
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1486
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 799
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 63 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2285
PV |  | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 88861
GEL ST. |  | 11/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 30915
WL (ml/30 min) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5774
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 119776
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 662275
DIESEL % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 83000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 49241
KCl (mg/l) |  | 43472.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 134700
CHLORIDES (mg/l) |  | 75700 | JAR |  | ST. STAB |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 160 | 3 1/2" HWDPS |  |  |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 21
SOLIDS % |  | 18 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 2.6 |  | BIT NO. 36 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 27152.625 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 26905528.2743 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 103.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43988 | 43988.1042 | 2.5 | DRL | NPT-UP | W/L / RIH | RIH CML TOOLS WITH DRL STRING (5" DP) DOWN TO 4756M. FILLED STRING EVERY 15 STANDS.
43988.1042 | 43988.125 | 0.5 | DRL | NPT-UP | W/L / CIR | BROKE CIRCULATION.
43988.125 | 43988.1562 | 0.75 | DRL | NPT-UP | W/L / RIH | CONT'D RIH FROM 4756M TO 4928M.
43988.1562 | 43988.1771 | 0.5 | DRL | NPT-UP | W/L / RW | WASHED DOWN FROM 4928M TO 4933M. RECORDED SPP AT DIFF FLOW RATES (1, 2, 3 & 4 BPM & 410, 780, 1230 & 1610 PSI RESPECTIVELY).
43988.1771 | 43988.2604 | 2 | DRL | NPT-UP | W/L / CIR | SPACED OUT TO 4888M. DROPPED DART & CHASED IT WITH 3.4 BPM (1400 PSI), 1.9 BPM (540 PSI) & THEN 1 BPM (260 PSI). PRESSURE INCREASED FROM 260 PSI TO 810 PSI & DROPPED TO 170 PSI. TOOLS DEPLOYED SUCCESSFULLY. CIRCULATED FOR 15 MIN PRIOR LOGGING.
43988.2604 | 43988.3333 | 1.75 | DRL | NPT-UP | W/L / POOH | POOH AT SLOW SPEED WHILE LOGGING (RUN# 01: RESISTIVITY-SONIC-GR) OPEN HOLE SECTION INSIDE WINDOW.
43988.3333 | 43988.3438 | 0.25 | DRL | NPT-UP | W/L / FC | FLOW CHECK, WELL STATIC.
43988.3438 | 43988.8125 | 11.25 | DRL | NPT-UP | W/L / POOH | CONT'D NORMAL POOH FROM 4759M TO SURFACE. L/D CWS BHA & LOGGING TOOLS.
43988.8125 | 43988.9271 | 2.75 | DRL | PT-P | W/L | PREPARED CML TOOLS FOR RUN# 02 AT SURFACE. MEANWHILE ATTEMPTED TO RETRIEVE THE DATA FROM CML TOOLS (RUN# 01). NO DATA RECORDED DUE TO TOOL MALFUNCTION.
43988.9271 | 43989 | 1.75 | DRL | PT-P | W/L | P/U & M/U MULE SHOE + LANDING & CIR SUB + 3 1/2" GARAGE PIPES (DPS) + LOWER LATCH; M/U & INSTALLED CML TOOLS (RUN# 02) IN GARAGE PIPES & F/T.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43989 | 43989.0417 | 1 | DRL | PT-P | W/L | CONT'D F/T TOOLS. M/U UPPER LATCH + 3 1/2" DP (P/JOINT) + FLOAT VALVE.
43989.0417 | 43989.25 | 5 | DRL | PT-P | W/L / RIH | RIH CML TOOLS (RUN# 02) WITH DRL STRING (3 1/2" & 5" DP) DOWN TO 1897M & IS IN PROGRESS. FILLED STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH CML TOOLS (RUN# 01) WITH DRL STRING DOWN TO 4933M. SPACED OUT TO 4888M. DROPPED & CHASED THE DART; DEPLOYED THE TOOLS SUCCESSFULLY. POOH AT SLOW SPEED WHILE LOGGING (RUN# 01: RESISTIVITY-SONIC-GR) OPEN HOLE SECTION INSIDE WINDOW. POOH TO SURFACE & L/D TOOLS. PREPARED THE TOOLS FOR RUN# 02. P/U & M/U CWS BHA & CML TOOLS FOR RUN# 02.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM & SPACE OUT. DROP & CHASE THE DART TO DEPLOY THE TOOLS (RUN# 02). POOH WHILE LOGGING OPEN HOLE. POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14