## DDR # 404
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 404
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 403.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1085
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 428
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1513
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 720
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2233
PV |  | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 116109
GEL ST. |  | 12/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 28274
WL (ml/30 min) |  | 3.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3731
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 21000
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 144383
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 592400
DIESEL % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 78000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 62750
KCl (mg/l) |  | 43091.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 43100
CHLORIDES (mg/l) |  | 75400 | JAR |  | ST. STAB |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 160 | 3 1/2" HWDPS |  |  |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 24
SOLIDS % |  | 18.02 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 2.36 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 115
DAILY WELL COST (US$) |  | 30681.9125 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 28023846.7635 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 88.62% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43992 | 43992.0104 | 0.25 | DRL | PT-P | W/L / RIH | CONT'D RIH FROM 4817M TO 4876M.
43992.0104 | 43992.0417 | 0.75 | DRL | PT-P | W/L / RW | WASHED DOWN FROM 4876M TO 4932M. RECORDED SPP AT DIFF FLOW RATES (1, 1.9, 2.8 & 3.4 BPM & 450, 650, 1040 & 1510 PSI RESPECTIVELY).
43992.0417 | 43992.1146 | 1.75 | DRL | PT-P | W/L / CIR | SPACED OUT TO 4885M. DROPPED DART & CHASED IT WITH 3.4 BPM (1400 PSI), 1.9 BPM (600 PSI) & THEN 1 BPM (300 PSI). OBSERVED PRESSURE INCREASED TO 450 PSI AND DROPPED TO 210 PSI. TOOLS DEPLOYED SUCCESSFULLY. CIRCULATED FOR 15 MIN PRIOR LOGGING.
43992.1146 | 43992.1667 | 1.25 | DRL | PT-P | W/L / POOH | POOH AT SLOW SPEED WHILE LOGGING (RUN# 03: RESISTIVITY-SONIC-HNGS) OPEN HOLE SECTION INSIDE WINDOW.
43992.1667 | 43992.1771 | 0.25 | DRL | PT-P | W/L / FC | FLOW CHECK, WELL STATIC.
43992.1771 | 43992.6146 | 10.5 | DRL | PT-P | W/L / POOH | CONT'D NORMAL POOH FROM 4759M TO SURFACE. L/D CWS BHA & LOGGING TOOLS (RUN# 03). (RETRIEVED THE DATA FROM TOOLS SUCCESSFULLY)
43992.6146 | 43992.8021 | 4.5 | DRL | PT-P | W/L | PREPARED CML TOOLS & REDRESSED CWS BHA AT SURFACE.
43992.8021 | 43992.8438 | 1 | DRL | NPT-UP | W/L | HELD PJSM. P/U 5" WASHPIPE ASSY WITH MULE SHOE. WHILE TORQUING UP WASHPIPE CONNECTIONS, OBSERVED GAP IN TORQUED UP CONNECTIONS. L/D THE ASSY AS A PRECAUTIONARY MEASURE.
43992.8438 | 43993 | 3.75 | DRL | PT-P | W/L | P/U BACK UP 5" WASHPIPE ASSY WITH MULE SHOE. INSTALLED CML TOOLS FOR RUN# 04 & FUNCTION TESTED. M/U X-OVER + LANDING & CIR SUB + 3 1/2" GARAGE PIPES (1 DP + 1 P/J) WHILE PICKING UP TOOLS & LATCHED IN LOWER LATCH; M/U UPPER LATCH + 3 1/2" DP (P/JOINT) + FLOAT VALVE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43993 | 43993.25 | 6 | DRL | PT-P | W/L / RIH | RIH CML TOOLS (RUN# 04) WITH DRL STRING (3 1/2" & 5" DP) DOWN TO 2334M & IS IN PROGRESS. FILLED STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 4817M TO 4932M. SPACED OUT TO 4885M. DROPPED & CHASED THE DART; DEPLOYED THE TOOLS SUCCESSFULLY. POOH AT SLOW SPEED WHILE LOGGING (RUN# 03: RESISTIVITY-SONIC-HNGS) OPEN HOLE SECTION INSIDE WINDOW. POOH TO SURFACE. M/U CWS BHA FOR RUN#04, INSTALLED LOGGING TOOLS & FUNCTION TESTED.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM & SPACE OUT. DROP & CHASE THE DART TO DEPLOY THE TOOLS (RUN# 04). POOH WHILE LOGGING OPEN HOLE. POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21