## DDR # 407
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 407
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 406.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 40.8
CHECK TIME |  | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1022.8
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 377
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1440.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 749
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 59 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2189.6
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 103564
GEL ST. |  | 11/13 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 26346
WL (ml/30 min) |  | 3.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5715
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 129910
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 667775
DIESEL % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 61125
KCl (mg/l) |  | 43091.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 31500
CHLORIDES (mg/l) |  | 75400 | JAR | 95.01 | ST. STAB 1 | 4.8 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 160 | 3 1/2" HWDPS | 97.47 | ST. STAB 2 | 4.8 | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  | 2.25 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 26
SOLIDS % |  | 18.02 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 2.75 |  | BIT NO. 36 RR1 |  |  | 1-1-CT-A-X-I-BT-TD |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 449820.7854 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 28540593.0822 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 90.26% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43995 | 43995.0833 | 2 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43995.0833 | 43995.0938 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
43995.0938 | 43995.1458 | 1.25 | DRL | PT-P | RW / POOH | PUMP OUT / POOH FROM 4934M TO 4785M. PUMPED OUT AT 4929M, 4854M, 4835M, 4809M. POOH ON ELEVATOR FROM 4785M TO 4757M INSIDE WINDOW. HOLE CONDITION, GOOD.
43995.1458 | 43995.1562 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
43995.1562 | 43995.5208 | 8.75 | DRL | PT-P | POOH | POOH FROM 4757M TO 511M.
43995.5208 | 43995.5729 | 1.25 | DRL | NPT-P | RS | CUT & SLIPPED 102 FT DRILL LINE. ADJUSTED CROWN-O-MATIC & RESET ACS.
43995.5729 | 43995.5938 | 0.5 | DRL | PT-P | POOH | POOH FROM 511M TO 284M. FLOW CHECK, WELL STATIC.
43995.5938 | 43995.6354 | 1 | DRL | PT-P | BHA | POOH BHA TO SURFACE. L/D JAR, 2x 4 3/4" DC, 2x ST. STABS, BIT SUB & BIT.
43995.6354 | 43995.6667 | 0.75 | DRL | PT-P | RU | R/U WFD TRS EQUIPMENT.
43995.6667 | 43995.8229 | 3.75 | DRL | PT-P | RC | HELD PJSM. P/U & M/U 5" LINER (18PPF, Q125, VAM FJL) SHOE TRACK [RS + 2x JOINTS + FC + JOINT + LC + JOINT]. APPLIED THREAD LOCK COMP ON EACH SHOE TRACK CONNECTION. CHECKED FLOATS INTEGRITY, OK. CONT'D RIH 5" LINER DOWN TO 224M.
43995.8229 | 43995.875 | 1.25 | DRL | PT-P | RC | P/U & M/U 5" LINER HANGER ASSY. INSTALLED SWP. CHECKED SHEAR PINS OF SWP, BALL SEAT, HOLD DOWN SUB, HANGER & PACKER. FILLED PBR WITH HI-VIS & CIRCULATED LINER VOLUME. RIH DOWN TO 235M.
43995.875 | 43996 | 3 | DRL | PT-P | RC | RIH 5" LINER ON 3 1/2" DP STRING FROM 235M TO 1435M. DRIFTED EACH STAND WITH 2 1/4" DRIFT. FILLED AFTER 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43996 | 43996.25 | 6 | DRL | PT-P | RC | CONT' RIH 5" LINER ON 3 1/2" & 5" DP STRING FROM 1435M TO 2900M & IS IN PROGRESS. DRIFTED EACH STAND WITH 2 1/4" DRIFT. FILLED AFTER 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 5" LINER IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TILL SHAKERS CLEAN. POOH TO SURFACE. RIH 5" LINER (18PPF, Q125, VAM FJL) WITH LINER HANGER ASSY DOWN TO 1435M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 5" LINER DOWN TO BOTTOM. SET LINER HANGER & RELEASE SETTING TOOL. CIRCULATE TO CONDITION MUD. PERFORM CEMENT JOB & SET PACKER. CIRCULATE TO CLEAN HOLE & POOH DRL STRING TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14