## DDR # 408
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 408
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 407.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 239.6
CHECK TIME | 11:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 749.3
DEPTH, MD (M) | 4934 | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 458
MW IN (SG) | 1.55 | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1446.9
MW OUT (SG) |  | 1.55 | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 824
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  | 110 | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 58 | 51 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2270.9
PV | 30 | 29 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 24 | 20 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 99783
GEL ST. | 11/13 | 5/8 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 25683
WL (ml/30 min) | 3.7 | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4444
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 125466
ALK (FILT.) | 0.3/1.0 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 635975
DIESEL % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 63300
KCl (mg/l) | 43091.4 | 43091.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 52500
CHLORIDES (mg/l) | 75400 | 75400 | JAR |  | ST. STAB 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 160 | 160 | 3 1/2" HWDPS |  | ST. STAB 2 |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % | 3 | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 5
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 1.63 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 30
SOLIDS % | 18.02 | 18.02 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 8.4 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 32438.33 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 28573031.4122 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 90.36% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43996 | 43996.3438 | 8.25 | DRL | PT-P | RC | CONT' RIH 5" LINER ON 3 1/2" & 5" DP STRING FROM 1435M TO 3562M. DRIFTED EACH STAND WITH 2 1/4" DRIFT. FILLED AFTER 15 STANDS.
43996.3438 | 43996.3646 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43996.3646 | 43996.5417 | 4.25 | DRL | PT-P | RC | CONT' RIH 5" LINER ON 5" DP STRING FROM 3562M TO 4753M. DRIFTED EACH STAND WITH 2 1/4" DRIFT. FILLED AFTER 15 STANDS.
43996.5417 | 43996.5625 | 0.5 | DRL | PT-P | CIR | BROKE CIRCULATION. RECORDED STRING WEIGHT, PRESSURE & TORQUE.
43996.5625 | 43996.625 | 1.5 | DRL | PT-P | RC | WASHED DOWN 5" LINER DOWN TO 4928.5M.
43996.625 | 43996.7083 | 2 | DRL | PT-P | RW | ATTEMPTED TO GO DEEPER WITH CIRCULATION & ROTATION, NO SUCCESS.
43996.7083 | 43996.8958 | 4.5 | DRL | PT-P | RW | OBSERVED PRESSURE SPIKES WHILE PUMPING AT 3 BPM & 1000 PSI; SUDDENLY PRESSURE INCREASED TO 1500 PSI. STOPPED PUMP, OBSERVED PRESSURE TRAPPED IN STRING AND NO LINER ROTATION. BLED OFF PRESSURE AND ATTEMPTED TO REGAIN CIRCULATION AT 1.5 BPM & 2300-2500 PSI. GRADUALLY GAINED CIRCULATION AT 4.2 BPM & 2400-2600 PSI (PRESSURE FLUCTUATING THROUGOUT CIRCULATION). ATTEMPTED TO RESUME ROTATION INTERMITTENTLY; NO SUCCESS.
43996.8958 | 43997 | 2.5 | DRL | PT-P | RC | DROPPED 1.25" ALUMINIUM BALL. M/U CEMENT HEAD ALREADY LOADED WITH DP DART. CHASED BALL WITH 1.7 BPM & 500 PSI. BALL SEATED & INCREASED PRESSURE TO 1400 PSI, WAIT FOR 5 MIN. SET HOLD DOWN SUB & HANGER. ATTEMPTED TO RELEASE THE RUNNING TOOL HYDRAULICALLY AT 1800 PSI, 2000 PSI & 2200 PSI, NO SUCCESS. BALL SEAT SHEARED AT 2200 PSI. RELEASED THE RUNNING TOOL MECHANICALLY. CHECKED STRING FREE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43997 | 43997.0208 | 0.5 | DRL | PT-P | P/T | HELD PJSM. R/U & P/T CEMENT LINES AT 4700 PSI.
43997.0208 | 43997.1146 | 2.25 | DRL | PT-P | CIR | CIRCULATED THROUGH RIG PUMP MEANWHILE PREPARED MIX FLUID & WEIGHTED UP BATCH MIXED GASBLOK CEMENT SLURRY.
43997.1146 | 43997.2083 | 2.25 | DRL | PT-P | CMC | PUMPED 100 BBL LOW RHEOLOGY MUD OF 1.55 SG FROM RIG PUMP FOLLOWED BY 64 BBL MUDPUSH II SPACER OF 15 PPG AT 4.2 BPM. SWITCHED TO CEMENT UNIT, PUMPED 30 BBL BATCH MIXED GASBLOK CEMENT SLURRY OF 17 PPG AT 3 BPM. DROPPED DP DART. PUMPED 15 BBL MUDPUSH II SPACER & 10 BBL MUD. OBSERVED SLOW SUPPLY OF MUD TO CEMENT UNIT, SWITCHED TO RIG PUMP AND PUMPED 209 BBL MUD (TOTAL DISPLACEMENT - 234 BBL). OBSERVED NO INDICATION OF SINGLE WIPER PLUG (SWP) PINS SHEARING. SWP WAS NOT BUMPED. BLED OFF PRESSURE, FLOATS HOLDING.
43997.2083 | 43997.2292 | 0.5 | DRL | PT-P | SPK | P/U STRING 4M AND SET PACKER WITH 30 TON WEIGHT. OBSERVED CLEAR INDICATION OF PINS SHEARING. MAX SLACKED OFF WEIGHT ON PACKER 35 TON. R/D CEMENT HEAD.
43997.2292 | 43997.25 | 0.5 | DRL | PT-P | CIR | POOH 2 STANDS AND CIRCULATION FOR BOTTOMS UP IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 5" LINER ON DRL STRING DOWN TO 4753M & WASHED DOWN TO 4928.5M. ATTEMPTED TO GO DEEPER WITH CIRCULATION & ROTATION, NO SUCCESS. OBSERVED PRESSURE INCREASED & TRAPPED IN STRING WITH NO LINER ROTATION. REGAINED CIRCULATION GRADUALLY FROM 1.5 TO 4.2 BPM BUT NO LINER ROTATION. SET 5" LINER HANGER AS PER PLAN & RELEASED RUNNING TOOL MECHANICALLY.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION. POOH TO SURFACE & L/D RUNNING TOOL. RIH RR 6" PDC BIT TO TAG TOP OF 5" LINER.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14
Note on F36: CMan.Rig3: 5" Liner rotation at bottom