## DDR # 409
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 409
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 408.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 85 |  | BHA NO. |  |  | 103 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 43.5
CHECK TIME |  | 20:30 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 36 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 892.1
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 337
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.071118 |  | ACT. SYS (BBL) | 1272.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | XZ516 |  | 27 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 252.82 | 8.7631 |  | RESV. SYS (BBL) | 802
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JM9047 | [12 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 57 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x OPEN JETS | [12 empty] | TOTAL | 2074.6
PV |  | 29 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 22 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 95384
GEL ST. |  | 8/11 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 25011
WL (ml/30 min) |  | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5071
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.7 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 120395
ALK (FILT.) |  | 0.4/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 619725
DIESEL % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 78000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 49750
KCl (mg/l) |  | 42710.1 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 98600
CHLORIDES (mg/l) |  | 75100 | JAR |  | ST. STAB 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 240 | 3 1/2" HWDPS | 95.22 | ST. STAB 2 |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 254.09 |  |  | MPCL | 5
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 33
SOLIDS % |  | 18.03 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 7.8 |  | BIT NO. 36 RR2 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 124
DAILY WELL COST (US$) |  | 31446.4517 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 28604477.8639 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 90.46% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43997 | 43997.0208 | 0.5 | DRL | PT-P | P/T | HELD PJSM. R/U & P/T CEMENT LINES AT 4700 PSI.
43997.0208 | 43997.1146 | 2.25 | DRL | PT-P | CIR | CIRCULATED THROUGH RIG PUMP MEANWHILE PREPARED MIX FLUID & WEIGHTED UP BATCH MIXED GASBLOK CEMENT SLURRY.
43997.1146 | 43997.2083 | 2.25 | DRL | PT-P | CMC | PUMPED 100 BBL LOW RHEOLOGY MUD OF 1.55 SG FROM RIG PUMP FOLLOWED BY 64 BBL MUDPUSH II SPACER OF 15 PPG AT 4.2 BPM. SWITCHED TO CEMENT UNIT, PUMPED 30 BBL BATCH MIXED GASBLOK CEMENT SLURRY OF 17 PPG AT 3 BPM. DROPPED DP DART. PUMPED 15 BBL MUDPUSH II SPACER & 10 BBL MUD. OBSERVED SLOW SUPPLY OF MUD TO CEMENT UNIT, SWITCHED TO RIG PUMP AND PUMPED 209 BBL MUD (TOTAL DISPLACEMENT - 234 BBL). OBSERVED NO INDICATION OF SINGLE WIPER PLUG (SWP) PINS SHEARING. SWP WAS NOT BUMPED. BLED OFF PRESSURE, FLOATS HOLDING.
43997.2083 | 43997.2292 | 0.5 | DRL | PT-P | SPK | P/U STRING 4M AND SET PACKER WITH 30 TON WEIGHT. OBSERVED CLEAR INDICATION OF PINS SHEARING. MAX SLACKED OFF WEIGHT ON PACKER 35 TON. R/D CEMENT HEAD.
43997.2292 | 43997.375 | 3.5 | DRL | PT-P | CIR | POOH 2 STANDS AND CIRCULATED FOR BOTTOMS UP. DUMPED 160 BBL CONTAMINATED MUD+SPACER+CEMENT. MAX WEIGHT RECEIVED AT SURFACE 13.8 PPG.
43997.375 | 43997.3854 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
43997.3854 | 43997.4062 | 0.5 | DRL | PT-P | POOH | POOH FROM 4634M TO 4475M.
43997.4062 | 43997.4271 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43997.4271 | 43997.7604 | 8 | DRL | PT-P | POOH | POOH FROM 4475M TO SURFACE.
43997.7604 | 43997.7917 | 0.75 | DRL | PT-P | POOH | L/D RUNNING TOOL. FOUND SWP WITH RUNNING TOOL & DP DART STUCK INSIDE SWP DUE TO ACCUMULATION OF DP'S INTERNAL COATING FLAKES IN SWP.
43997.7917 | 43997.8438 | 1.25 | DRL | PT-P | BHA | M/U & RIH RR 6" PDC BIT (OPEN JETS) AS PER BHA DOWN TO 253M.
43997.8438 | 43998 | 3.75 | DRL | PT-P | RIH | RIH FROM 253M TO 1713M. FLUSHED STRING AT 1685M. OBSERVED ABNORMAL INCREASE AND FLUCTUATION IN PRESSURE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43998 | 43998.25 | 6 | DRL | PT-P | RIH | CONT'D RIH FROM 1713M TO 4554M & IS IN PROGRESS. FILLED STRING EVERY 25 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | BATCH MIXED GASBLOK CEMENT SLURRY OF 17 PPG & PERFORMED CEMENT JOB AS PER PLAN. SET LINER TOP PACKER. POOH 2 STANDS & CIRCULATED BOTTOMS UP. POOH TO SURFACE & L/D RUNNING TOOL. RIH RR 6" PDC BIT (OPEN JETS) AS PER BHA DOWN TO 1713M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH DOWN TO BOTTOM. TAG TOP OF 5" LINER. CIRCULATE & POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14