## DDR#41
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 41
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2355 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 40.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2355 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-01-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2203
DEPTH, MD (M) |  | 2355 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 839
MW IN (SG) |  | 1.52 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 3042
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 111
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 1.8
µ FUNNEL (SEC) |  |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 3553
PV |  | 35 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 126500
GEL ST. |  | 8/32 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 23500
WL (ml/30 min.) |  | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 25000
ALK (MUD) |  | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 150000
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 42000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 150000
KCl (mg/l) |  | 53387.6 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 193880
CHLORIDES |  | 25000 | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 442000
CALCIUM |  | 160 | 8" DCS |  | STAB - 2 & 3 |  | HSI | [14 empty] | POB
OIL% |  | 2 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
DIESEL % |  | 2 | BHA ROT. HRS |  |  |  | BIT No. 3RR3 |  | 2/3/WT/T,S/IN/ER/TD |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 24
SOLIDS % |  | 16.82 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 6
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2248 |  | 2.52 |  | 109.3 |  |  | 0.23 |  | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 29369 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2277 |  | 2.47 |  | 105.15 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3752474 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2304 |  | 2.84 |  | 111.01 |  |  | 0.51 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 20.79% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2335 |  | 3.34 |  | 105.62 |  |  | 0.56 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 236
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2355 |  | 180 / 265 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2355 |  | 175 / 263 |  | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43130 | 43130.0521 | 1.25 | DRL | PT-P | POOH | CONT'D POOH FROM 438 M TO 182 M.
43130.0521 | 43130.1354 | 2 | DRL | PT-P | BHA | RESUMED POOH BHA FROM 182 M TO SURFACE. MEANWHILE L/DOWN 3 X 9 1/2'' DC'S + JAR + 3 X STABS + BIT
43130.1354 | 43130.1979 | 1.5 | DRL | PT-P | CRA | REPLACED UPPER PIPE RAMS WITH 13.375'' CSG RAMS.
43130.1979 | 43130.2292 | 0.75 | DRL | PT-P | BOPT | RETRIEVED WEAR BUSHING. P/UP AND M/UP TEST PLUG ASSY. INSTALLED SAME. CLOSED BOP, P/TESTED BONNET SEALS @ 400 / 2700 PSI FOR 5 / 10 MINS, OK.
43130.2292 | 43130.3229 | 2.25 | DRL | PT-P | RU | R/UP W.FORD TRS GEARS. CHANGED TDS LINKS TO LONG LINKS, INSTALLED W.FORD FILLING & CIRCULATING DEVICE.
43130.3229 | 43130.375 | 1.25 | DRL | NPT-UP | RC | PJSM. P/UP 1ST JOINT + F/SHOE. WHILE FILLING UP 1ST JT + F/SHOE THROUGH W.FORD LA FLEUR, OBSERVED LEAKAGE IN LA FLEUR VALVE. TRIED TO FIX IT, NO SUCCESS. REMOVED LA FLEUR HOSE. R/UP FILL UP HOSE FOR CSG FILL UP.
43130.375 | 43130.6354 | 6.25 | DRL | PT-P | RC | P/U & M/U 13.375" SHOE TRACK, 72PPF, SM110TT (F/SHOE + 2 X 13.375" CSG JNTS + F/COLLAR = 25.858 M) AND RIH. CHECKED INTEGRITY OF FLOATS - OK. CONT'D RIH FROM 26 M TO 433 M. FILLED UP CSG EVERY 5 JOINTS.
43130.6354 | 43130.6667 | 0.75 | DRL | PT-P | RC | REPLACED SIDE DOOR ELEVATOR + HAND SLIPS WITH SPIDER ELEVATOR AND SPIDER SLIPS.
43130.6667 | 43130.7708 | 2.5 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 433 M TO 599 M. FILLED UP CSG EVERY 5 JOINTS.
43130.7708 | 43130.7917 | 0.5 | DRL | PT-P | CIR | CIRCULATED CASING CONTENTS AND RECORDED WEIGHT.
43130.7917 | 43131 | 5 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 599 M TO 1020 M. (81 JTS IN HOLE, REMAINING 109 JTS) FILLED UP CSG EVERY 5 JOINTS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43131 | 43131.1354 | 3.25 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 1020 M TO 1209 M. FILLED UP CSG EVERY 5 JOINTS.
43131.1354 | 43131.1458 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION.
43131.1458 | 43131.25 | 2.5 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 1209 M TO 1435 M. FILLED UP CSG EVERY 5 JOINTS. (118 JTS IN HOLE, REMAINING 72 JTS)
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | RIH 13.375'' CSG IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 438 M TO SURFACE. L/DOWN STABS+ DC'S + BIT. REPLACED UPPER PIPE RAMS WITH CASING RAMS, P/TESTED SAME, R/UP W.FORD TRS GEARS. 13.375'' CSG JOB IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 13 3/8'' CSG TO BOTTOM, 13 3/8'' CSG CMT JOB.
REMARKS |  |  | OBSERVED FREQUENT W.FORD POWER TONG FAILURES WHILE M/UP CONNECTIONS. (STUCK ON CSG JOINTS)
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14