## DDR#41
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 41
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 40.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 4RR3 |  | BHA NO. |  |  | 9 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 159
CHECK TIME | 16:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2199
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.11629 |  | PITS (BBL) | 798
MW IN (SG) | 2.06 | 2.04 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TFH519S |  | BIT SUB (F.V) |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.08 | 0.34888 |  | ACT. SYS (BBL) | 3156
MW OUT (SG) |  | 1.98 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E260745 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.31 | 0.74622 |  | RESV. SYS (BBL) | 1294
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL)
FL TEMP. °F |  | 163.4 | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 5 X 16 |  | STRING STAB |  |  | 17.375 | 3.1875 |  | 7 5/8 REG |  | 2.36 | 0.76237 |  | KILL MW (SG)
µ FUNNEL (SEC) | 67 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2420 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.54 | 5.9891 |  | TOTAL | 4450
PV | 39 | 35 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.19 | 0.70745 |  | DIESEL (LTR)
YIELD POINT | 26 | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.78 | 11.8814 |  | RIG TANK | 119341
GEL ST. | 14/22 | 14/22 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.95 | 0.30689 |  | CAMP TANK | 15062
WL (ml/30 min) | 7 | 9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.49 | 4.1288 |  | CONSUMED | 8229
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | DRILLING JAR |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 9.58 | 2.1392 |  | RECEIVED | 49000
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.42 | 4.1132 |  | TOTAL | 134403
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X/OVER |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | WATER (LTR)
PH | 9.5 | 9.7 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.4 | 8.4486 |  | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 66500
KCl (mg/l) | 58726.4 | 56629 | JAR | 51.16 | STAB - 1 | 51.16 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 31500
CHLORIDES (mg/l) | 28000 | 27000 | 5 1/2" HWDPS | 51.16 | STAB - 2 | 51.16 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 525000
HARDNESS (mg/l) | 320 | 320 | 9 1/2" DCS | 51.16 | STAB - 3 | 51.16 | HSI | [14 empty] | POB
SAND % | 0.2 | 0.15 | 8" DCS | 51.16 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.45 |  |  | MPCL | 7
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 51.16 |  | BIT NO. 4RR3 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 34
SOLIDS % | 34.67 | 34.97 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 10 | 8.8 | CIRC. HRS |  | 35.18 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 127
DAILY WELL COST (US$) |  | 48300.28 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3918949.0192 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 19.69% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43629 | 43629.0833 | 2 | EVAL | PT-P | BHA | POOH BHA FROM 63M TO SURFACE, RETRIEVED TOTCO & RECORDED 1 DEG DEVIATION @ 2410M. FOUND 1ST & 3RD S. STAB FULLY BALLED UP AND 2ND S. STAB & BIT PARTIALLY BALLED UP. L/DOWN D. JAR & 3 X S. STABS.
43629.0833 | 43629.125 | 1 | EVAL | PT-P | RU | R/UP SLB W/L LOGGING GEAR. MEANWHILE MONITORED WELL THRU TRIP TANK.
43629.125 | 43629.1979 | 1.75 | EVAL | PT-P | W/L | PJSM. R/UP & M/UP LOGGING TOOLS. FUNCTION TESTED & CALIBRATED SAME. MEANWHILE MONITORED WELL THRU TRIP TANK.
43629.1979 | 43629.3958 | 4.75 | EVAL | PT-P | W/L | RIH LOGGING TOOLS & RECORDED SLB "BHC-LDL-GR-PPC-GPIT" W/LINE LOGS AS PER PROGRAM. MEANWHILE MONITORED WELL THRU TRIP TANK.
43629.3958 | 43629.4583 | 1.5 | EVAL | PT-P | RD | R/DOWN W/L LOGGING GEAR. MEANWHILE MONITORED WELL THRU TRIP TANK. RECORDED 13 BBL GAIN DURING W/LINE LOGGING.
43629.4583 | 43629.5521 | 2.25 | DRL | PT-P | BHA | P/UP, M/UP & RIH SAME 17 1/2" PDC BIT NO. 4RR3 WITH SAME 03 X STRING STABS ROTARY BHA TO 215M, FILLED & FLUSHED STRING WITH MUD. WHILE RIH P/UP JAR & 3 X S. STABS FROM CATWALK.
43629.5521 | 43629.8229 | 6.5 | DRL | PT-P | RIH | RIH BHA FROM 215M TO 2333M ON ELEVATORS & OBSERVED OBSTRUCTION @ 2333M. WHILE RIH FILLED UP STRING WITH MUD. RECORDED 15 BBL GAIN DURING RIH.
43629.8229 | 43630 | 4.25 | DRL | PT-P | RW | HARD REAMED FROM 2333M TO 2411M. OBSERVED EXCESSIVE CUTTINGS & MECHANICAL CAVINGS ON BTM UP. RECORDED MIN MUD CUT OF 1.37 SG ON BTM UP.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43630 | 43630.0312 | 0.75 | DRL | PT-P | RW | CONT'D HARD REAMED FROM 2411M TO BTM @ 2420M.
43630.0312 | 43630.25 | 5.25 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZE & CONDITION MUD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATING TO HOMOGENIZE MUD
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH BHA FROM 63M TO SURFACE. RECORDED "BHC-LDL-GR-PPC-GPIT" SLB W/LINE LOGS. M/UP & RIH SAME 17 1/2" PDC BIT NO. 4RR3 WITH SAME ROTARY BHA TO 2333M & OBSERVED OBSTRUCTION. HARD REAMED FROM 2333M TO 2411M. RECORDED MIN MUD CUT OF 1.37 SG ON BTM UP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE TO HOMOGENIZE & CONDITION MUD. CONDUCT SHORT WIPER TRIP & POOH TO SURFACE TO RIH 13 5/8" X 13 3/8" CASING.
REMARKS |  |  | CONDUCTED FIRE & STRETCHER DRILL AT RIG SITE.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14