## DDR # 411
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 411
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 410.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4934 | 4900 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 86 |  | BHA NO. |  |  | 104 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 219.9
CHECK TIME | 11:00 | 23:29 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 37 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 651.1
DEPTH, MD (M) | 4934 | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 4.125 |  | INSERT BLADED MILL |  |  | 4.125 |  |  | 2 3/8 REG |  | 0.85 |  |  | PITS (BBL) | 369
MW IN (SG) | 1.55 | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | WEATHERFORD |  | BIT SUB |  |  | 3.125 | 1.125 |  | 2 7/8 HT PAC |  | 0.36 |  |  | ACT. SYS (BBL) | 1240
MW OUT (SG) |  | 1.55 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | INSERT BLADED MILL |  | 15x DC |  |  | 3.125 | 1.5 |  | 2 7/8 HT PAC |  | 134.05 |  |  | RESV. SYS (BBL) | 827
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 1778196 | [12 empty] | KILL MUD (BBL)
FL TEMP. °F |  | 110 | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 63 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 4 x PORTS | [12 empty] | TOTAL | 2067
PV | 30 | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 24 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 112526
GEL ST. | 10/13 | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 23644
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 7001
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 28000
ALK (MUD) | 0.7 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 136170
ALK (FILT.) | 0.4/1.3 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 590475
DIESEL % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 81000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 38625
KCl (mg/l) | 42710.1 | 42519.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 42000
CHLORIDES (mg/l) | 75100 | 75000 | JAR |  | ST. STAB 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 240 | 200 | 3 1/8" DC | 2.8 | ST. STAB 2 |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % | 3 | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 135.26 |  |  | MPCL | 5
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 2.8 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 4 |  |  | MPCL SERV | 33
SOLIDS % | 18.13 | 18.14 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 3.8 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802.11/4782.87 |  | 26.53 |  | 307.03 |  |  | 4.37 |  | MWD |  | TOTAL | 123
DAILY WELL COST (US$) |  | 32219.075 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4830.50/4808.17 |  | 27.55 |  | 319.16 |  |  | 5.92 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 28729859.9873 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4858.57/4832.97 |  | 28.23 |  | 317.95 |  |  | 0.95 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 90.85% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4887.52/4858.39 |  | 29.04 |  | 315.78 |  |  | 1.37 |  | MWD |  | FIT (EMW)
[7 empty] | 5'' LINER- ST3 (Q125, 18#, VAMFJL) |  |  |  | 4929.5 / 4696 (TOL) | 4917.55/4884.91 |  | 26.89 |  | 313.97 |  |  | 2.31 |  | MWD |  | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43999 | 43999.0417 | 1 | DRL | NPT-UP | DP | L/D 8x 3 1/2" 13.3 PPF DP STANDS RACKED BACK IN DERRICK SINGLE BY SINGLE.
43999.0417 | 43999.0729 | 0.75 | DRL | PT-P | BHA | L/D 3x 4 3/4" DC STANDS RACKED BACK IN DERRICK SINGLE BY SINGLE.
43999.0729 | 43999.125 | 1.25 | DRL | PT-P | RU | R/U WELLSERVE POWER TONG & WFD 2 7/8"' STRING HANDLING TOOLS.
43999.125 | 43999.2292 | 2.5 | DRL | PT-P | BHA | HELD PJSM. P/U & M/U 4 1/8" INSERT BLADED MILL & RIH WITH SLIM BHA DOWN TO 135M. WHILE RIH, P/U 15x 3 1/8" DC FROM CATWALK SINGLE BY SINGLE. DRIFTED EACH JOINT & FLUSHED WITH WATER.
43999.2292 | 43999.3333 | 2.5 | DRL | PT-P | RIH | RIH FROM 135M TO 250M. WHILE RIH, P/U 12x 2 7/8" DP FROM CATWALK SINGLE BY SINGLE. DRIFTED EACH JOINT & FLUSHED WITH WATER. CIRCULATED TWICE DRILL STRING VOLUME.
43999.3333 | 43999.6042 | 6.5 | DRL | NPT-UP | RIH | RIH FROM 250M TO 1567M. WHILE RIH, P/U 138x 3 1/2" 15.5 PPF DP FROM CATWALK SINGLE BY SINGLE. DRIFTED EACH JOINT & FLUSHED WITH WATER. CIRCULATED TWICE DRILL STRING VOLUME.
43999.6042 | 43999.8646 | 6.25 | DRL | PT-P | RIH | RIH FROM 1567M TO 4695M.
43999.8646 | 44000 | 3.25 | DRL | PT-P | DC | WASHED DOWN FROM 4695M TO 4700M. OBSERVED 3-4 TON COMPRESSION. DRILL OUT MODERATELY HARD - HARD IN PARTS SOFT CEMENT FROM 4700M TO 4762M. (WOB- 0-2 TON, RPM-30-40, GPM- 150, TORQUE- 1-2 KFT-LB, SPP- 1950-2050 PSI).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
44000 | 44000.25 | 6 | DRL | PT-P | DC | DRILL OUT MODERATELY HARD - HARD IN PARTS SOFT CEMENT FROM 4762M TO 4894M & IS IN PROGRESS. (WOB- 0-2 TON, RPM- 40, GPM- 150, TORQUE- 1-3 KFT-LB, SPP- 1750-2350 PSI).
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | DRILLING OUT CEMENT IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | L/D 8x 3 1/2" DP STANDS & 3x 4 3/4" DC STANDS SINGLE BY SINGLE. RIH 4 1/8" INSERT BLADED MILL WITH SLIM STRING DOWN TO 4695M. WHILE RIH, P/U 15x 3 1/8" DC, 12x 2 7/8" DP & 138x 3 1/2" 15.5 PPF DP SINGLE BY SINGLE. WASHED DOWN FROM 4695M TO 4700M. DRILL OUT MODERATELY HARD - HARD IN PARTS SOFT CEMENT FROM 4700M TO 4762M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL OUT L/COLLAR, F/COLLAR & SHOE TRACK CEMENT. CIRCULATE & POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14