## DDR # 413
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 413
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | 4927M MD / 4893M TVD PBTD |  |  | DAYS SINCE SPUD: | [6 empty] | 412.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: | [8 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 87 |  | BHA NO. |  |  | 105 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 229.5
CHECK TIME |  | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 37 RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 638.1
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 4.125 |  | INSERT BLADED MILL |  |  | 4.125 |  |  | 2 3/8 REG |  | 0.85 |  |  | PITS (BBL) | 353
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | WEATHERFORD |  | 5" CSG SCRAPPER |  |  | 5 | 1.125 |  | 2 3/8 REG |  | 1.68 |  |  | ACT. SYS (BBL) | 1220.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | INSERT BLADED MILL |  | X-OVER |  |  | 3.125 | 1.125 |  | 2 7/8 HT PAC |  | 0.54 |  |  | RESV. SYS (BBL) | 903
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 1778196 |  | 15x DC |  |  | 3.125 | 1.5 |  | 2 7/8 HT PAC |  | 134.05 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 11x DP |  |  | 2.875 | 1.5 |  | 2 7/8 HT PAC |  | 105.54 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 4 x PORTS |  | X-OVER |  |  | 5 | 1.5625 |  | 3 1/2 IF |  | 0.34 |  |  | TOTAL | 2123.6
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 7" CSG SCRAPPER |  |  | 7 | 2 |  | 3 1/2 IF |  | 1.61 |  |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 105954
GEL ST. |  | 11/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 22252
WL (ml/30 min) |  | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4326
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 128206
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 520601
DIESEL % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 82000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 50125
KCl (mg/l) |  | 42138.1 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 42000
CHLORIDES (mg/l) |  | 74800 | JAR |  | ST. STAB 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 160 | 3 1/8" DC | 22.2 | ST. STAB 2 |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  | 3 | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 244.61 |  |  | MPCL | 5
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 5.6 |  |  | MPCL SERV | 36
SOLIDS % |  | 18.15 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 0.66 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 126
DAILY WELL COST (US$) |  | 33443.9292 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 28792532.1998 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 91.05% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | 5'' LINER- ST3 (Q125, 18#, VAMFJL) |  |  |  | 4932 / 4698 (TOL) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
44001 | 44001.2812 | 6.75 | DRL | PT-P | POOH | CONT'D POOH FROM 3638M TO 250M.
44001.2812 | 44001.3021 | 0.5 | DRL | PT-P | RU | R/U WELLSERVE POWER TONG & WFD 2 7/8"' STRING HANDLING TOOLS.
44001.3021 | 44001.3229 | 0.5 | DRL | PT-P | DP | POOH FROM 250M TO 135M. WHILE POOH, L/D 12x 2 7/8" DP SINGLE BY SINGLE.
44001.3229 | 44001.375 | 1.25 | DRL | PT-P | BHA | POOH BHA TO SURFACE. WHILE POOH, L/D 12x 3 1/8" DC SINGLE BY SINGLE. L/D BIT SUB.
44001.375 | 44001.4062 | 0.75 | DRL | PT-P | BHA | M/U RR 4 1/8" INSERT BLADED MILL WITH 5" CSG SCRAPPER & RIH DOWN TO 56M. WHILE RIH, P/U 3x 3 1/8" DC SINGLE BY SINGLE.
44001.4062 | 44001.4375 | 0.75 | DRL | NPT-UP | E/F | OBSERVED PROBLEM IN WELLSERVE POWER TONG. L/D FAULTY POWER TONG & R/U BACK UP POWER TONG.
44001.4375 | 44001.5104 | 1.75 | DRL | PT-P | BHA | RIH FROM 56M TO 270M. WHILE RIH, P/U 9x 3 1/8" DC, 11x 2 7/8" DP, X-OVER & 7" CSG SCRAPPER SINGLE BY SINGLE.
44001.5104 | 44001.5312 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
44001.5312 | 44001.9062 | 9 | DRL | PT-P | RIH | RIH FROM 270M TO 4698M.
44001.9062 | 44001.9792 | 1.75 | DRL | PT-P | COC | WORKED ON 5" CSG SCRAPPER FROM 4698M TO 4927M & 7" CSG SCRAPPER FROM 4454M TO 4683M SIMULTANEOUSLY. WASHED DOWN LAST SINGLE FROM 4918M TO 4927M.
44001.9792 | 44002 | 0.5 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
44002 | 44002.1042 | 2.5 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP TILL SHAKERS CLEAN.
44002.1042 | 44002.1146 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
44002.1146 | 44002.25 | 3.25 | DRL | PT-P | POOH | POOH FROM 4927M TO 3860M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 3638M TO SURFACE. RIH RR 4 1/8" INSERT BLADED MILL WITH 5" & 7" CSG SCRAPPERS IN TANDEM DOWN TO 4927M. WORKED ON 5" CSG SCRAPPER FROM 4698M TO 4927M & 7" CSG SCRAPPER FROM 4454M TO 4683M SIMULTANEOUSLY. CIRCULATED TO CLEAN HOLE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. CONDUCT CBL-VDL OF 5" LINER.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14