## DDR # 415
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 415
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4934 | 4900 |  |  | 4927M MD / 4893M TVD PBTD |  |  | DAYS SINCE SPUD: | [6 empty] | 414.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: | [8 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-06-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 227.9
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 638.5
DEPTH, MD (M) |  | 4934 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 471
MW IN (SG) |  | 1.4 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1337.4
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 1048
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2385.4
PV |  | 22 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 32 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 99472
GEL ST. |  | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 20920
WL (ml/30 min) |  | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3448
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 120392
ALK (FILT.) |  | 0.3/1.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 541522
DIESEL % |  |  | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 82000
KCl (%) |  | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 70249
KCl (mg/l) |  | 37180.7 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 53600
CHLORIDES (mg/l) |  | 50000 | JAR |  | ST. STAB 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 120 | 3 1/8" DC | 22.2 | ST. STAB 2 |  | TFA (IN²) | [15 empty] | POB
MAX SHIELD % |  |  | PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 5
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 51
SOLIDS % |  | 13.44 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 2.3 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 31622000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 142
DAILY WELL COST (US$) |  | 70801.2683 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 28892264.4807 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 91.37% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | 5'' LINER- ST3 (Q125, 18#, VAMFJL) |  |  |  | 4932 / 4698 (TOL) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-06-06 | 2020-07-06 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-06-12 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
44003 | 44003.125 | 3 | DRL | NPT-UP | W/L | CONT'D POOH TO SURFACE. REPLACED USIT SUB.
44003.125 | 44003.3854 | 6.25 | DRL | PT-P | W/L | RIH AGAIN FOR 5" LINER CASED HOLE LOGGING (USIT-CBL-VDL-CCL-GR). WHILE LOGGING, OBSERVED SAME PROBLEM OF DATA ACQUISITION QUALITY OF USIT. CONDUCTED W/L LOGGING (CBL-VDL-CCL-GR). POOH & L/D W/L TOOLS.
44003.3854 | 44003.3958 | 0.25 | DRL | PT-P | RD | R/D WIRELINE GEARS.
44003.3958 | 44003.4167 | 0.5 | DRL | NPT-P | RS | SERVICED TDS. WELL HANDED OVER TO PRODUCTION DEPT FOR PRODUCTION TESTING AT 10:00 HRS ON JUNE 21, 2020.
44003.4167 | 44003.4896 | 1.75 | TEST | PT-P | RIH | RIH OPEN ENDED SLIM STRING WITH BIT SUB DOWN TO 249M. WHILE RIH, P/U 3 1/8" BIT SUB, 15x 3 1/8" DC & 12x 2 7/8" DP SINGLE BY SINGLE.
44003.4896 | 44003.8854 | 9.5 | TEST | PT-P | RIH | CONT'D RIH OEDP FROM 249M TO 4924M.
44003.8854 | 44003.9062 | 0.5 | TEST | PT-P | CT | HELD PJSM. PRESSURE TESTED 5" LINER AT 3500 PSI WITH RIG PUMP FOR 10 MIN, OK. BLED OFF PRESSURE.
44003.9062 | 44004 | 2.25 | TEST | PT-P | DISP | DISPLACED 1.55 SG MUD IN HOLE WITH 1.40 SG MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
44004 | 44004.0417 | 1 | TEST | PT-P | DISP | CONT'D DISPLACING 1.55 SG MUD IN HOLE WITH 1.40 SG MUD.
44004.0417 | 44004.1667 | 3 | TEST | PT-P | CIR | CIRCULATED TO CONDITION & HOMOGENIZE MUD.
44004.1667 | 44004.1771 | 0.25 | TEST | PT-P | FC | FLOW CHECK, WELL STATIC.
44004.1771 | 44004.25 | 1.75 | TEST | PT-P | POOH | POOH FROM 4927M TO 4151M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH W/L TOOLS & REPLACED USIT SUB. RIH; WHILE LOGGING, OBSERVED SAME PROBLEM OF DATA ACQUISITION QUALITY OF USIT. CONDUCTED W/L LOGGING (CBL-VDL-CCL-GR). POOH & L/D W/L TOOLS. WELL HANDED OVER TO PROD DEPT FOR PRODUCTION TESTING AT 10:00 HRS ON JUNE 21, 2020. RIH OEDP DOWN TO 4924M. P/T 5" LINER AT 3500 PSI, OK. DISPLACED 1.55 SG MUD IN HOLE WITH 1.40 SG MUD.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE AND L/D EXCESS DRL STRING. RIH TCP GUNS.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14