## DDR#42
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 42
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-01
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2355 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 41.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2355 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-01-31 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2283
DEPTH, MD (M) |  | 2355 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | F/SHOE |  |  | 13.375 |  |  | VAMTOP |  | 0.73 |  |  | PITS (BBL) | 779
MW IN (SG) |  | 1.52 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 1ST JT |  |  | 13.375 |  |  | VAMTOP |  | 12.03 |  |  | ACT. SYS (BBL) | 3062
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 2ND JT |  |  | 13.375 |  |  | VAMTOP |  | 12 |  |  | RESV. SYS (BBL) | 247
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | F/COLLAR |  |  | 13.375 |  |  | VAMTOP |  | 1.1 |  |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 92 X 72#, SM110TT |  |  | 13.375 |  |  | VAMTOP |  | 1101.912 |  |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) |  |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 96 X 72#, P-110 |  |  | 13.375 |  |  | VAMTOP |  | 1222.275 |  |  | TOTAL | 3709
PV |  | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 1 X PUP JT, 72 #, P-110 |  |  | 13.375 |  |  | VAMTOP |  | 6.02 |  |  | DIESEL (LTR)
YIELD POINT |  | 22 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 121500
GEL ST. |  | 7/26 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 23000
WL (ml/30 min.) |  | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 144500
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 140000
KCl (mg/l) |  | 53387.6 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 136740
CHLORIDES |  | 25000 | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 160 | 8" DCS |  | STAB - 2 & 3 |  | HSI | [14 empty] | POB
OIL% |  | 2 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 2356.067 |  |  | MPCL | 4
DIESEL % |  | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 26
SOLIDS % |  | 16.82 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 5
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2248 |  | 2.52 |  | 109.3 |  |  | 0.23 |  | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 32158 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2277 |  | 2.47 |  | 105.15 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3784738 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2304 |  | 2.84 |  | 111.01 |  |  | 0.51 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 20.97% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2335 |  | 3.34 |  | 105.62 |  |  | 0.56 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43131 | 43131.1354 | 3.25 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 1020 M TO 1209 M. FILLED UP CSG EVERY 5 JOINTS.
43131.1354 | 43131.1458 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION.
43131.1458 | 43131.75 | 14.5 | DRL | PT-P | RC | CONT'D RIH 13.375'' CSG FROM 1209 M TO 2346 M. FILLED UP STRING EVERY 5 JOINTS. (TOTAL 190 JOINTS IN HOLE)
43131.75 | 43131.8333 | 2 | DRL | PT-P | RW | P/UP & M/UP LANDING JOINT (1 X PUP JOINT + X/O + CIRCULATING SWEDGE). WASHED DOWN FROM 2346 M TO 2354.5 M.
43131.8333 | 43131.9271 | 2.25 | DRL | PT-P | CIR | CIRCULATED BOTTOM UP. KEPT CIRCULATING TILL SHAKERS CLEANED.
43131.9271 | 43131.9583 | 0.75 | DRL | PT-P | RU | P/UP SCHL CMT HEAD PRE-LOADED WITH TOP/BOTTOM PLUG. M/UP SAME ON LAST JOINT. CONNECTED RIG & CMT LINES.
43131.9583 | 43132 | 1 | DRL | PT-P | CIR | RESUMED CIRCULATION TO CONDITION MUD, MEANWHILE MIXED FLUID FOR CEMENT JOB.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43132 | 43132.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATING HOLE TO CONDITION MUD MEANWHILE MIXED FLUID FOR CMT JOB.
43132.0521 | 43132.0625 | 0.25 | DRL | PT-P | SM | CONDUCTED PRE JOB SAFETY MEETING FOR 13.375'' CSG CEMENTATION WITH RIG /CMT CREW.
43132.0625 | 43132.0833 | 0.5 | DRL | PT-P | P/T | FLUSHED CMT LINES WITH WATER. CLOSED VALVE, P/TESTED CMT LINES AT 3500 PSI, HELD FOR 10 MINS. OK.
43132.0833 | 43132.25 | 4 | DRL | PT-P | CMC | PUMPED 150 BBL MUDPUSH II (13.5 PPG) THROUGH RIG PUMPS. DROPPED BOTTOM PLUG. SWITCHED OVER TO CMT UNIT, FLY MIXED & PUMPED 1132 BBL LEAD SLURRY (14.5 PPG) @ 5-7 BPM. PUMPING BATCHED MIXED, TAIL SLURRY (15.8 PPG) IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | 13.375'' CSG CMT JOB IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH FROM 1020 M TO 2354.5 M. WASHED DOWN LAST JOINT. CONDITIONED HOLE PRIOR TO CMT JOB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION PRIOR TO CMT, CMT 13.375'' CSG, N/D BOP, CSG HANGER, CUT AND DRESS CSG, WELLHEAD JOB, TEST WELLHEAD, N/U BOP, BOPT, WOC
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14