## DDR#43
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 43
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2355 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 42.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2355 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-02-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL)
DEPTH, MD (M) |  | 2355 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 843
MW IN (SG) |  | 1.52 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 843
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 1245
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 1.8
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2488
PV |  | 35 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 22 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 117500
GEL ST. |  | 7/26 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 22500
WL (ml/30 min.) |  | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 140000
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 150000
KCl (mg/l) |  | 53387.6 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 182320
CHLORIDES |  | 25000 | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 160 | 8" DCS |  | STAB - 2 & 3 |  | HSI | [14 empty] | POB
OIL% |  | 2 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 4
DIESEL % |  | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 19
SOLIDS % |  | 16.82 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 5
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2248 |  | 2.52 |  | 109.3 |  |  | 0.23 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 578472 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 2277 |  | 2.47 |  | 105.15 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4363210 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2304 |  | 2.84 |  | 111.01 |  |  | 0.51 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 24.17% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2335 |  | 3.34 |  | 105.62 |  |  | 0.56 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | CAMERON CHINA | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CAMERON CHINA | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | CAMERON CHINA | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS | CAMERON CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43109 | 43132.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD MEANWHILE MIXED FLUID FOR CMT JOB.
43132.0521 | 43132.0625 | 0.25 | DRL | PT-P | SM | CONDUCTED PRE JOB SAFETY MEETING FOR 13.375'' CSG CEMENTATION WITH RIG /CMT CREW.
43132.0625 | 43132.0833 | 0.5 | DRL | PT-P | P/T | FLUSHED CMT LINES WITH WATER. CLOSED VALVE, P/TESTED CMT LINES AT 3500 PSI, HELD FOR 10 MINS. OK.
43132.0833 | 43132.3542 | 6.5 | DRL | PT-P | CMC | PUMPED 150 BBL MUDPUSH II (13.5 PPG) THROUGH RIG PUMPS. DROPPED BOTTOM PLUG. SWITCHED OVER TO CMT UNIT, FLY MIXED & PUMPED 1132 BBL LEAD SLURRY (14.5 PPG) @ 5-7 BPM. PUMPED 200 BBL BATCHED MIXED, TAIL SLURRY (15.8 PPG) @ 5-6 BPM. DROPPED TOP PLUG. POST FLUSHED 10 BBL MUDPUSH II (13.5 PPG). SWITCHED OVER TO RIG PUMP. DISPLACED 1100 BBL THROUGH RIG PUMPS. SWITCHED OVER TO CMT UNIT AGAIN FOR FINAL DISPLACEMENT. DISPLACED 22 BBL THROUGH CMT UNIT. NO INDICATION OBSERVED FOR PLUGS BUMPED. DISPLACED HALF SHOE TRACK VOLUME = 6.2 BBL., OBSERVED NO INDICATION. (TOTAL DISPLACEMENT = 10 + 1100 + 22 + 6 = 1138 BBLS, DUMPED 260 BBL NEAT CMT DURING THE JOB.)
43132.3542 | 43132.4271 | 1.75 | DRL | PT-P | NDB | MADE ARRANGEMENTS, DISCONNECTED FLOW LINE. LIFTED BOP STACK WITH BOP TROLLEY.
43132.4271 | 43132.4479 | 0.5 | DRL | PT-P | WH | CENTERED 13.375'' CSG AND SET SLIP AND SEAL ASSY IN CASING HEAD HOUSING. SLACKED OFF CSG WEIGHT ON SLIP AND SEAL ASSY.
43132.4479 | 43132.4688 | 0.5 | DRL | PT-P | CC | P/UP BOP, ROUGH CUT 13.375'' CSG.
43132.4688 | 43132.5 | 0.75 | DRL | PT-P | RD | R/DOWN CMT HEAD, SPIDER ELEVATOR. L/D LANDING JOINT + CUT JOINT.
43132.5 | 43132.5625 | 1.5 | DRL | PT-P | NDB | N/DOWN 20 3/4'' BOP STACK.
43132.5625 | 43132.625 | 1.5 | DRL | PT-P | CC | FINAL CUT 13.375'' CSG AT 6'' WITH HOT CUTTER. BEVELED AND DRESSED SAME.
43132.625 | 43132.7917 | 4 | DRL | PT-P | WH | N/UP 21-1/4''-5K X 13 5/8''-10K CASING HEAD SPOOL. P/TESTED FS SEALS, CAVITY, HANGER SEAL & FLANGE @ 2300 PSI - OK.
43132.7917 | 43133 | 5 | DRL | PT-P | NUB | N/UP 13 5/8"-10K SPACER SPOOL, LOWER PIPE RAMS, DOUBLE PIPE RAMS & ANNULAR BOP. NIPPLING UP BOP STACK IN PROGRESS
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43133 | 43133.0417 | 1 | DRL | PT-P | NUB | CONT'D N/UP BOP. H/UP CHOKE & KILL LINES.
43133.0417 | 43133.25 | 5 | DRL | NPT-UP | RR | WOC, MEANWHILE WORK ON TDS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | WOC MEANWHILE WORK ON TDS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED PRIOR TO CMT, 13.375'' CMT JOB, N/D BOP, CSG HANGER, CUT AND DRESS CSG, WELLHEAD JOB, P/TESTED WELLHEAD, N/U BOP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WOC, WORK ON TDS, P/T BOP STACK, RIH WITH SLICK BHA FOR COC, MEANWHILE P/UP 5.5'' DP'S FOR NEXT PHASE. COC. CSG TEST. DRILL 12 1/4'' NEW HOLE. FIT.
REMARKS |  |  | W.FORD TRS CREW & EQUIPMENT RELEASED ON 01-02-2018- D&M CREW & EQUIPMENT ARRIVED ON 01-02-2018
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+14