## DDR#43
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 43
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 42.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 215
CHECK TIME | 16:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2183
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | FLOAT SHOE |  |  | 14.5 | 12.375 |  | VAMTOP |  | 1.33 | 88.2 PPF |  | PITS (BBL) | 695
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 4 X 13 5/8" CSG JTS |  |  | 13.625 | 12.375 |  | VAMTOP |  | 45.35 | 88.2 PPF |  | ACT. SYS (BBL) | 3093
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FLOAT COLLAR |  |  | 14.5 | 12.375 |  | VAMTOP |  | 0.92 | 88.2 PPF |  | RESV. SYS (BBL) | 1305
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 35 X 13 5/8" CSG JTS |  |  | 13.625 | 12.375 |  | VAMTOP |  | 394.29 | 88.2 PPF |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 58 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 4398
PV | 39 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 132663
GEL ST. | 12/23 | 12/20 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 29631
WL (ml/30 min) | 7.8 | 7.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 6936
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 48000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 162294
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 320000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 155500
KCl (mg/l) | 56629 | 56629 | JAR | 71.45 | STAB - 1 | 71.45 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 10500
CHLORIDES (mg/l) | 27000 | 27000 | 5 1/2" HWDPS | 71.45 | STAB - 2 | 71.45 | TFA (IN²) | [14 empty] | TOTAL | 375000
HARDNESS (mg/l) | 320 | 320 | 9 1/2" DCS | 71.45 | STAB - 3 | 71.45 | HSI | [14 empty] | POB
SAND % | 0.15 | 0.15 | 8" DCS | 71.45 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 441.89 |  |  | MPCL | 7
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 71.45 |  | BIT NO. 4RR3 |  | 1-2-FC-A-X-I-DL-TD |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 36
SOLIDS % | 35.98 | 35.98 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 8.8 | 8.8 | CIRC. HRS |  | 55.68 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 128
DAILY WELL COST (US$) |  | 37232.8167 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4017392.6259 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 20.18% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 65
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 6 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43631 | 43631.2396 | 5.75 | DRL | PT-P | RW | PRECAUTIONARY BACK REAMED FROM 1332M TO 558M (INSIDE 20" CASING SHOE) TO AVOID SWABBING.
43631.2396 | 43631.25 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43631.25 | 43631.3021 | 1.25 | DRL | PT-P | POOH | POOH FROM 558M TO 215M (TOP OF BHA).
43631.3021 | 43631.3125 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43631.3125 | 43631.4167 | 2.5 | DRL | PT-P | BHA | POOH BHA FROM 215M TO SURFACE. OBSERVED 3 X S. STABS & BIT PARTIALLY BALLED UP. L/DOWN D. JAR, 3 X S. STABS, BIT SUB & BIT.
43631.4167 | 43631.5417 | 3 | DRL | PT-P | CRA | REPLACED 5 1/2" PIPE RAMS WITH 13 3/8" CSG RAMS. MEANWHILE SHIFTED WF TRS GEAR TO RIG FLOOR & M/UP ACP + PUP JOINT WITH BUCKING UNIT.
43631.5417 | 43631.5833 | 1 | DRL | PT-P | BOPT | P/UP & M/UP TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG. P/TESTED BONNET SEALS @ 1000 PSI FOR 5 MIN - OK. L/DOWN TEST PLUG ASSY.
43631.5833 | 43631.625 | 1 | DRL | PT-P | RU | R/UP WF TRS GEAR & INSTALLED ROTARY MOUNTED SPIDER SLIPS (RMS).
43631.625 | 43632 | 9 | DRL | PT-P | RC | HELD PJSM. P/UP, M/UP, THREAD LOCKED & RIH 13 5/8" CASING [88.2 PPF, P110, VAMTOP] SHOE TRACK (F/SHOE + 4 X 13 5/8" CSG JNTS + F/COLLAR = 47.60 M) TO 47M. OBSERVED FLOAT SHOE NOT DRAINING MUD WHILE CHECKING INTEGRITY, INSTALLED CIRCULATING & CIRCULATED TO OPEN FLOAT VALVES AND AGAIN CHECKED & CONFIRMED INTEGRITY OF FLOATS - FOUND OK. RIH 13 5/8" CASING FROM 47M TO 441M. WHILE RIH FILLED UP EVERY CASING JOINT, BROKE CIRCULATION @ 227M & INSTALLED CENTRALIZERS AS PER TALLY.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43632 | 43632.0833 | 2 | DRL | PT-P | RC | CONT'D RIH 13 5/8" CASING FROM 441M TO 565M. WHILE RIH FILLED UP EVERY CASING JOINT & INSTALLED CENTRALIZERS AS PER TALLY.
43632.0833 | 43632.125 | 1 | DRL | PT-P | CIR | INSTALLED CIRCULATING HEAD & CIRCULATED CASING VOLUME. MEANWHILE SHIFTED 13 5/8" SPIDER ELEVATOR TO RIG FLOOR & CHANGED TDS LINKS.
43632.125 | 43632.1458 | 0.5 | DRL | PT-P | RU | R/UP 13 5/8" CASING SPIDER ELEVATOR.
43632.1458 | 43632.25 | 2.5 | DRL | PT-P | RC | RIH 13 5/8" CASING FROM 565M TO 710M (63 JOINTS). WHILE RIH FILLED UP EVERY CASING JOINT & INSTALLED CENTRALIZERS AS PER TALLY.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 13 5/8" CASING
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | PRECAUTIONARY BACK REAMED FROM 1332M TO 558M TO AVOID SWABBING. POOH FROM 558M TO SURFACE. REPLACED 5 1/2" PIPE RAMS WITH 13 3/8" CSG RAMS & P/TESTED BONNET SEALS. RIH 13 5/8" CASING TO 441M AS PER TALLY.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 13 5/8" X 13 3/8" CASING AS PER PROGRAM.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14