## DDR#45
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 45
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 44.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 10:00 | 21:00 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2218
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | FLOAT SHOE |  |  | 14.5 | 12.375 |  | P110 / VT |  | 1.33 | 88.2 PPF |  | PITS (BBL) | 780
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 4 X 13 5/8" CSG JTS |  |  | 13.625 | 12.375 |  | P110 / VT |  | 45.35 | 88.2 PPF |  | ACT. SYS (BBL) | 2998
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FLOAT COLLAR |  |  | 14.5 | 12.375 |  | P110 / VT |  | 0.92 | 88.2 PPF |  | RESV. SYS (BBL) | 1898
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 96 X 13 5/8" CSG JTS |  |  | 13.625 | 12.375 |  | P110 / VT |  | 1080.61 | 88.2 PPF |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | X/OVER |  |  | 13.625 | 12.375 |  | P110 / VT |  | 0.84 | 88.2 PPF |  | KILL MW (SG)
µ FUNNEL (SEC) | 56 | 52 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 16 X 13 3/8" CSG JTS |  |  | 13.375 | 12.347 |  | SM110TT / VT |  | 191.52 | 72 PPF |  | TOTAL | 4896
PV | 40 | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 46 X 13 3/8" CSG JTS |  |  | 13.375 | 12.347 |  | P110 / VT |  | 536.78 | 72 PPF |  | DIESEL (LTR)
YIELD POINT | 24 | 18 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | ACP |  |  | 13.375 | 12.347 |  | P110 / VT |  | 3.08 | 72 PPF |  | RIG TANK | 122223
GEL ST. | 12/21 | 11/17 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 1 X 13 3/8" PUP JT |  |  | 13.375 | 12.347 |  | P110 / VT |  | 4.49 | 72 PPF |  | CAMP TANK | 28205
WL (ml/30 min) | 7.9 | 8.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 48 X 13 3/8" CSG JTS |  |  | 13.375 | 12.347 |  | P110 / VT |  | 549.51 | 72 PPF |  | CONSUMED | 7110
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 1 X 13 3/8" PUP JT |  |  | 13.375 | 12.347 |  | P110 / VT |  | 6.02 | 72 PPF |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 150428
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 340000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 160000
KCl (mg/l) | 56629 | 56629 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 63000
CHLORIDES (mg/l) | 27000 | 27000 | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 385000
HARDNESS (mg/l) | 320 | 320 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.15 | 0.15 | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 2420.45 |  |  | MPCL | 7
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 36
SOLIDS % | 35.98 | 35.98 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 8.8 | 8.8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 136
DAILY WELL COST (US$) |  | 42675 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4095420 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 20.57% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43633 | 43633.3021 | 7.25 | DRL | PT-P | RC | P/UP, M/UP & RIH 13 3/8" ACP WITH PUP JOINT AND RIH 13 3/8" CASING FROM 1857M TO 2398M. WHILE RIH FILLED UP EVERY CASING JOINT, BROKE CIRCULATION AFTER EVERY 20 JOINTS & INSTALLED CENTRALIZERS AS PER TALLY.
43633.3021 | 43633.3229 | 0.5 | DRL | PT-P | RD | B/O & L/D FILL UP TOOL.
43633.3229 | 43633.3646 | 1 | DRL | PT-P | RC | CONNECTED CIRCULATED HEAD AND WASHED DOWN FROM 2398M TO 2419M.
43633.3646 | 43633.6458 | 6.75 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE AND REDUCE MUD RHEOLOGY. MEANWHILE L/D WF TRS GEAR.
43633.6458 | 43633.6875 | 1 | DRL | PT-P | RU | R/U SLB CEMENT HEAD AND LINES.
43633.6875 | 43633.7396 | 1.25 | DRL | PT-P | CIR | CIRCULATED TO REDUCE MUD RHEOLOGY, MEANWHILE PREPARED MIX FLUID FOR CMT JOB.
43633.7396 | 43633.7604 | 0.5 | DRL | PT-P | CIR | CHECKED MUD PUMPS EFFICIENCY.
43633.7604 | 43633.7917 | 0.75 | DRL | PT-P | RU | R/U SLB CEMENT HEAD WITH PRE LOADED CEMENT PLUGS.
43633.7917 | 43633.8021 | 0.25 | DRL | PT-P | P/T | P/T CEMENT LINE @ 1000/4000 PSI - OK.
43633.8021 | 43633.8646 | 1.5 | DRL | PT-P | CIR | CONT'D CIRCULATION TO REDUCE MUD RHEOLOGY, MEANWHILE PREPARED MIX FLUID (ADDED RETARDER AS PER PROGRAM).
43633.8646 | 43633.875 | 0.25 | DRL | PT-P | SM | HELD PJSM PRIOR TO CMT JOB.
43633.875 | 43634 | 3 | DRL | PT-P | CMC | PERFORMED CMT JOB AS PER PROGRAM: PUMPED 100 BBL OF CEMPRIME SCRUB SPACER (2.12 SG) & 50 BBL OF MUDPUSH II SPACER (2.12 SG) @10 BPM WITH RIG PUMPS. DROPPED 1ST BOTTOM CMT PLUG MANUALLY . SWITCHED OVER TO CEMENT UNIT & PUMPED FLY MIXED LEAD SLURRY (2.20 SG) @ 5 BPM IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43634 | 43634.25 | 6 | DRL | PT-P | CMC | CONT'D PUMPING FLY MIXED LEAD SLURRY TOTAL 960 BBL (2.20 SG) @ 5 BPM (ADDED CEMNET AS PER PROGRAM).DROPPED 2ND BOTTOM PLUG PRE LOADED IN CEMENT HEAD FOLLOWED BY 300 BBL FLY MIXED TAIL SLURRY (2.20 SG) @ 5 BPM (ADDED CEMNET AS PER PROGRAM). DROPPED TOP PLUG FOLLOWED BY 10 BBL MUD PUSH II SPACER (2.12 SG), SWITCHED OVER TO RIG PUMP AND DISPLACED 1120 BBL MUD, SWITCHED OVER TO CMT UNIT AND DISPLACED 43 BBL AT SLOW RATE. TOTAL DISPLACEMENT = 10 + 1120 + 43 = 1173 BBL. DUMPED SPACER + CMT CONTAMINATION= 500 BBL. OBSERVED LOSS = 126 BBL DURING CMT PUMPING. OBSERVED PLUGS BUMPED, GRADUALLY INCREASED PRESSURE FROM 300 PSI TO 1000 PSI, HELD FOR 5 MIN, OK. BLED OFF SAME, NO BACK FLOW OBSERVED. INCREASED PRESSURE IN INCREMENTS TO 2700 PSI, OBSERVED PRESSURE DROPPED 150 PSI AND STABILIZED (ACP INFLATED). BLED OFF PRESSURE TO 1000 PSI & INCREASED TO 3000 PSI, HELD FOR 5 MIN, OK.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | INFLATION OF ACP IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | 13 5/8'' X 13 3/8'' CSG JOB, CSG CMT JOB
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CSG CMT JOB, SET SLIP AND SEAL ASSEMBLY, CUT CSG, INSTALL WELLHEAD, WOC, N/UP BOP, BOPT.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14