## DDR#46
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 46
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 45.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 1178.3
CHECK TIME | 20:00 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL)
DEPTH, MD (M) | 2420 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 669
MW IN (SG) | 2.08 |  | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1847.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 2064
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 55 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 3911.3
PV | 32 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 20 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 117739
GEL ST. | 12/19 |  | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 27501
WL (ml/30 min) | 8.5 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5188
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.4 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 145240
ALK (FILT.) | 0.5 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 100000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 48000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 182000
KCl (mg/l) | 56629 |  | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 182000
CHLORIDES (mg/l) | 27000 |  | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 148000
HARDNESS (mg/l) | 320 |  | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.15 |  | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 7
LUBRICANT % | 1 |  | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 29
SOLIDS % | 35.98 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 8.8 |  | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 130
DAILY WELL COST (US$) |  | 482532 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4579206 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 23% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43634 | 43634.25 | 6 | DRL | PT-P | CMC | CONT'D PUMPING FLY MIXED LEAD SLURRY TOTAL 960 BBL (2.20 SG) @ 5 BPM (ADDED CEMNET AS PER PROGRAM).DROPPED 2ND BOTTOM PLUG PRE LOADED IN CEMENT HEAD FOLLOWED BY 300 BBL FLY MIXED TAIL SLURRY (2.20 SG) @ 5 BPM (ADDED CEMNET AS PER PROGRAM). DROPPED TOP PLUG FOLLOWED BY 10 BBL MUD PUSH II SPACER (2.12 SG), SWITCHED OVER TO RIG PUMP AND DISPLACED 1120 BBL MUD, SWITCHED OVER TO CMT UNIT AND DISPLACED 43 BBL AT SLOW RATE. TOTAL DISPLACEMENT = 10 + 1120 + 43 = 1173 BBL. DUMPED SPACER + CMT CONTAMINATION= 500 BBL. OBSERVED LOSS = 126 BBL DURING CMT PUMPING. OBSERVED PLUGS BUMPED, GRADUALLY INCREASED PRESSURE FROM 300 PSI TO 1000 PSI, HELD FOR 5 MIN, OK. BLED OFF SAME, NO BACK FLOW OBSERVED. INCREASED PRESSURE IN INCREMENTS TO 2700 PSI, OBSERVED PRESSURE DROPPED 150 PSI AND STABILIZED (ACP INFLATED). BLED OFF PRESSURE TO 1000 PSI & INCREASED TO 3000 PSI, HELD FOR 5 MIN, OK.
43634.25 | 43634.3021 | 1.25 | DRL | PT-P | WOC / NDB | MADE ARRANGEMENTS TO LIFT BOP, DISCONNECTED FLOW LINE. LIFTED BOP STACK.
43634.3021 | 43634.375 | 1.75 | DRL | PT-P | WOC / WH | CENTRED 13.375'' CSG AND SET SLIP AND SEAL ASSY IN CASING HEAD HOUSING. SLACKED OFF CSG WEIGHT ON SLIP AND SEAL ASSY.
43634.375 | 43634.6042 | 5.5 | DRL | PT-P | WOC / CC | ROUGH CUT 13.375'' CSG & N/D BOP BOTH IN PARTS. MEANWHILE R/D CMT HEAD, SPIDER ELEVATOR, L/D LANDING JOINT + CUT JOINT.
43634.6042 | 43634.75 | 3.5 | DRL | PT-P | WOC / CC | FINAL CUT 13.375'' CSG AT 6'' WITH COLD CUTTER. BEVELLED AND DRESSED SAME.
43634.75 | 43634.9167 | 4 | DRL | PT-P | WOC / WH | N/UP 21-1/4''-5K X 13 5/8''-10K CASING HEAD SPOOL. N/UP SPACER SPOOL. P/TESTED FS SEALS, CAVITY, HANGER SEAL & FLANGE @ 1750 PSI - OK.
43634.9167 | 43635 | 2 | DRL | PT-P | WOC / NUB | N/UP 13 5/8'' BOP STACK IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43635 | 43635.2083 | 5 | DRL | PT-P | WOC / NUB | CONT'D N/UP 13 5/8'' BOP STACK.
43635.2083 | 43635.25 | 1 | DRL | PT-P | WOC / BOPT | HELD PJSM, P/UP AND M/UP TEST PLUG ASSEMBLY. INSTALLED TEST PLUG IN CASING HEAD SPOOL.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | BOPT IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CSG CMT JOB, WOC, SET SLIP AND SEAL ASSEMBLY, CUT CSG, INSTALLED WELLHEAD, P/TESTED SAME, N/UP BOP IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | N/UP BOP, BOPT, REPLACE DRILL LINE, L/DOWN BHA COMPONENT FROM DERRICK, P/UP AND M/UP 5.5'' DP STANDS, RIH FOR COC.
REMARKS |  |  | RELEASED W.FORD TRS EQP + CREW.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30