## DDR#47
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 47
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 46.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 1178.3
CHECK TIME | 20:00 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL)
DEPTH, MD (M) | 2420 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 667
MW IN (SG) | 2.08 |  | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1847.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 2061
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 56 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 3908.3
PV | 36 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 20 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 114761
GEL ST. | 12/21 |  | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 26783
WL (ml/30 min) | 8.5 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 3696
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.4 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 141544
ALK (FILT.) | 0.5 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 387000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 83100
KCl (mg/l) | 56629 |  | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 83100
CHLORIDES (mg/l) | 27000 |  | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 427000
HARDNESS (mg/l) | 320 |  | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.15 |  | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 7
LUBRICANT % | 1 |  | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 29
SOLIDS % | 35.98 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 8.8 |  | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 130
DAILY WELL COST (US$) |  | 104023 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4683229 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 23.53% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43635 | 43635.2083 | 5 | DRL | PT-P | WOC / NUB | CONT'D N/UP 13 5/8'' BOP STACK.
43635.2083 | 43635.3958 | 4.5 | DRL | PT-P | BOPT | HELD PJSM. P/U, M/U & RIH TEST PLUG ASSY, SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP & STAND PIPE @ 500 PSI/5000 PSI FOR 5 / 10 MIN - OK. CLOSED UPPER PIPE RAM BOP (VARIABLE: 4.5" TO 7") P/TESTED HCR VALVES & MANUAL VALVES @ KILL LINE /CHOKE LINE; FOSV, IBOP, MANUAL IBOP/ROTARY HOSE;CO-FLEXIP-MASTER VALVE @ CHOKE MANIFOLD & KILL LINE CHECK VALVE @ 500 / 8000 PSI FOR 5 / 10 MIN - OK. RETRIEVED TEST PLUG & SET WEAR BUSHING.
43635.3958 | 43635.9583 | 13.5 | DRL | NPT-UP | RR | REPLACED SAVER SUB, DRILL LINE SPOOL & STAND PIPE MANIFOLD VALVES. P/TESTED SURFACE LINES (STAND PIPE, PUMP MANIFOLD, ROTARY HOSE SAVER SUB & MUD PUMP CHOKE MANIFOLD) @ 6000 PSI.
43635.9583 | 43636 | 1 | DRL | NPT-UP | RR | MODIFICATION OF BELL NIPPLE + FLOW LINE IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43636 | 43636.0521 | 1.25 | DRL | NPT-UP | RR | CONT'D MODIFYING BELL NIPPLE + FLOW LINE.
43636.0521 | 43636.25 | 4.75 | DRL | PT-P | DP | L/DOWN 9 X 9 1/2'' DC'S, 4 X 8'' DC'S, 9 X 5.5'' HWDP FROM DERRICK.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | L/DOWN DC'S / DP'S FROM DERRICK IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | N/UP BOP, BOPT, REPLACED SAVER SUB, DRILL LINE SPOOL, P/TESTED SURFACE LINES AT 6000 PSI, OK. MODIFICATION OF BELL NIPPLE + FLOW LINE IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | MODIFY BELL NIPPLE + FLOW LINE, L/DOWN BHA COMPONENT FROM DERRICK, P/UP AND M/UP RR PDC BIT + ROTARY BHA, WHILE RIH P/UP 5.5'' DP SNGL BY SNGL FROM CAT WALK.
REMARKS |  |  | RELEASED FMC WELLHEAD ENGR, CHANGED MUD PUMP LINERS TO 5.5''.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14