## DDR#48
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 48
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH/HAMZA/MOHSIN/TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2390 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 47.5833
RIG REP.: |  | JAVED MUGHAL/ IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2396 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-02-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5 |  | BHA No. |  |  | 8 | IN (M) |  | 2367 |  | OUT (M) |  |  | STRING (BBL) | 135.44
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 2390 |  | SIZE (IN) |  | 12-1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 950
DEPTH, MD (M) |  | 2390 | TVD @ 00:00HR (M) |  | 2390 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 |  |  | 6-5/8 REG |  | 0.36 |  |  | PITS (BBL) | 909
MW IN (SG) |  | 1.98 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 9.97 |  |  | ACT. SYS (BBL) | 1994.44
MW OUT (SG) |  | 1.98 | INST. ROP (M/HR) |  | 0.9 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.59 |  |  | RESV. SYS (BBL) | 1557
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1 |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 1.55 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 8 |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.61 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 62 | AVG. RPM SURFACE |  | 40 |  | DEPTH IN (M) |  | 2367 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.29 |  |  | TOTAL | 3551.44
PV |  | 40 | AVG. RPM DOWNHOLE |  | 70 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.48 |  |  | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  | 630 |  | METERAGE (M) |  | 23 |  | NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 9 |  |  | RIG TANK | 91000
GEL ST. |  | 10/36 | PRESSURE (PSI) |  | 3150 |  | RPM SURF. |  | 0-60 |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.68 |  |  | CAMP TANK | 20000
WL (ml/30 min.) |  | 4.4 | TORQ. ON-BTM (KLB-FT) |  | 2018-06-08 |  | RPM BTM. |  | 75-135 |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 5.15 |  |  | CONSUMED | 7500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 1-9 |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.76 |  |  | RECEIVED
ALK (MUD) |  | 0.1 | STRING WT. (TON) - ROT |  | 140 |  | AVG. ROP (M/HR) |  | 1.637 |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.9 |  |  | TOTAL | 111000
ALK (FILT.) |  | 0.2 | PICK-UP WT. (TON) |  | 141 |  | BIT ROT HRS. |  | 14.05 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.25 |  |  | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 132 |  | K-REVS IN 24 HRS |  | 84 | [12 empty] | RIG STORAGE | 460000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 84 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 47.84 | [12 empty] | CONSUMED
KCl (mg/l) |  | 47667.5 | JAR | 8.68 | NMDC | 8.68 | JET VELOCITY (M/SEC) |  | 56.8 | [12 empty] | RECEIVED | 68370
CHLORIDES |  | 22000 | 5" HWDPS | 8.68 | STAB - 1 | 8.68 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 500000
CALCIUM |  | 160 | 8" DCS | 8.68 | STAB - 2 & 3 | 8.68 | HSI |  | 1.3 | [12 empty] | POB
OIL% |  | 2 | 9 1/2" DCS | 8.68 | SPSA | 8.68 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 177.59 |  |  | MPCL | 5
DIESEL % |  | 2 | BHA ROT. HRS |  | 8.68 |  | BIT No. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 19
SOLIDS % |  | 31.25 | ON BOTTOM HRS |  | 14.05 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 20.12 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2277 |  | 2.47 |  | 105.15 |  |  | 0.19 |  | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 83397.0744 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 2304 |  | 2.84 |  | 111.01 |  |  | 0.51 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4788005.3195 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2335 |  | 3.31 |  | 105.73 |  |  | 0.48 |  | MWD |  | LAST CSG SIZE | 13.375''
% OF AFE SPENT |  | 26.53% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2366 |  | 3.18 |  | 108.69 |  |  | 0.21 |  | MWD |  | FIT (EMW) | 1.98
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 736
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | CAMERON CHINA | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2392 |  | 227/360 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CAMERON CHINA | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2392 |  | 215/345 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | CAMERON CHINA | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS | CAMERON CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-02-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-16 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43137 | 43137.4688 | 11.25 | DRL | NPT-UP | WC | KILLED WELL BY WAIT & WEIGHT METHOD WITH 1.97SG MUD. MW IN = 1.97SG & MW OUT = 1.94SG.
43137.4688 | 43137.4792 | 0.25 | DRL | NPT-UP | WC | CLOSED CHOKE & MONITORED WELL. OBSERVED SICP & SIDP = 0.
43137.4792 | 43137.5 | 0.5 | DRL | NPT-UP | CIR | OPENED BOP RAMS & MONITORED WELL. FOUND WELL STATIC.
43137.5 | 43137.625 | 3 | DRL | NPT-UP | CIR | ESTABLISHED DIRECT CIRCULATION TO HOMOGENIZE MUD TO 1.98SG. MW IN = 1.98SG & MW OUT = 1.97SG
43137.625 | 43137.7708 | 3.5 | DRL | NPT-UP | OTH | PULLED BACK TO CASING SHOE. PREPARED 1.98SG MUD @ SHAKER TANK, INTERMEDIATE TANK & R-1
43137.7708 | 43138 | 5.5 | DRL | NPT-UP | CIR | RAN BACK TO 2372M & CIRCULATED TO HOMOGENIZE ACTIVE SYSTEM MUD TO 1.98SG. MW IN = 1.98SG & MW OUT = 1.98SG. MEANWHILE RECIPROCATED STRING DURING CIRCULATION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43138 | 43138.0625 | 1.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2390M TO 2392M.
43138.0625 | 43138.25 | 4.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN SLIDE MODE FROM 2392M TO 2396M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12.25" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | KILLED WELL BY WAIT & WEIGHT METHOD. CLOSED CHOKE & MONITORED WELL. OBSERVED SICP & SIDP = 0. OPENED BOP RAMS & MONITORED WELL. FOUND WELL STATIC. ESTABLISHED DIRECT CIRCULATION TO HOMOGENIZE MUD TO 1.98SG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12.25'' HOLE SECTION.
REMARKS |  |  | PREPARED 600 BBLS KILL MUD OF 2.20 SPGR DURING CIRCULATION & DRILLING.
Formulas:
DHARIAN - 1 = [DATE]+14