## DDR#48
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 48
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH/SAIFULLAH/HAMZA/MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 47.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 5RR |  | BHA NO. |  |  | 10 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 100
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1009
DEPTH, MD (M) | 2420 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.4 |  |  | PITS (BBL) | 733
MW IN (SG) | 2.08 |  | DAILY PROGRESS (M) |  |  |  | TYPE |  | SF56H |  | BIT SUB |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 |  |  | ACT. SYS (BBL) | 1842
MW OUT (SG) | 2.08 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12180325 |  | 6 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 55.27 | 12.3417 |  | RESV. SYS (BBL) | 2061
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 7 X 16/32'' |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.58 | 6.1586 |  | KILL MW (SG)
µ FUNNEL (SEC) | 57 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2420 |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | TOTAL | 3903
PV | 36 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 9 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | DIESEL (LTR)
YIELD POINT | 21 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 109735
GEL ST. | 12/19 |  | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 26053
WL (ml/30 min) | 8.5 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5756
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.4 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 135788
ALK (FILT.) | 0.5 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 432000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 60000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 0
KCl (mg/l) | 56629 |  | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 55200
CHLORIDES (mg/l) | 27000 |  | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 492000
HARDNESS (mg/l) | 320 |  | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.15 |  | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 179.53 |  |  | MPCL | 8
LUBRICANT % | 1 |  | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 17 |  |  | MPCL SERV | 27
SOLIDS % | 35.98 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 8.8 |  | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 127
DAILY WELL COST (US$) |  | 353365.7685 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5026735.2227 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 25.25% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43636 | 43636.0521 | 1.25 | DRL | NPT-UP | RR | CONT'D MODIFYING BELL NIPPLE + FLOW LINE.
43636.0521 | 43636.2812 | 5.5 | DRL | PT-P | DP | L/DOWN 9 X 9 1/2'' DC'S, 4 X 8'' DC'S, 9 X 5.5'' HWDP FROM DERRICK.
43636.2812 | 43636.3958 | 2.75 | DRL | PT-P | BHA | P/U & M/U USED 12 1/4" PDC AND RIH WITH SLICK BHA FROM SURFACE TO 178M. WHILE RIH P/U 9 X 8" DC, 1 X 8" D. JAR, 9 X 5.5" HWDP SINGLE BY SINGLE.
43636.3958 | 43637 | 14.5 | DRL | PT-P | RIH | RIH FROM 178M TO 2102M. FILLED UP STRING EVERY 15 STANDS. P/U 5.5" DP SINGLE BY SINGLE WHILE RIH.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43637 | 43637.1667 | 4 | DRL | PT-P | RIH | CONT'D RIH FROM 2102M TO 2350M. WHILE RIH P/UP 5.5'' DP'S (TOTAL 5.5'', 21.90 PPF DP'S = 240)
43637.1667 | 43637.25 | 2 | DRL | PT-P | DC / DFS | M/UP TDS, PRECAUTIONARY WASHED DOWN FROM 2350M AND TAGGED CMT PLUG AT 2369M. DRILLED OUT CMT PLUGS DOWN TO 2371M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING OUT CMT PLUGS /F.COLLAR IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | MODIFIED BELL NIPPLE + FLOW LINE, L/DOWN 9 1/2'', 8'' & 5.5'' HWDP FROM DERRICK, P/UP AND M/UP 12 1/4'' RR PDC BIT + SLICK BHA & RIH TO 2102M, WHILE RIH P/UP 5.5'' DP SNGL BY SNGL FROM CAT WALK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 2102M TO TAG CMT PLUGS, DRILL OUT CMT PLUG/ F.COLLAR & SHOE TRACK CMT, CSG TEST, DRILL OUT CMT + SHOE, DRILL 12 1/4'' HOLE TO 2423M, CIRCULATION, FIT, DRILL AHEAD TO 2430M, POOH TO CHANGE BHA.
REMARKS |  |  | RECEIVED 1 X 8'' B/UP D.JAR.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14