## DDR#49
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 49
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/HAMZA/MOHSIN/TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 48.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 5RR |  | 6 | BHA NO. |  |  | 11 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | 12.25 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1173
DEPTH, MD (M) | 2420 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HLB |  | BAKER | TRICONE BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 690
MW IN (SG) | 2.08 |  | DAILY PROGRESS (M) |  |  |  | TYPE |  | SF56H |  | MXL-3 | JUNK SUB |  |  | 11.75 | 3.5 |  | 6 5/8 REG |  | 1.41 |  |  | ACT. SYS (BBL) | 1863
MW OUT (SG) | 2.08 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12180325 |  | 5221807 | BIT SUB (F.V) |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | RESV. SYS (BBL) | 1952
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 137 | 1X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.14 | 2.0409 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 7 X 16/32'' |  | 3 X 20/32'' | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.73 | 0.38631 |  | KILL MW (SG)
µ FUNNEL (SEC) | 51 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2420 |  | 2420 | 5 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 46.13 | 10.3008 |  | TOTAL | 3815
PV | 37 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  |  | D.JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 0.35152 |  | DIESEL (LTR)
YIELD POINT | 18 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 5 1/2 FH |  | 27.58 | 6.1586 |  | RIG TANK | 104224
GEL ST. | 11/17 |  | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | CAMP TANK | 25311
WL (ml/30 min) | 8.5 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 9 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | CONSUMED | 6253
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [15 empty] | RECEIVED
ALK (MUD) | 0.4 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [15 empty] | TOTAL | 129535
ALK (FILT.) | 0.5 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | WATER (LTR)
PH | 10 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [15 empty] | RIG STORAGE | 367000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 70000
KCl (mg/l) | 56629 |  | JAR | 7.5 | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 42000
CHLORIDES (mg/l) | 27000 |  | 5 1/2" HWDPS | 7.5 | STAB - 2 |  | TFA (IN²) |  |  |  | 0.9203 | [11 empty] | TOTAL | 422000
HARDNESS (mg/l) | 400 |  | 9 1/2" DCS |  | STAB - 3 |  | HSI | [15 empty] | POB
SAND % | 0.1 |  | 8" DCS | 7.5 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  |  | TOTAL LENGTH (M) | [7 empty] | 182.62 |  |  | MPCL | 8
LUBRICANT % | 1 |  | BHA ROT. HRS |  | 7.5 |  | BIT NO. 5RR |  | 2-8-WT-S-X -2-RO-TQ |  |  | BHA WT. IN MUD (TON) | [7 empty] | 17 |  |  | MPCL SERV | 29
SOLIDS % | 35.98 |  | ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 |  | CIRC. HRS |  | 7.7 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 |  | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 128
DAILY WELL COST (US$) |  | 32284 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 20" SURFACE / K-55, 133# |  |  | 579 |  | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5059019 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 |  | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 25.41% | MUD CLEANER | 3 X 170 | [7 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" |  | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" |  | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" |  | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43637 | 43637.1667 | 4 | DRL | PT-P | RIH | CONT'D RIH FROM 2102M TO 2350M. WHILE RIH P/UP 5.5'' DP'S (TOTAL 5.5'', 21.90 PPF DP'S = 240)
43637.1667 | 43637.3438 | 4.25 | DRL | PT-P | DC / DFS | M/UP TDS, PRECAUTIONARY WASHED DOWN FROM 2350M AND TAGGED CMT PLUG AT 2369M. DRILLED OUT WIPER PLUGS, FLOAT COLLAR AND CEMENT BELOW FLOAT COLLAR FROM 2371M TO 2387M. @ 5/6 MPHR.
43637.3438 | 43637.4167 | 1.75 | DRL | PT-P | DC | DRILLED HARD CEMENT FROM 2387M TO 2389 M @ OBSEREVED HI ERRATIC TORQUE, TDS STALLING DURING CLEAN OUT. OBSERVED MAGNETIC METAL SHAVINGS AT BOTTOMS UP. STOPPED DRILLING CEMENT.
43637.4167 | 43637.5 | 2 | DRL | NPT-UP | CIR | DISCUSSED SITUATION IN TOWN. DECIDED TO POOH & CHECK BIT CONDITION. CIRCULATED FOR BOTTOM UP PRIOR POOH.
43637.5 | 43637.5104 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43637.5104 | 43637.7188 | 5 | DRL | NPT-UP | POOH | POOH FROM 2389M TO 179M (TOP OF BHA).
43637.7188 | 43637.7708 | 1.25 | DRL | NPT-UP | BHA | POOH BHA FROM 179M TO SURFACE. L/DOWN JAR & BIT. FOUND BIT RANG OUT.
43637.7708 | 43637.9167 | 3.5 | DRL | NPT-UP | OTH | MADE ARRANGEMENTS, FINALIZED BHA, DECIDED TO RIH WITH 12 1/4'' TC BIT & JUNK SUB.
43637.9167 | 43637.9583 | 1 | DRL | NPT-UP | RR | FIXED BELL NIPPLE LEAKAGE.
43637.9583 | 43638 | 1 | DRL | NPT-UP | BHA | P/UP, M/UP AND RIH NEW 12 1/4'' TC BIT (MXL-3; IADC 137;BAKER, 3 X 20/32'') + 11 3/4'' JUNK SUB. RIH AS PER BHA DOWN TO 28M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43638 | 43638.0417 | 1 | DRL | NPT-UP | BHA | CONT'D RIH FROM 28M TO 181M. MEANWHILE P/UP AND M/UP D.JAR.
43638.0417 | 43638.2396 | 4.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 181M TO 2353M. FILLED UP STRING EVERY 15 STANDS.
43638.2396 | 43638.25 | 0.25 | DRL | NPT-UP | RW | M/UP TDS, PRECAUTIONARY WASHED DOWN FROM 2353M TO 2370M. RECORDED STRING WEIGHTS (UP, DOWN & ROTATING TORQUE).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WASHING DOWN BELOW 2370M IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 2102M & TAGGED CMT PLUGS AT 2369M , DRILLED OUT CMT PLUG/ F.COLLAR & SHOE TRACK CMT DOWN TO 2389M, OBSERVED HIGH ERRATIC TORQUE AT 2387M FOLLOWED BY METALLIC SHAVINGS AT SHAKERS, DECIDED TO POOH, POOH TO SURFACE, L/DOWN BIT, P/UP NEW TC BIT + JUNK SUB & RIH TO 28M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH JUNK SUB BHA FROM 28M TO 2370M, PRECAUTIONARY WASH DOWN FROM 2370M TO 2389M, CIRCULATION, WORK ON JUNK SUB, ATTEMPT TO DRILL OUT BELOW 2387M.
REMARKS |  |  | MANAGER DRILLING VISITED WELLSITE.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14