## DDR#50
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 50
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-09
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH/HAMZA/MOHSIN/TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2436 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 49.5833
RIG REP.: |  | JAVED MUGHAL/ IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2440 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 26
2018-02-08 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5 |  | BHA No. |  |  | 8 | IN (M) |  | 2367 |  | OUT (M) |  |  | STRING (BBL) | 139
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2436 |  | SIZE (IN) |  | 12-1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 968
DEPTH, MD (M) | 2418 | 2436 | TVD @ 00:00HR (M) |  | 2436 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 |  |  | 6-5/8 REG |  | 0.36 |  |  | PITS (BBL) | 1008
MW IN (SG) | 2418 | 2436 | DAILY PROGRESS (M) |  | 26 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 9.97 |  |  | ACT. SYS (BBL) | 2115
MW OUT (SG) | 2 | 2 | INST. ROP (M/HR) |  | 1.59 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.59 |  |  | RESV. SYS (BBL) | 1168
ECD (SG) | 2.03 | 2.03 | AVG. ROP (M/HR) |  | 1.31 |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 1.55 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F | 152 | 150 | AVG. WOB (TON) |  | 2-9 |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.61 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 62 | 60 | AVG. RPM SURFACE |  | 0-80 |  | DEPTH IN (M) |  | 2367 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.29 |  |  | TOTAL | 3883
PV | 44 | 49 | AVG. RPM DOWNHOLE |  | 80-160 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.48 |  |  | DIESEL (LTR)
YIELD POINT | 24 | 26 | FLOWRATE (GPM) |  | 700 |  | METERAGE (M) |  | 69 |  | NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 9 |  |  | RIG TANK | 115800
GEL ST. | 8/36 | 9/40 | PRESSURE (PSI) |  | 3500-3600 |  | RPM SURF. |  | 0-80 |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.68 |  |  | CAMP TANK | 19000
WL (ml/30 min.) | 5 | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 2-4 |  | RPM BTM. |  | 75-160 |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 5.15 |  |  | CONSUMED | 13700
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | WOB (TON) |  | 1-10 |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.76 |  |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 117 |  | AVG. ROP (M/HR) |  | 1.3274 |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.9 |  |  | TOTAL | 134800
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  | 118 |  | BIT ROT HRS. |  | 51.98 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.25 |  |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 116 |  | K-REVS IN 24 HRS |  | 131 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 311 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 47.68 | [12 empty] | CONSUMED | 96160
KCl (mg/l) | 47667.5 | 47667.5 | JAR | 25.48 | NMDC | 25.48 | JET VELOCITY (M/SEC) |  | 56.6 | [12 empty] | RECEIVED | 91160
CHLORIDES | 22000 | 22000 | 5" HWDPS | 25.48 | STAB - 1 | 25.48 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 440000
CALCIUM | 160 | 140 | 8" DCS | 25.48 | STAB - 2 & 3 | 25.48 | HSI |  | 1.7 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS | 25.48 | SPSA | 25.48 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 177.59 |  |  | MPCL | 5
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 25.48 |  | BIT No. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 18
SOLIDS % | 31.15 | 31.15 | ON BOTTOM HRS |  | 51.98 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY | 4
M.B.T. | 18 | 18 | CIRC. HRS |  | 83.87 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2335 |  | 3.31 |  | 105.73 |  |  | 0.48 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 61131.2544 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 2366 |  | 3.18 |  | 108.69 |  |  | 0.21 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4971159.0083 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2385 |  | 2.27 |  | 107.96 |  |  | 1.44 |  | MWD |  | LAST CSG SIZE | 13.375''
% OF AFE SPENT |  | 27.54% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2414 |  | 1.29 |  | 94.61 |  |  | 1.09 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 668
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | CAMERON CHINA | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2404 |  | 310/430 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CAMERON CHINA | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2404 |  | 340/430 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | CAMERON CHINA | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS | CAMERON CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-02-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-16 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43139 | 43139.0208 | 0.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2410M TO 2411M.
43139.0208 | 43139.6875 | 16 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN SLIDE MODE FROM 2411M TO 2422M.
43139.6875 | 43140 | 7.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2422M TO 2436M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43140 | 43140.25 | 6 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN SLIDE MODE FROM 2436M TO 2440M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12.25" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12.25'' HOLE IN ROTARY & SLIDE MODE FROM 2410M TO 2436M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12.25'' HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14