## DDR#50
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 50
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL/ HAMZA /TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 49.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 6 |  | BHA NO. |  |  | 11 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 140
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 964
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | TRICONE BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 682
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MXL-3 |  | JUNK SUB |  |  | 11.75 | 3.5 |  | 6 5/8 REG |  | 1.41 |  |  | ACT. SYS (BBL) | 1786
MW OUT (SG) | 2.08 | 2.08 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5221807 |  | BIT SUB (F.V) |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | RESV. SYS (BBL) | 2010
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | 1X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.14 | 2.0409 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 X 20/32'' |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.73 | 0.38631 |  | KILL MW (SG)
µ FUNNEL (SEC) | 56 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2420 |  | 5 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 46.13 | 10.3008 |  | TOTAL | 3796
PV | 39 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | D.JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 0.35152 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 5 1/2 FH |  | 27.58 | 6.1586 |  | RIG TANK | 100305
GEL ST. | 12/21 | 12/23 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | CAMP TANK | 24558
WL (ml/30 min) | 8.5 | 8.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 9 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | CONSUMED | 4672
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 124863
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 420000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 54000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 69500
KCl (mg/l) | 56629 | 56629 | JAR | 20.5 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 123500
CHLORIDES (mg/l) | 27000 | 27000 | 5 1/2" HWDPS | 20.5 | STAB - 2 |  | TFA (IN²) |  | 0.92 | [12 empty] | TOTAL | 474000
HARDNESS (mg/l) | 400 | 400 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.15 | 0.15 | 8" DCS | 20.5 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 182.62 |  |  | MPCL | 7
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 13 |  | BIT NO. 6 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 17 |  |  | MPCL SERV | 24
SOLIDS % | 35.98 | 35.98 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 18.4 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 35030 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5094049 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 25.59% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43638 | 43638.0417 | 1 | DRL | NPT-UP | BHA | CONT'D RIH FROM 28M TO 181M. MEANWHILE P/UP AND M/UP D.JAR.
43638.0417 | 43638.2396 | 4.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 181M TO 2353M. FILLED UP STRING EVERY 15 STANDS.
43638.2396 | 43638.25 | 0.25 | DRL | NPT-UP | RW | M/UP TDS, PRECAUTIONARY WASHED DOWN FROM 2353M TO 2370M. RECORDED STRING WEIGHTS (UP, DOWN & ROTATING TORQUE).
43638.25 | 43638.2812 | 0.75 | DRL | NPT-UP | RW | CONT'D WASH DOWN FROM 2370M TO 2387M & OBSERVED COMPRESSION.
43638.2812 | 43638.3438 | 1.5 | DRL | NPT-UP | CIR | PUMPED AND SWEPT OUT HI-VIS PILL, OBSERVED MINOR METALLIC SHAVINGS ON SHAKERS AT BTMS UP.
43638.3438 | 43638.6458 | 7.25 | DRL | NPT-UP | RW /DC | ATTEMPTED SEVERAL TIMES TO PASS BELOW 2387M WITH CIRCULATION AND SLOW ROTATION, OBSERVED HI TORQUE AND COMPRESSION. REAMED DOWN SLOWLY FROM 2387M TO 2388.50M. P/UP STRING, INCREASED RPM AND ATTEMPTED TO CLEAR OBSTRUCTION WITH LOW WOB. OBSERVED HI-TORQUE WITH EXCESSIVE BOUNCING. ATTEMPTED SEVERAL TIMES TO CLEAR SAME, NO SUCCESS. OBSERVED METALLIC SHAVINGS, FORMATION SAMPLES & CMT ON BTMS UP.
43638.6458 | 43639 | 8.5 | DRL | NPT-UP | CIR | P/UP OFF BTM, CIRCULATED TO CLEAN HOLE MEANWHILE ARRANGING SERVICES/TOOLS FOR MILLING JOB.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43639 | 43639.0521 | 1.25 | DRL | NPT-UP | CIR | PUMPED & SWEPT OUT HI-VIS PILL PRIOR POOH.
43639.0521 | 43639.0625 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43639.0625 | 43639.25 | 4.5 | DRL | NPT-UP | POOH | POOH FROM 2385M TO 210M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH JUNK SUB BHA FROM 28M TO 2370M, PRECAUTIONARY WASHED DOWN FROM 2370M TO 2387M, OBSVD COMPRESSION, SWEPT OUT HI-VIS, CLEARED OBSTRUCTION TO 2388.50M WITH CIRCULATION AND ROTATION. ATTEMPTED TO CLEAR FURTHER, NO SUCCESS, OBSVD METALLIC SHAVINGS AT SHAKERS, CIRCULATION TO CLEAN HOLE IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | SWEEP OUT HI-VIS PILL, FLOW CHECK, POOH TO SURFACE, RIH WITH TAPER MILL ASSEMBLY. MILLING JOB.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14