## DDR#52
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 52
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 51.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 7RR |  | BHA NO. |  |  | 13 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 130
CHECK TIME | 9:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 981.6
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 827
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MMD65 |  | BIT SUB (F.V) |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 |  |  | ACT. SYS (BBL) | 1938.6
MW OUT (SG) | 2.08 | 2.08 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12932459 |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.73 | 0.38631 |  | RESV. SYS (BBL) | 1815
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 1X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.19 | 2.0521 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 4 X16, 2 X 18 |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 2.33 | 0.52029 |  | KILL MW (SG)
µ FUNNEL (SEC) | 65 | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2420 |  | 1X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.25 | 2.0655 |  | TOTAL | 3753.6
PV | 41 | 40 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.55 | 0.34611 |  | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 6 X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 55.27 | 12.3417 |  | RIG TANK | 135746
GEL ST. | 15/25 | 13/23 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CAMP TANK | 23182
WL (ml/30 min) | 8 | 7.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.7 | 6.1854 |  | CONSUMED | 7622
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.027945 |  | RECEIVED | 48000
ALK (MUD) | 0.7 | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 9 X 5.5'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | TOTAL | 158928
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 483000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 50000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 9000
KCl (mg/l) | 49574 | 49574 | JAR | 33.4 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 86000
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 33.4 | STAB - 2 |  | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 533000
HARDNESS (mg/l) | 440 | 440 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.2 | 0.2 | 8" DCS | 33.4 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 203.66 |  |  | MPCL | 8
LUBRICANT % | 0.75 | 0.75 | BHA ROT. HRS |  | 8.6 |  | BIT NO. 7RR |  | 2-3-WT-S,G-X-1-CT-TQ |  | BHA WT. IN MUD (TON) | [7 empty] | 22 |  |  | MPCL SERV | 23
SOLIDS % | 36.31 | 36.31 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 9.1 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 59
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 43791.08 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5170483.7667 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 25.97% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43640 | 43640.0833 | 2 | DRL | NPT-UP | MIL | CONT'D MILL OUT CMT FROM 2393.50M TO 2396M.
43640.0833 | 43640.125 | 1 | DRL | NPT-UP | CIR | SWEPT OUT HI-VIS PILL & CIRCULATED TO CLEAN HOLE. MEANWHILE DRESSED/POLISHED CSG FROM 2387M TO 2390M.
43640.125 | 43640.1354 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43640.1354 | 43640.3021 | 4 | DRL | NPT-UP | POOH | POOH FROM 2396M TO 240M.
43640.3021 | 43640.3125 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43640.3125 | 43640.3958 | 2 | DRL | NPT-UP | BHA | CONT'D POOH FROM 240M TO SURFACE. L/DOWN JAR & FLAT BTM MILL ASSEMBLY.
43640.3958 | 43640.4792 | 2 | DRL | NPT-UP | BHA | M/UP 12 1/4'' RR PDC BIT (HLB, MMD65DMH) WITH BIT SUB. RIH AS PER BHA DOWN TO 203M.
43640.4792 | 43640.7188 | 5.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 203M TO 2375M. FILLED UP STRING EVERY 15 STANDS.
43640.7188 | 43640.7292 | 0.25 | DRL | NPT-UP | RW | PRECAUTIONARY WASHED/REAMED DOWN FROM 2375M TO 2396M.
43640.7292 | 43640.875 | 3.5 | DRL | NPT-UP | DC | DRILLED OUT CMT FROM 2396M TO 2403M, OBSERVED ERRATIC TORQUE WHILE DRILLING OUT CEMENT BELOW 2401M. OBSERVED MAGNETIC METAL SHAVING AT SHAKERS. STOPPED DRILLING CEMENT. CIRCULATED FOR BTMS UP. OBSERVED EXCESSIVE METAL SHAVINGS AT SHAKERS.
43640.875 | 43640.9479 | 1.75 | DRL | NPT-UP | CIR | PUMPED 50 BBL HI-VIS PILL & CIRCULATED OUT AT HIGH GPM TO CLEAN HOLE. SMALL AMOUNT OF METAL SHAVINGS OBSERVED @ BOTTOMS UP.
43640.9479 | 43640.9583 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43640.9583 | 43641 | 1 | DRL | NPT-UP | POOH | POOH FROM 2403M TO 2058M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43641 | 43641.1354 | 3.25 | DRL | NPT-UP | POOH | POOH FROM 2396M TO 203M.
43641.1354 | 43641.1458 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43641.1458 | 43641.2292 | 2 | DRL | NPT-UP | BHA | POOH BHA FROM 203M TO SURFACE, MEANWHILE L/DOWN JAR, STABS AND BIT.
43641.2292 | 43641.25 | 0.5 | DRL | NPT-UP | BHA | P/UP AND M/UP 12 1/8'' FLAT BTM MILL (BLADED)+ BIT SUB + 8'' PONY DC IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | P/UP AND M/UP MILL ASSEMBLY IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D MILL OUT TO 2396M. SWEPT OUT HI-VIS PILL, POOH TO SURFACE, L/DOWN FLAT BTM MILL & WATER MELON MILL, P/UP AND M/UP 12 1/4'' RR PDC WITH PACKED HOLE BHA AND RIH TO BTM AT 2396M, DRILLED OUT CMT FROM 2396M TO 2403M, OBSERVED HIGH ERRATIC TORQUE FOLLOWED BY METALLIC SHAVINGS AT SHAKERS ON BTMS UP, SWEPT OUT HI-VIS PILL AND POOH TO 2058M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE, L/DOWN PDC BIT + JAR + STABS, P/UP AND M/UP MILLING ASSEMBLY, RIH TO BTM AT 2403M, MILL OUT JUNK/CMT.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14