## DDR#53
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 53
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 52.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  | 14 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 153
CHECK TIME | 13:00 | 22:30 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 940.6
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | FLAT BOTTOM MILL |  |  | 12.125 |  |  | 6 5/8 REG |  | 1.07 |  |  | PITS (BBL) | 796
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | BIT SUB (F.V) |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 |  |  | ACT. SYS (BBL) | 1889.6
MW OUT (SG) | 2.08 | 2.08 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | PONY DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 2.88 | 0.6431 |  | RESV. SYS (BBL) | 889.6
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | WATER MELLON MILL |  |  | 12.25 | 3.5 |  | 6 5/8 REG |  | 1.22 | 0.27242 |  | KILL MUD (BBL) | 1000
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | 3 X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 27.69 | 6.1831 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 58 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | ST. STAB |  |  | 12.25 | 3 |  | 6 5/8 REG |  | 1.73 | 0.38631 |  | TOTAL | 2779.2
PV | 41 | 41 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 9 X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 82.97 | 18.5271 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | D.JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | RIG TANK | 129973
GEL ST. | 15/28 | 14/26 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.58 | 6.1586 |  | CAMP TANK | 22563
WL (ml/30 min) | 8 | 8.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | CONSUMED | 6392
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 9 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | RECEIVED
ALK (MUD) | 0.8 | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [12 empty] | 0 |  | TOTAL | 152536
ALK (FILT.) | 0.7 | 0.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 11 | 11.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 485000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 48000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 171500
KCl (mg/l) | 47667.5 | 46714.2 | JAR | 43.2 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 171500
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS | 43.2 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 533000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.25 | 0.25 | 8" DCS | 43.2 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 241.42 |  |  | MPCL | 7
LUBRICANT % | 0.7 | 0.6 | BHA ROT. HRS |  | 9.8 |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 22 |  |  | MPCL SERV | 25
SOLIDS % | 36.4 | 36.5 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 10.7 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 60
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 123
DAILY WELL COST (US$) |  | 41354 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5211838 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE
% OF AFE SPENT |  | 26.18% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 6 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 6 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43641 | 43641.1354 | 3.25 | DRL | NPT-UP | POOH | POOH FROM 2396M TO 203M.
43641.1354 | 43641.1458 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43641.1458 | 43641.2292 | 2 | DRL | NPT-UP | BHA | POOH BHA FROM 203M TO SURFACE, MEANWHILE L/DOWN JAR, STABS AND BIT.
43641.2292 | 43641.3333 | 2.5 | DRL | NPT-UP | BHA | P/UP, M/UP AND RIH FLAT BOTTOM MILL (BLADED) + BIT SUB + 1 X 8'' PONY DC + WATER MELON MILL. RIH AS PER BHA DOWN TO 241M.
43641.3333 | 43641.5625 | 5.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 241M TO 2390M. FILLED UP STRING EVERY 15 STANDS.
43641.5625 | 43641.5833 | 0.5 | DRL | NPT-UP | RS | SERVICED TDS.
43641.5833 | 43641.6042 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED FOR 20 MINUTES. RECORDED SCR. RIH WITH CIR & TAGGED COMPRESSION @ 2403.30M.
43641.6042 | 43642 | 9.5 | DRL | NPT-UP | MIL | RESUMED MILLING. MILLED OUT FROM 2403.30M TO 2413M. MEANWHILE OBSERVED ERRATIC TORQUE FROM 2403.30M TO 2406M, OBSERVED METALLIC SHAVINGS AT BTM UP. OBSERVED CMT BELOW 2406M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43642 | 43642.2083 | 5 | DRL | NPT-UP | MIL | CONT'D MILL OUT FROM 2413M TO 2417.6M. STOPPED MILLING.
43642.2083 | 43642.25 | 1 | DRL | NPT-UP | CIR | CIRCULATION IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 2396M TO SURFACE. L/DOWN JAR, STABS & PDC BIT, P/UP AND M/UP FLAT BTM MILL ASSEMBLY AND RIH TO 2390M, RESUMED MILLING OUT FROM 2403.30M TO 2413M, MILLING IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE MILL OUT, CIRCULATION TO HOMOGENIZE/CONDITION MUD, POOH TO 2365M, R/UP DWS, P/TEST HOOK UP, PERFORM FIT, RESUME MILLING OUT TO 2420, POOH.
REMARKS |  |  | W.FORD FISHING ENGR./EQP ON LOCATION.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14