## DDR#54
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 54
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 53.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2420 / 2420 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-06-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  | 15 | IN (M) |  | 2420 |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1162.2
DEPTH, MD (M) | 2420 | 2420 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 693
MW IN (SG) | 2.08 | 2.08 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | BIT SUB (F.V) |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 |  |  | ACT. SYS (BBL) | 1855.2
MW OUT (SG) | 2.08 | 2.08 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | PONY DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 2.88 | 0.6431 |  | RESV. SYS (BBL) | 743
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | ST. STAB |  |  | 12.25 | 3 |  | 6 5/8 REG |  | 1.73 | 0.38631 |  | KILL MUD (BBL) | 1000
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | 1X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.19 | 2.0521 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 58 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.55 | 0.34611 |  | TOTAL | 2598.2
PV | 41 | 41 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 9X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 73.77 | 16.4727 |  | DIESEL (LTR)
YIELD POINT | 28 | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | RIG TANK | 120461
GEL ST. | 14/24 | 14/25 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.7 | 6.1854 |  | CAMP TANK | 21861
WL (ml/30 min) | 7.5 | 7.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.027945 |  | CONSUMED | 10214
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 9 X 5.5'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | RECEIVED
ALK (MUD) | 0.7 | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 142322
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 11 | 11 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 492000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 60000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 149800
KCl (mg/l) | 45760.8 | 45760.8 | JAR | 56.1 | STAB - 1 | 35.6 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 168800
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS | 56.1 | STAB - 2 | 9.8 | TFA (IN²) | [14 empty] | TOTAL | 552000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
SAND % | 0.1 | 0.1 | 8" DCS | 56.1 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 213.46 |  |  | MPCL | 7
LUBRICANT % | 0.7 | 0.6 | BHA ROT. HRS |  | 12.9 |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 23 |  |  | MPCL SERV | 23
SOLIDS % | 36.91 | 36.91 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 12.9 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 61
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 45919 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5257758 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 13.625
% OF AFE SPENT |  | 26.41% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 827
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 16 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 16 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43642 | 43642.2083 | 5 | DRL | NPT-UP | MIL | CONT'D MILL OUT FROM 2413M TO 2417.6M. STOPPED MILLING.
43642.2083 | 43642.2917 | 2 | DRL | NPT-UP | CIR | CIRCULATED TO CONDITION MUD.
43642.2917 | 43642.3125 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 2417.6M TO 2363M.
43642.3125 | 43642.3333 | 0.5 | DRL | NPT-UP | P/T | HELD PJSM FOR LOT, R/UP DOWELL CMT LINES. FLUSHED & P/TESTED AT 500 / 1500 PSI. HELD PRESSURE FOR 10 MINS OK.
43642.3333 | 43642.375 | 1 | DRL | NPT-UP | FIT | CLOSED BOP, PERFORMED LOT WITH 2.08 SG MUD. MAX SURFACE PRESSURE APPLIED 850 PSI. PRESSURE DROPPED & STABILIZED AT 827 PSI. (EMW = 2.32 SG @ 2387M).
43642.375 | 43642.3854 | 0.25 | DRL | NPT-UP | RIH | RIH FROM 2363M TO 2417.6M. PRECAUTIONARY WASHED/REAMED DOWN FROM 2393M TO BOTTOM AT 2417.6M.
43642.3854 | 43642.5625 | 4.25 | DRL | NPT-UP | MIL | CONT'D MILL OUT FROM 2417.60M TO 2419M.
43642.5625 | 43642.6146 | 1.25 | DRL | NPT-UP | CIR | SWEPT OUT 50 BBL HI-VIS PILL, KEPT CIRCULATING TILL SHAKERS CLEAN.
43642.6146 | 43642.625 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED , WELL STATIC.
43642.625 | 43642.8542 | 5.5 | DRL | NPT-UP | POOH | POOH FROM 2419M TO 241M (BHA).
43642.8542 | 43642.8646 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED , WELL STATIC.
43642.8646 | 43642.9479 | 2 | DRL | NPT-UP | BHA | POOH FROM 241M TO SURFACE. MEANWHILE L/DOWN JAR, STAB AND FLAT BTM MILL ASSEMBLY.
43642.9479 | 43643 | 1.25 | DRL | NPT-UP | BHA | P/UP & M/UP 12 1/4'' RR PDC BIT (HLB, MMD65, 4X16+2 X18) & BIT SUB. RIH AS PER BHA TO 90M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43643 | 43643.0417 | 1 | DRL | NPT-UP | BHA | CONT'D RIH FROM 90M TO 213M
43643.0417 | 43643.2396 | 4.75 | DRL | NPT-UP | RIH | RIH FROM 213M TO 2383M. FILLED UP STRING EVERY 15 STANDS.
43643.2396 | 43643.25 | 0.25 | DRL | NPT-UP | RW | RECORDED SCR, WASHED DOWN FROM 2383M TO 2390M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WASH DOWN IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D MILL OUT TO 2417.6M, CIRCULATED TO CONDITION MUD, PJSM, PERFORMED LOT AT EMD = 2.33SG, CONT'D MILL OUT FROM 2417.6M TO 2419M, SWEPT OUT HI-VIS & CIRCULATION, POOH TO SURFACE, L/DOWN MILL ASSEMBLY, P/UP 12 1/4'' RR PDC BIT, RIH AS PER BHA TO 16M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH WITH ROTARY BHA TO 2419M, DRILL OUT RAT HOLE + NEW FORMATION +/- 40M, POOH FOR BHA CHANGE.
REMARKS |  |  | RELEASED FISHING ENGR / TOOLS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14