## DDR#55
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 55
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2424 / 2424 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 54.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2424 / 2424 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 4
2019-06-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 7RR1 |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 2424 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1179.8
DEPTH, MD (M) | 2423 | 2424 | TVD @ 00:00HR (M) |  | 2424 |  | MANUFACTURER |  | HLB | [12 empty] | PITS (BBL) | 693
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 4 |  | TYPE |  | MMD65 | [12 empty] | ACT. SYS (BBL) | 1872.8
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12932459 | [12 empty] | RESV. SYS (BBL) | 700
ECD (SG) | 2.11 |  | AVG. ROP (M/HR) |  | 0.82 |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 1000
FL TEMP. °F | 130 |  | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  | 4 X16, 2 X 18 | [12 empty] | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 60 | 59 | AVG. RPM SURFACE |  | 50 |  | DEPTH IN (M) |  | 2420 | [12 empty] | TOTAL | 2572.8
PV | 42 | 42 | AVG. RPM DOWNHOLE |  | 50 |  | DEPTH OUT (M) |  | 2424 | [12 empty] | DIESEL (LTR)
YIELD POINT | 26 | 25 | FLOWRATE (GPM) |  | 650 |  | METERAGE (M) |  | 4 | [12 empty] | RIG TANK | 115524
GEL ST. | 14/25 | 15/25 | PRESSURE (PSI) |  | 2000 |  | RPM SURF. |  | 50 | [12 empty] | CAMP TANK | 21156
WL (ml/30 min) | 6.0 | 6 | TORQ. ON-BTM (KLB-FT) |  | 6-7 |  | RPM BTM. |  | 50 | [12 empty] | CONSUMED | 5642
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 6-10 | [12 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 128 |  | AVG. ROP (M/HR) |  | 1.0989 | [12 empty] | TOTAL | 136680
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 130 |  | BIT ROT HRS. |  | 3.64 | [12 empty] | WATER (LTR)
PH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 127 |  | K-REVS IN 24 HRS |  | 10.85 | [12 empty] | RIG STORAGE | 490000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 10.85 | [12 empty] | CAMP STORAGE | 52000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 47.2 | [12 empty] | CONSUMED | 169500
KCl (mg/l) | 45760.8 | 45760.8 | JAR | 62.9 | STAB - 1 | 42.4 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 159500
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS | 62.9 | STAB - 2 | 16.6 | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 542000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 62.9 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 7
LUBRICANT % | 0.7 | 0.7 | BHA ROT. HRS |  | 6.86 |  | BIT NO. 7RR1 |  | 2-3-BT-S-X-1-WT-PR |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 23
SOLIDS % | 37.41 | 37.41 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 7.5 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 60
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 119
DAILY WELL COST (US$) |  | 49517 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5307275 | SHAKER-3 | 1 X 100 | 2 X 100 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 13-3/8 / 13-5/8
% OF AFE SPENT |  | 26.66% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 7 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 7 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43643 | 43643.0417 | 1 | DRL | NPT-UP | BHA | CONT'D RIH FROM 90M TO 213M
43643.0417 | 43643.2396 | 4.75 | DRL | NPT-UP | RIH | RIH FROM 213M TO 2383M. FILLED UP STRING EVERY 15 STANDS.
43643.2396 | 43643.2708 | 0.75 | DRL | NPT-UP | RW | RECORDED SCR, WASHED DOWN FROM 2383M TO 2416M.
43643.2708 | 43643.3125 | 1 | DRL | NPT-UP | RW | DRESSED F/SHOE FROM 2416M TO 2419M. DRILLED RAT HOLE CEMENT DOWN TO 2420M.
43643.3125 | 43643.3333 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED TO CLEAN HOLE.
43643.3333 | 43643.5312 | 4.75 | DRL | PT-P | DCD | DRILLED 12-1/4" HOLE FROM 2420M TO 2424M. DECIDED TO POOH DUE TO LOW ROP.
43643.5312 | 43643.5417 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, LEVEL STATIC.
43643.5417 | 43643.7083 | 4 | DRL | PT-P | POOH | POOH FROM 2424M TO 753M.
43643.7083 | 43643.7292 | 0.5 | DRL | PT-P | RU | HELD PJSM. R/UP DOWELL CMT LINES. FLUSHED & P/TESTED AT 500 / 1500 PSI. HELD PRESSURE FOR 10 MINS OK.
43643.7292 | 43643.75 | 0.5 | DRL | PT-P | FIT | CLOSED BOP AND PERFORMED FIT WITH 2.10 SG MUD. MAX SURFACE PRESSURE APPLIED 688 PSI (EMD = 2.30 SG), OK.
43643.75 | 43643.8542 | 2.5 | DRL | PT-P | POOH | POOH FROM 753M TO 213M (BHA TOP).
43643.8542 | 43643.9375 | 2 | DRL | PT-P | BHA | CONT'D POOH FROM 213M TO SURFACE. L/DOWN JAR, STABS & BIT.
43643.9375 | 43644 | 1.5 | DRL | PT-P | BHA | P/UP & M/UP USED TC BIT + MUD MOTOR + S. STAB + MWD TOOLS (CHECKED & PLACED SLIMPULSE INSIDE SPSA).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43644 | 43644.0104 | 0.25 | DRL | PT-P | BHA | CONT'D RIH TO 23M.
43644.0104 | 43644.25 | 5.75 | DRL | NPT-UP | P/T | CONNECTED TDS, WHILE PERFORMING SHALLOW TEST, MWD TOOL MALFUNCTIONED (NOT RECEIVING SIGNALS). ATTEMPTED SEVERAL TIMES ON DIFFERENT GPM, NO SUCCESS. RETRIEVED SLIMPULSE, DUMPED SAME & CHECKED ON SURFACE, CHANGED SURFACE SYSTEM (CABLES/ SENSOR). PLACED SLIMPULSE IN SPSA, ATTEMPTED TO RECTIFY PROBLEM, NO SUCCESS. DISCUSSED WITH SLB BASE, RETRIEVED SLIMPULSE AGAIN, DUMPING AND CHECKING DATA IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RECTIFYING MWD TOOL PROBLEM IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 2383M, PRECAUTIONARY WASHED DOWN FROM 2383M TO 2416M, DRESSED F/SHOE FROM 2416M TO 2419M, DRILLED OUT CMT IN RAT HOLE, DRILLED 12 1/4'' HOLE FROM 2420M TO 2424M, DECIDED TO POOH DUE TO LOW PENETRATION. POOH TO 753M, PERFORMED FIT @ EMW = 2.30 SG WITH 2.10 SG MUD. POOH TO SURFACE, P/UP MOTOR ASSEMBLY IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | P/UP AND M/UP MOTOR ASSEMBLY WITH NEW 12 1/4'' PDC BIT, SHALLOW TEST, RIH TO BTM AT 2424M, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14