## DDR#56
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 56
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH/MOHSIN/TALHA/AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 2636 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 55.5833
RIG REP.: |  | JAVED MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2648 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 31
2018-02-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5 |  | BHA No. |  |  | 8 | IN (M) |  | 2367 |  | OUT (M) |  |  | STRING (BBL) | 156
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2636 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1047
DEPTH, MD (M) | 2622 | 2637 | TVD @ 00:00HR (M) |  | 2636 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12-1/4" |  |  | 6-5/8 REG |  | 0.36 |  |  | PITS (BBL) | 1008
MW IN (SG) | 2 | 2 | DAILY PROGRESS (M) |  | 31 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 9.97 |  |  | ACT. SYS (BBL) | 2211
MW OUT (SG) | 2 | 2 | INST. ROP (M/HR) |  | 1.72 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.59 |  |  | RESV. SYS (BBL) | 1051
ECD (SG) | 2.033 | 2.033 | AVG. ROP (M/HR) |  | 1.49 |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 1.55 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F | 171 | 170 | AVG. WOB (TON) |  | 6-13 |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.61 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 63 | 65 | AVG. RPM SURFACE |  | 0-100 |  | DEPTH IN (M) |  | 2367 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.29 |  |  | TOTAL | 3862
PV | 42 | 43 | AVG. RPM DOWNHOLE |  | 75-175 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.48 |  |  | DIESEL (LTR)
YIELD POINT | 29 | 29 | FLOWRATE (GPM) |  | 670-700 |  | METERAGE (M) |  | 269 |  | NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 9 |  |  | RIG TANK | 95800
GEL ST. | 11/40 | 11/42 | PRESSURE (PSI) |  | 3230-3410 |  | RPM SURF. |  | 0-100 |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.68 |  |  | CAMP TANK | 16000
WL (ml/30 min.) | 4 | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 4-8 |  | RPM BTM. |  | 75-175 |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 5.15 |  |  | CONSUMED | 11700
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 1-13 |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.76 |  |  | RECEIVED
ALK (MUD) | 0.2 | 0.2 | STRING WT. (TON) - ROT |  | 120 |  | AVG. ROP (M/HR) |  | 1.6383 |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.9 |  |  | TOTAL | 111800
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  | 125 |  | BIT ROT HRS. |  | 164.19 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.25 |  |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 124 |  | K-REVS IN 24 HRS |  | 185 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1164 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 44.55 | [12 empty] | CONSUMED | 102720
KCl (mg/l) | 43854.1 | 43854.1 | JAR | 93.69 | NMDC | 93.69 | JET VELOCITY (M/SEC) |  | 56.4 | [12 empty] | RECEIVED | 102720
CHLORIDES | 20000 | 20000 | 5" HWDPS | 187.99 | STAB - 1 | 93.69 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 445000
CALCIUM | 160 | 160 | 8" DCS | 187.99 | STAB - 2 & 3 |  | HSI |  | 1.7 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS |  | SPSA | 93.69 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 177.59 |  |  | MPCL | 5
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 187.99 |  | BIT No. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 16
SOLIDS % | 32.24 | 32.24 | ON BOTTOM HRS |  | 164.19 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY | 4
M.B.T. | 15 | 15 | CIRC. HRS |  | 218.65 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2529 |  | 2.05 |  | 320.42 |  |  | 0.11 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 55795.6544 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 2557 |  | 1.87 |  | 318.15 |  |  | 0.21 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5286425.833 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2585 |  | 1.96 |  | 314.96 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 13.375''
% OF AFE SPENT |  | 29.29% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2614 |  | 1.75 |  | 315.83 |  |  | 0.22 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 668
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-14 | 2018-02-28 | ANNULAR | CAMERON CHINA | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2625 |  | 400/500 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CAMERON CHINA | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2625 |  | 400/500 |  | CHINJI | 342
FIRE DRILL | 2018-02-09 | 2018-02-23 | BLIND RAMS | CAMERON CHINA | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS | CAMERON CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-02-10 | 2018-02-24 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-02-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-16 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43145 | 43145.25 | 6 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2605M TO 2619M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
43145.25 | 43145.6042 | 8.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN SLIDE MODE FROM 2619M TO 2624M.
43145.6042 | 43146 | 9.5 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2624M TO 2636M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43146 | 43146.25 | 6 | DRL | PT-P | DM | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2636M TO 2648M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12.25" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12.25'' HOLE IN ROTARY MODE FROM 2605M TO 2636M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12.25'' HOLE SECTION.
REMARKS |  |  | CONDUCTED BOP DRILL. OBSERVED POOR RESPONSE.
Formulas:
DHARIAN - 1 = [DATE]+14
Note on E33: 94.3 hrs from previous run.
Note on E34: 94.3 hrs from previous run