## DDR#57
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 57
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH/ MASOOD / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2487 / 2487 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 56.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2504 / 2504 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 54
2019-06-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 8 |  | BHA NO. |  |  | 16 | IN (M) |  | 2424 |  | OUT (M) |  |  | STRING (BBL) | 180
CHECK TIME | 6:30 | 23:59 | MD @ 00:00HR (M) |  | 2487 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 939
DEPTH, MD (M) | 2444 | 2487 | TVD @ 00:00HR (M) |  | 2487 |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.4 |  |  | PITS (BBL) | 661
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 54 |  | TYPE |  | TD606FX |  | MUD MOTOR |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.41 | 2.3245 |  | ACT. SYS (BBL) | 1780
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  | 3.2 |  | SERIAL NO. |  | 5293592 |  | FLOAT SUB |  |  | 8.25 | 2.9375 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 636
ECD (SG) | 2.13 | 2.13 | AVG. ROP (M/HR) |  | 2.42 |  | IADC CODE |  | M223 |  | ST.STAB |  |  | 12.25 | 3 |  | 6 5/8 REG |  | 1.55 | 0.34611 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | 145 | 146 | AVG. WOB (TON) |  | 9 |  | NOZZLES (1/32") |  | 6 X15 |  | 1X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.19 | 2.0521 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 63 | 75 | AVG. RPM SURFACE |  | 80 |  | DEPTH IN (M) |  | 2424 |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 2.33 | 0.52029 |  | TOTAL | 2416
PV | 43 | 44 | AVG. RPM DOWNHOLE |  | 160 |  | DEPTH OUT (M) |  |  |  | 9X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 82.93 | 18.5181 |  | DIESEL (LTR)
YIELD POINT | 27 | 29 | FLOWRATE (GPM) |  | 730 |  | METERAGE (M) |  | 63 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.43 | 2.1057 |  | RIG TANK | 100301
GEL ST. | 12/28 | 13/29 | PRESSURE (PSI) |  | 2500 - 3000 |  | RPM SURF. |  | 80-100 |  | 3 X 8'' DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.56 | 6.1541 |  | CAMP TANK | 19735
WL (ml/30 min) | 6.0 | 5.7 | TORQ. ON-BTM (KLB-FT) |  | 6-9 |  | RPM BTM. |  | 160-185 |  | X/O |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.027945 |  | CONSUMED | 11703
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 6-14 |  | 9 X 5.5'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.92 | 3.1225 |  | RECEIVED
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  | 127 |  | AVG. ROP (M/HR) |  | 2.3077 | [12 empty] | TOTAL | 120036
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 128 |  | BIT ROT HRS. |  | 27.3 | [12 empty] | WATER (LTR)
PH | 9.5 | 10 | SLACK-OFF WT. (TON) |  | 126 |  | K-REVS IN 24 HRS |  | 216.08 | [12 empty] | RIG STORAGE | 250000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 247.18 | [12 empty] | CAMP STORAGE | 50000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 52.9 | [12 empty] | CONSUMED | 357000
KCl (mg/l) | 42901 | 44807.5 | JAR | 92.66 | STAB - 1 | 72.16 | JET VELOCITY (M/SEC) |  | 68.86 | [12 empty] | RECEIVED | 111000
CHLORIDES (mg/l) | 23000 | 24000 | 5 1/2" HWDPS | 92.66 | STAB - 2 | 46.36 | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 300000
HARDNESS (mg/l) | 500 | 500 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.7 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 92.66 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 230.27 |  |  | MPCL | 9
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 22.86 |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 23
SOLIDS % | 37.16 | 37.03 | ON BOTTOM HRS |  | 22.34 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 8.8 | 8.8 | CIRC. HRS |  | 22.86 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 61
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 94969 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5473839 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LAST CSG SIZE | 13-3/8 / 13-5/8
% OF AFE SPENT |  | 27.5% | MUD CLEANER | 3 X 170 | [6 empty] | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 2485 | 250/250/250 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 2485 | 350/350/350 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 2485 | 420/410/410 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 18 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 18 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43645 | 43646 | 24 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 2433M TO 2487M. WASHED/REAMED DRILLED INTERVAL PRIOR CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43646 | 43646.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 2487M TO 2504M. WASHED/REAMED DRILLED INTERVAL PRIOR CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4'' HOLE FROM 2433M TO 2487M. WASHED/REAMED DRILLED INTERVAL PRIOR CONNECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14