## DDR#60
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 60
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH / MOHSIN / TALHA / AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 2777 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 59.5833
RIG REP.: |  | JAVED MUGHAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 2777 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-02-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5 |  | 5RR1 | BHA NO. |  |  | 9 | IN (M) |  | 2777 |  | OUT (M) |  |  | STRING (BBL) | 162.34
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2777 |  | SIZE (IN) |  | 12-1/4" |  | 12-1/4" | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1099.99
DEPTH, MD (M) | 2777 | 2777 | TVD @ 00:00HR (M) |  | 2777 |  | MANUFACTURER |  | HLB |  | HLB | PDC BIT |  |  | 12-1/4" |  |  | 6-5/8 REG |  | 0.36 |  |  | PITS (BBL) | 1018
MW IN (SG) | 2 | 2 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MMD65DMH |  | MMD65DMH | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 10.48 |  |  | ACT. SYS (BBL) | 2280.33
MW OUT (SG) | 2 | 2 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12932459 |  | 12932459 | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.79 |  |  | RESV. SYS (BBL) | 1048
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M323 |  | M323 | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 1.73 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 x 16/32" |  | 6 x 16/32" | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.6 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 60 | 61 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2367 |  | 2777 | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.44 |  |  | TOTAL | 3928.33
PV | 36 | 37 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 2777 |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.54 |  |  | DIESEL (LTR)
YIELD POINT | 25 | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 410 |  |  | NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 9 |  |  | RIG TANK | 107500
GEL ST. | 11/40 | 12/36 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 0 - 100 |  |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.38 |  |  | CAMP TANK | 14000
WL (ml/30 min.) | 5 | 5.1 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 75 - 175 |  |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 5.63 |  |  | CONSUMED | 5000
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 1 - 13 |  |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.88 |  |  | RECEIVED
ALK (MUD) | 0.2 | 0.2 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 1.9098 |  |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.74 |  |  | TOTAL | 121500
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 214.68 |  |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 55.84 |  |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 139 | [13 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1694 | [13 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 44.28 | [13 empty] | CONSUMED | 90830
KCl (mg/l) | 40994.1 | 40994.4 | JAR |  | NMDC | 0 | JET VELOCITY (M/SEC) |  | 56.4 | [13 empty] | RECEIVED | 90830
CHLORIDES | 18500 | 18500 | 5" HWDPS | 0 | STAB - 1 | 0 | TFA (IN²) |  | 1.18 |  | 1.18 | [11 empty] | TOTAL | 495000
CALCIUM | 160 | 160 | 8" DCS | 0 | STAB - 2 & 3 |  | HSI |  | 1.7 | [13 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS |  | SPSA | 0 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  |  | TOTAL LENGTH (M) | [7 empty] | 178.41 |  |  | MPCL | 5
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 0 |  | BIT No. 5 |  | 1/1/WT/A/X/I/NO/BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 16
SOLIDS % | 33.31 | 33.31 | ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY | 4
M.B.T. | 15 | 15 | CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 20" SURFACE CASING |  |  | 594 |  | 2614 |  | 1.75 |  | 315.83 |  |  | 0.22 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 28845.3044 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 |  | 2643 |  | 2.06 |  | 315.69 |  |  | 0.32 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5477692.5873 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  |  | 2673 |  | 2.17 |  | 321.49 |  |  | 0.24 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 30.35% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  |  | 2700 |  | 2.12 |  | 322.29 |  |  | 0.06 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 668
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-14 | 2018-02-28 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" |  | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" |  | 4200 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-02-09 | 2018-02-23 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" |  | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 |  | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-02-10 | 2018-02-24 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-02-18 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 17 |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-02-16 | 2018-03-02 | NEXT BOP TEST DATE |  | 2018-03-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 17 |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43149 | 43149.0938 | 2.25 | DRL | PT-P | POOH | CONT'D POOH FROM 1120M TO 178M (TOP OF BHA).
43149.0938 | 43149.1042 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC.
43149.1042 | 43149.2188 | 2.75 | DRL | PT-P | BHA | POOH BHA FROM 178M TO 30M. WHILE POOH L/D COMPLETE BHA FOR INSPECTION.
43149.2188 | 43149.3125 | 2.25 | DRL | PT-P | BHA | HANDLED DIRECTIONAL BHA AND L/DOWN DIRECTIONAL TOOLS & BIT.
43149.3125 | 43149.5417 | 5.5 | DRL | PT-P | BOPT | PJSM. M/U & RIH TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP & IBOP @ 300 PSI/5000 PSI FOR 5/10 MIN - OK. P/TESTED LOWER PIPE RAM BOP(5" RAMS), UPPER PIPE RAM BOP (VARIABLE-4.5" TO 7"), BLIND RAM BOP, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE & KILL LINE CHECK VALVE @ 300/6500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE/STANDPIPE @ 300/4000 PSI FOR 5/10 MIN - OK. SET WEAR BUSHING.
43149.5417 | 43149.5625 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43149.5625 | 43149.7188 | 3.75 | DRL | PT-P | BHA | P/UP 9-5/8" MUD MOTOR & REPLACED SLEEVE STAB WITH BLANK SLEEVE. P/U & M/U USED 12.25" TRI-CONE BIT, SLB MUD MOTOR, ST.STAB, SPSA AND INSTALLED MWD TOOL. SET MUD MOTOR BEND TO 1.5° & ADJUSTED TOOLFACE OFFSET. SHALLOW FUNCTION TESTED MUD MOTOR & MWD @ 690 GPM & 1190 PSI - OK. BROKE OUT 12.25" TRI-CONE BIT.
43149.7188 | 43149.8542 | 3.25 | DRL | PT-P | BHA | P/UP & M/UP 12.25" RR PDC BIT (HLB, MMD65DMH) & RIH DIRECTIONAL BHA TO 178M.
43149.8542 | 43150 | 3.5 | DRL | PT-P | RIH | RIH FROM 178M TO 1748M. FILLED UP STRING EVERY 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43150 | 43150.0938 | 2.25 | DRL | PT-P | RIH | CONT'D RIH FROM 1748M TO 2346M. FILLED UP STRING EVERY 15 STANDS.
43150.0938 | 43150.1562 | 1.5 | DRL | NPT-P | RS | SLIPPED AND CUT 26M DRILL LINE.
43150.1562 | 43150.2292 | 1.75 | DRL | PT-P | RIH | CONT'D RIH FROM 2346M TO 2746M. OBSERVED COMPRESSION @ 2746M
43150.2292 | 43150.25 | 0.5 | DRL | PT-P | RW | M/UP TDS & REAMED DOWN TO 2749M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | RIH TO BOTTOM.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. P/TESTED BOP. RIH 12.25" DIRECTIONAL BHA FROM SURFACE TO 1748M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM & DRILL AHEAD 12.25" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14