## DDR#60
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 60
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-03
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH/ MASOOD / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2627 / 2627 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 59.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2627 / 2627 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 21
2019-07-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 8 |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 8:30 | 23:59 | MD @ 00:00HR (M) |  | 2627 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1277
DEPTH, MD (M) | 2627 | 2627 | TVD @ 00:00HR (M) |  | 2627 |  | MANUFACTURER |  | BAKER | [12 empty] | PITS (BBL) | 544
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 21 |  | TYPE |  | TD606FX | [12 empty] | ACT. SYS (BBL) | 1821
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5293592 | [12 empty] | RESV. SYS (BBL) | 625
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.4 |  | IADC CODE |  | M223 | [12 empty] | KILL MUD (BBL) | 1000
FL TEMP. °F | 161 |  | AVG. WOB (TON) |  | 10 |  | NOZZLES (1/32") |  | 6 X15 | [12 empty] | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 65 | 70 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2424 | [12 empty] | TOTAL | 2446
PV | 43 | 42 | AVG. RPM DOWNHOLE |  | 185 |  | DEPTH OUT (M) |  | 2627 | [12 empty] | DIESEL (LTR)
YIELD POINT | 28 | 29 | FLOWRATE (GPM) |  | 775 |  | METERAGE (M) |  | 203 | [12 empty] | RIG TANK | 111228
GEL ST. | 14/28 | 13/26 | PRESSURE (PSI) |  | 3000 -3400 |  | RPM SURF. |  | 100 | [12 empty] | CAMP TANK | 17513
WL (ml/30 min) | 5.4 | 5.2 | TORQ. ON-BTM (KLB-FT) |  | 4-6 |  | RPM BTM. |  | 175-185 | [12 empty] | CONSUMED | 13019
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 2-3 |  | WOB (TON) |  | 6-15 | [12 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.4 | STRING WT. (TON) - ROT |  | 128 |  | AVG. ROP (M/HR) |  | 2.6093 | [12 empty] | TOTAL | 128741
ALK (FILT.) | 0.4 | 0.3 | PICK-UP WT. (TON) |  | 130 |  | BIT ROT HRS. |  | 77.8 | [12 empty] | WATER (LTR)
PH | 9.8 | 9.5 | SLACK-OFF WT. (TON) |  | 127 |  | K-REVS IN 24 HRS |  | 96.46 | [12 empty] | RIG STORAGE | 490000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 802.42 | [12 empty] | CAMP STORAGE | 46000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 51.9 | [12 empty] | CONSUMED | 224000
KCl (mg/l) | 43854 | 43854 | JAR | 81.88 | STAB - 1 | 128.5 | JET VELOCITY (M/SEC) |  | 73.17 | [12 empty] | RECEIVED | 273000
CHLORIDES (mg/l) | 24000 | 23000 | 5 1/2" HWDPS | 149 | STAB - 2 | 102.7 | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 536000
HARDNESS (mg/l) | 440 | 460 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 3.4 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 149 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 8
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 10 |  | BIT NO. 8 |  | 0-0-NO-C-X-I-NO-BHA |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 22
SOLIDS % | 37.34 | 37.48 | ON BOTTOM HRS |  | 8.74 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | CIRC. HRS |  | 10 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 52577 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5668539 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2410/2410 |  | 1 | [6 empty] | TOTCO |  | LAST CSG SIZE | 13-3/8 / 13-5/8
% OF AFE SPENT |  | 28.48% | MUD CLEANER | 3 X 170 | [6 empty] | 2616/2616 |  | 2 | [6 empty] | TOTCO |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 2571 | 270/320/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 2571 | 270/320/400 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 2571 | 270/320/400 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43648 | 43648.3542 | 8.5 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 2606M TO 2627M. WASHED/REAMED DRILLED INTERVAL PRIOR CONNECTION.
43648.3542 | 43648.3958 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43648.3958 | 43648.4062 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43648.4062 | 43648.7083 | 7.25 | DRL | PT-P | POOH | DROPPED TOTCO. POOH FROM 2627M TO 230M (BHA TOP). WHILE POOH, OBSERVED TIGHT SPOT @ 2513M. PUMPED OUT FROM 2513M TO 2493M.
43648.7083 | 43648.7188 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43648.7188 | 43648.75 | 0.75 | DRL | PT-P | BHA | POOH FROM 230M TO 144M. L/D 7 x HWDP.
43648.75 | 43648.8125 | 1.5 | DRL | PT-P | E/C | P/UP & M/U 8 1/4''PBL SUB + 2 x HWDP. FUNCTION TESTED PBL SUB, OK. (PORTS OPENED AT 100 PSI, CLOSED AT 2200 PSI) L/D PBL SUB.
43648.8125 | 43648.9583 | 3.5 | DRL | PT-P | BHA | CONT'D POOH BHA FROM 144M TO SURFACE. L/D COMPLETE BHA INCLUDING JAR, STABS, MUD MOTOR AND BIT. MEANWHILE RETRIEVED TOTCO SURVEY TOOL, FOUND INCLINATION = 2.0°
43648.9583 | 43649 | 1 | DRL | PT-P | BOPT | HELD PJSM, P/UP AND M/UP TEST PLUG ASSEMBLY, RETRIEVED WEAR BUSHING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43649 | 43649.1458 | 3.5 | DRL | PT-P | BOPT | SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE VALVES @ 500 PSI/4000 PSI FOR 5 / 10 MIN - OK. CLOSED UPPER PIPE RAM BOP (VARIABLE: 4.5" TO 7") P/TESTED HCR VALVES & MANUAL VALVES @ KILL LINE /CHOKE LINE; FOSV, IBOP, MANUAL IBOP/ROTARY HOSE;CO-FLEXIP-MASTER VALVE @ CHOKE MANIFOLD & KILL LINE CHECK VALVE @ 500 / 8000 PSI FOR 5 / 10 MIN - OK. P/TESTED BLIND RAM @ 500/8000 PSI FOR 5/10 MIN, OK. RETRIEVED TEST PLUG & SET WEAR BUSHING.
43649.1458 | 43649.25 | 2.5 | DRL | PT-P | BHA / E/C | P/UP & M/UP SCHL DIRECTIONAL/PERFORMANCE TOOLS + USED TC BIT. SHALLOW TEST RSS IN PROGRESS
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | SHALLOW TEST RSS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D DRILLING 12 1/4'' HOLE FROM 2606M TO 2627M, CIRCULATION, FLOW CHECKED-OK, POOH TO SURFACE MEANWHILE L/DOWN ALL BHA COMPONENTS FOR INSPECTION, F/TESTED PBL SUB, OK. BOP TEST IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | BOP TEST, P/UP SINGLE BY SINGLE DIRECTIONAL/ PERFORMANCE ASSEMBLY + BHA COMPONENTS MEANWHILE SHALLOW TEST DIRECTIONAL TOOLS, RIH TO BTM AT 2627M, RESUME DRILLING.
REMARKS |  |  | RECEIVED 8 1/4'' PBL SUB.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14