## DDR#61
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 61
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH/ MASOOD / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2627 / 2627 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 60.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2633 / 2633 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-07-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 9 |  | BHA NO. |  |  | 17 | IN (M) |  | 2627 |  | OUT (M) |  |  | STRING (BBL) | 188
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  | 2627 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 993
DEPTH, MD (M) | 2627 |  | TVD @ 00:00HR (M) |  | 2627 |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.43 |  |  | PITS (BBL) | 795
MW IN (SG) | 2.1 |  | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD605X |  | POWER DRIVE PD |  |  | 9.5 | 5.125 |  | 6 5/8 REG |  | 4.25 | 0.94902 |  | ACT. SYS (BBL) | 1976
MW OUT (SG) | 2.1 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 7913471 |  | X/O |  |  | 9 | 2.875 |  | 6 5/8 REG |  | 0.6 | 0.13398 |  | RESV. SYS (BBL) | 522
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | M/MOTOR (S. STAB) |  |  | 12.125 | 7.875 |  | 6 5/8 REG |  | 10.57 | 2.3603 |  | KILL MUD (BBL) | 1000
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 5 x 16/32 |  | FLOAT SUB |  |  | 8.25 | 2.9375 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 65 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2627 |  | ST.STAB |  |  | 12.25 | 2.875 |  | 6 5/8 REG |  | 2.36 | 0.52698 |  | TOTAL | 2498
PV | 43 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | L.SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.6 | 0.13398 |  | DIESEL (LTR)
YIELD POINT | 28 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | SPSA |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | RIG TANK | 106783
GEL ST. | 13/26 |  | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | U.SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | CAMP TANK | 16720
WL (ml/30 min) | 5 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | ST.STAB |  |  | 12.25 | 2.875 |  | 6 5/8 REG |  | 2.44 | 0.54485 |  | CONSUMED | 5238
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | NMDC |  |  | 8.25 | 2.8125 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | RECEIVED
ALK (MUD) | 0.4 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | TOTAL | 123503
ALK (FILT.) | 0.3 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | 8X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 73.88 | 16.4973 |  | WATER (LTR)
PH | 9.5 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | 3X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.029416 |  | CONSUMED | 111500
KCl (mg/l) | 43854 |  | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) |  |  |  | 9 X 5.5'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | RECEIVED | 100500
CHLORIDES (mg/l) | 23000 |  | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 525000
HARDNESS (mg/l) | 480 |  | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
PENETREX % | 2 |  | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 241.93 |  |  | MPCL | 8
LUBRICANT % | 0.7 |  | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 23
SOLIDS % | 37.48 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 |  | CIRC. HRS |  | 3 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 59
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 119
DAILY WELL COST (US$) |  | 78416.18 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2503 |  | 1.5 |  | 329.25 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5746875.5067 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2561 |  | 1.94 |  | 322.99 |  |  |  |  | MWD |  | LAST CSG SIZE | 13-3/8 / 13-5/8
% OF AFE SPENT |  | 28.87% | MUD CLEANER | 3 X 170 | [6 empty] | 2589 |  | 2.09 |  | 316.86 |  |  |  |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 2614 | 500/550/600 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 2614 | 500/550/600 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 2614 | 500/550/600 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43649 | 43649.1458 | 3.5 | DRL | PT-P | BOPT | SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE VALVES @ 500 PSI/4000 PSI FOR 5 / 10 MIN - OK. CLOSED UPPER PIPE RAM BOP (VARIABLE: 4.5" TO 7") P/TESTED HCR VALVES & MANUAL VALVES @ KILL LINE /CHOKE LINE; FOSV, IBOP, MANUAL IBOP/ROTARY HOSE;CO-FLEXIP-MASTER VALVE @ CHOKE MANIFOLD & KILL LINE CHECK VALVE @ 500 / 8000 PSI FOR 5 / 10 MIN - OK. P/TESTED BLIND RAM @ 500/8000 PSI FOR 5/10 MIN, OK. RETRIEVED TEST PLUG & SET WEAR BUSHING.
43649.1458 | 43649.25 | 2.5 | DRL | NPT-UP | BHA / E/C | M/UP 12-1/4" RR TC BIT WITH POWER DRIVE & RIH. M/U TDS. CIRCULATED & FUNCTION TESTED. OBSERVED FLOW FROM ALL PADS. L/D POWER DRIVE.
43649.25 | 43649.3125 | 1.5 | DRL | PT-P | BHA / E/C | M/UP 12-1/4" RR TC BIT WITH BACKUP POWER DRIVE & RIH. M/U TDS. CIRCULATED & FUNCTION TESTED. DOWN LINKED / PROGRAMMED POWER DRIVE DURING CIRCULATION. FUNCTION TESTED AFTER DOWN LINKING. OBSERVED WORKING SATISFACTORILY.
43649.3125 | 43649.4271 | 2.75 | DRL | PT-P | BHA / E/C | P/UP MUD MOTOR, 12-1/8" S.STAB; SPSA. M/UP WITH POWER DRIVE & RIH AS PER BHA DOWN TO 29 M. LOADED SLIM PUSE INSIDE SPSA. M/UP TDS. FUNCTION TESTED @ 600 GPM/500 PSI, OK. PULLED BACK TO ROTARY TABLE. L/DOWN TC BIT. M/U NEW 12-1/4" PDC BIT (BAKER, TD605X, SR # 7913471, 5 X 16/32") WITH PD.
43649.4271 | 43649.625 | 4.75 | DRL | PT-P | BHA | CONT'D RIH VORTEX BHA DOWN TO 241M. WHILE RIH P/UP BHA; 8'' PBL SUB, D.JAR, 11 X 8'' DC & 9 X 5 1/2'' HWDP.
43649.625 | 43649.8438 | 5.25 | DRL | PT-P | RIH | CONT'D RIH DOWN TO 2126M. FILLED UP STRING EVERY 15 STANDS.
43649.8438 | 43649.8958 | 1.25 | DRL | PT-P | RS | SLIPPED & CUT 35M D. LINE.
43649.8958 | 43649.9583 | 1.5 | DRL | PT-P | RIH | CONT'D RIH FROM 2126M TO 2500M. MEANWHILE RECORDED MWD CHECK SHOT @ 2440M
43649.9583 | 43650 | 1 | DRL | PT-P | RW | WASHED/REAMED FROM 2500M TO 2584M, MEANWHILE RECORDED MWD SURVEY @ 2527M
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43650 | 43650.0208 | 0.5 | DRL | NPT-UP | S | WHILE RECORDING MWD SURVEY AT 2584M, OBSERVED PROBLEM IN MWD TOOL SIGNALS. RECORDED MWD SURVEY IN 3RD ATTEMPT.
43650.0208 | 43650.125 | 2.5 | DRL | PT-P | RW | CONT'D WASHED/ REAMED DOWN TO BOTTOM AT 2627M, OBSERVED HARD REAMING BELOW 2600M. MEANWHILE RECORDED MWD SURVEY, RECORDED SCR.
43650.125 | 43650.25 | 3 | DRL | PT-P | DM | BROKE IN THE BIT, DRILLED 12 1/4'' HOLE FROM 2627M TO 2633M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | PERFORMED BOP TEST AS PER POLICY, P/UP AND M/UP SCHL DIRECTIONAL/PERFORMANCE TOOLS, SHALLOW TESTED SAME, OK, RIH TO 2126M, MEANWHILE P/UP BHA, FILLED UP STRING EVERY 15 STANDS, CUT AND SLIP D. LINE, CONT'D RIH FROM 2126M TO 2500M, WASHED/REAMED FROM 2500M TO 2584.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE REAM DOWN TO BTM AT 2627M, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14