## DDR#62
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 62
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH/ MASOOD / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2663 / 2663 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 61.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2668 / 2668 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 36
2019-07-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 9 |  | BHA NO. |  |  | 17 | IN (M) |  | 2627 |  | OUT (M) |  |  | STRING (BBL) | 189
CHECK TIME | 14:30 | 23:59 | MD @ 00:00HR (M) |  | 2663 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1007.2
DEPTH, MD (M) | 2648 | 2663 | TVD @ 00:00HR (M) |  | 2663 |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.43 |  |  | PITS (BBL) | 759
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 36 |  | TYPE |  | TD605X |  | POWER DRIVE PD |  |  | 9.5 | 5.125 |  | 6 5/8 REG |  | 4.25 | 0.94902 |  | ACT. SYS (BBL) | 1955.2
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 7913471 |  | X/O |  |  | 9 | 2.875 |  | 6 5/8 REG |  | 0.6 | 0.13398 |  | RESV. SYS (BBL) | 515
ECD (SG) | 2.12 | 2.12 | AVG. ROP (M/HR) |  | 1.87 |  | IADC CODE |  | - |  | M/MOTOR (S. STAB) |  |  | 12.125 | 7.875 |  | 6 5/8 REG |  | 10.57 | 2.3603 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | 142 | 145 | AVG. WOB (TON) |  | 9 |  | NOZZLES (1/32") |  | 5 x 16/32 |  | FLOAT SUB |  |  | 8.25 | 2.9375 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 65 | 63 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2627 |  | ST.STAB |  |  | 12.25 | 2.875 |  | 6 5/8 REG |  | 2.36 | 0.52698 |  | TOTAL | 2470.2
PV | 41 | 42 | AVG. RPM DOWNHOLE |  | 176 |  | DEPTH OUT (M) |  |  |  | L.SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.6 | 0.13398 |  | DIESEL (LTR)
YIELD POINT | 34 | 30 | FLOWRATE (GPM) |  | 688 |  | METERAGE (M) |  | 36 |  | SPSA |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | RIG TANK | 95759
GEL ST. | 27/36 | 22/29 | PRESSURE (PSI) |  | 2600-2900 |  | RPM SURF. |  | 100 |  | U.SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | CAMP TANK | 16008
WL (ml/30 min) | 6.5 | 5.8 | TORQ. ON-BTM (KLB-FT) |  | 4-6 |  | RPM BTM. |  | 175 |  | ST.STAB |  |  | 12.25 | 2.875 |  | 6 5/8 REG |  | 2.44 | 0.54485 |  | CONSUMED | 11736
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 2-3 |  | WOB (TON) |  | 8-13 |  | NMDC |  |  | 8.25 | 2.8125 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 132 |  | AVG. ROP (M/HR) |  | 1.8711 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | TOTAL | 111767
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 19.24 |  | 8X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 73.88 | 16.4973 |  | WATER (LTR)
PH | 9 | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 196.68 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 196.68 |  | 3X 8'' DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | CAMP STORAGE | 47000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 46.9 |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.029416 |  | CONSUMED | 238000
KCl (mg/l) | 43854 | 44807.5 | JAR | 22.65 | STAB - 1 | 22.65 | JET VELOCITY (M/SEC) |  | 68.75 |  | 9 X 5.5'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | RECEIVED | 230000
CHLORIDES (mg/l) | 24000 | 24500 | 5 1/2" HWDPS | 22.65 | STAB - 2 | 22.65 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 517000
HARDNESS (mg/l) | 490 | 500 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.7 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 22.65 | SPSA | 22.65 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 241.93 |  |  | MPCL | 9
LUBRICANT % | 0.7 | 0.7 | BHA ROT. HRS |  | 22.65 |  | BIT NO. 9 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 23
SOLIDS % | 36.94 | 37.22 | ON BOTTOM HRS |  | 19.24 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY
M.B.T. (lb/bbl) | 15 | 15 | CIRC. HRS |  | 23.13 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 61
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 2503 |  | 1.5 |  | 329.25 |  |  |  |  | MWD |  | TOTAL | 123
DAILY WELL COST (US$) |  | 76666 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2561 |  | 1.94 |  | 322.99 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5823542 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 13 5/8'' X 13 3/8'' (P-110, 88.2/72) |  |  | 2419 | 2589 |  | 2.09 |  | 316.86 |  |  |  |  | MWD |  | LAST CSG SIZE | 13-3/8 / 13-5/8
% OF AFE SPENT |  | 29.26% | MUD CLEANER | 3 X 170 | [6 empty] | 2617 |  | 2.13 |  | 320.66 |  |  |  |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 2614 | 500/550/600 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 2614 | 500/550/600 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 2614 | 500/550/600 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43650 | 43650.0208 | 0.5 | DRL | NPT-UP | S | WHILE RECORDING MWD SURVEY AT 2584M, OBSERVED PROBLEM IN MWD TOOL SIGNALS. RECORDED MWD SURVEY IN 3RD ATTEMPT.
43650.0208 | 43650.125 | 2.5 | DRL | PT-P | RW | CONT'D WASHED/ REAMED DOWN TO BOTTOM AT 2627M, OBSERVED HARD REAMING BELOW 2600M. MEANWHILE RECORDED MWD SURVEY, RECORDED SCR.
43650.125 | 43650.9792 | 20.5 | DRL | PT-P | DM | BROKE IN THE BIT, DRILLED 12 1/4'' HOLE FROM 2627M TO 2663M. WASHED/REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
43650.9792 | 43651 | 0.5 | DRL | NPT-UP | POOH | OBSERVED LEAKAGE IN WASHPIPE, DISCONNECTED TDS, POOH FROM 2663M TO 2613M. OBSERVED TIGHT SPOT @ 2630M, CLEARED WITH RECIPROCATION OF STRING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43651 | 43651.0417 | 1 | DRL | NPT-UP | POOH | CONT'D POOH FROM 2613M TO 2413M (INSIDE CSG). OBSERVED TIGHT SPOT AT 2611M, CLEARED WITH RECIPROCATION OF STRING.
43651.0417 | 43651.0729 | 0.75 | DRL | NPT-UP | RR | REPLACED WASHPIPE, P/TESTED SAME AT 2000 PSI, OK.
43651.0729 | 43651.1146 | 1 | DRL | NPT-UP | RIH | RIH FROM 2413M TO BOTTOM AT 2663M, MEANWHILE RECORDED CHECK SHOT AT 2627M.
43651.1146 | 43651.25 | 3.25 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED 12 1/4'' HOLE FROM 2663M TO 2668M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D REAM DOWN TO BTM AT 2627M, DRILLED 12 1/4'' HOLE FROM 2627M TO 2663M, OBSERVED LEAKAGE IN WASH PIPE, POOH FROM 2663M TO 2613M & IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH INSIDE CSG, REPLACE WASHPIPE, RIH BACK TO BTM AT 2663M, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14