## DDR#65
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 65
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-02-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / MOHSIN / AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 2983 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 64.5833
RIG REP.: |  | JAVED MUGHAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 2988 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 38
2018-02-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5RR1 |  | BHA NO. |  |  | 9 | IN (M) |  | 2777 |  | OUT (M) |  |  | STRING (BBL) | 176.48
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2983 |  | SIZE (IN) |  | 12-1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1178.59
DEPTH, MD (M) | 2959 | 2983 | TVD @ 00:00HR (M) |  | 2983 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12-1/4" |  |  | 6-5/8 REG |  | 0.36 |  |  | PITS (BBL) | 939
MW IN (SG) | 2 | 2 | DAILY PROGRESS (M) |  | 38 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 10.48 |  |  | ACT. SYS (BBL) | 2294.07
MW OUT (SG) | 2 | 2 | INST. ROP (M/HR) |  | 2.3 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.79 |  |  | RESV. SYS (BBL) | 1150
ECD (SG) | 2.029 | 2.029 | AVG. ROP (M/HR) |  | 1.81 |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 1.73 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 3 - 8 |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.6 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 60 | 59 | AVG. RPM SURFACE |  | 0 - 100 |  | DEPTH IN (M) |  | 2777 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.44 |  |  | TOTAL | 4044.07
PV | 38 | 38 | AVG. RPM DOWNHOLE |  | 75 - 175 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.54 |  |  | DIESEL (LTR)
YIELD POINT | 30 | 28 | FLOWRATE (GPM) |  | 650 |  | METERAGE (M) |  | 206 |  | NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 9 |  |  | RIG TANK | 92000
GEL ST. | 11/35 | 9/35 | PRESSURE (PSI) |  | 3400 - 3600 |  | RPM SURF. |  | 0 - 100 |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.38 |  |  | CAMP TANK | 21500
WL (ml/30 min.) | 5.8 | 5.7 | TORQ. ON-BTM (KLB-FT) |  | 4 - 7 |  | RPM BTM. |  | 75 - 175 |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 5.63 |  |  | CONSUMED | 12500
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3 - 4 |  | WOB (TON) |  | 2 - 9 |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.88 |  |  | RECEIVED | 25000
ALK (MUD) | 0.2 | 0.2 | STRING WT. (TON) - ROT |  | 134 |  | AVG. ROP (M/HR) |  | 2.0777 |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.74 |  |  | TOTAL | 113500
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 99.15 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 55.84 |  |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 132 |  | K-REVS IN 24 HRS |  | 197 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 883 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 42.38 | [12 empty] | CONSUMED | 182320
KCl (mg/l) | 40040.7 | 40040.7 | JAR | 78.41 | NMDC | 78.41 | JET VELOCITY (M/SEC) |  | 54 | [12 empty] | RECEIVED | 182320
CHLORIDES | 18000 | 18000 | 5" HWDPS | 78.41 | STAB - 1 | 78.41 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 495000
CALCIUM | 160 | 160 | 8" DCS | 78.41 | STAB - 2 & 3 |  | HSI |  | 1.5 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS |  | SPSA | 78.41 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 178.41 |  |  | MPCL | 4
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 78.41 |  | BIT No. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 16
SOLIDS % | 33.33 | 33.33 | ON BOTTOM HRS |  | 99.15 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY | 4
M.B.T. | 15 | 15 | CIRC. HRS |  | 111.1 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 29
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 20" SURFACE CASING |  |  | 594 | 2871 |  | 1.77 |  | 290.45 |  |  | 0.17 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 50881.5244 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 2901 |  | 1.89 |  | 282.4 |  |  | 0.45 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 5722217.9543 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2928 |  | 1.9 |  | 285.86 |  |  | 0.17 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 31.7% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2958 |  | 1.41 |  | 277.34 |  |  | 0.46 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 668
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-14 | 2018-02-28 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2967 |  | 400/480 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30/40 |  | 2967 |  | 400/480 |  | CHINJI | 342
FIRE DRILL |  |  | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-02-21 | 2018-03-07 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-02-10 | 2018-02-24 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-02-18 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 22 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-02-16 | 2018-03-02 | NEXT BOP TEST DATE |  | 2018-03-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 22 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43154 | 43154.2708 | 6.5 | DRL | PT-P | DM | DRILLED 12.25" HOLE IN ROTARY MODE FROM 2945M TO 2955M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
43154.2708 | 43154.5521 | 6.75 | DRL | PT-P | DM | DRILLED 12.25" HOLE IN SLIDE MODE FROM 2955M TO 2960M.
43154.5521 | 43155 | 10.75 | DRL | PT-P | DM | DRILLED 12.25" HOLE IN ROTARY MODE FROM 2960M TO 2983M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-02-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43155 | 43155.25 | 6 | DRL | PT-P | DM | DRILLED 12.25" HOLE IN SLIDE MODE FROM 2983M TO 2988M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12.25" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12.25" HOLE IN ROTARY & SLIDE MODE FROM 2945M TO 2983M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12.25" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14