## DDR#70
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 70
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH/MASOOD/AHSEN/TALHA/MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3083 / 3083 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 69.9792
RIG REP.: |  | JAVED MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 3097 / 3097 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 55
2019-07-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 10 |  | BHA NO. |  |  | 18 | IN (M) |  | 2790 |  | OUT (M) |  |  | STRING (BBL) | 213
CHECK TIME | 14:30 | 23:59 | MD @ 00:00HR (M) |  | 3083 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1170
DEPTH, MD (M) | 3067 | 3083 | TVD @ 00:00HR (M) |  | 3083 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 752
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 55 |  | TYPE |  | TK66M |  | M/MOTOR (S. STAB) |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.32 | 2.3044 |  | ACT. SYS (BBL) | 2135
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  | 2.5 |  | SERIAL NO. |  | E243361 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 541
ECD (SG) | 2.14 | 2.14 | AVG. ROP (M/HR) |  | 2.74 |  | IADC CODE |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.39 | 0.53368 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | 159 | 160 | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.62 | 0.13845 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 72 | 69 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2790 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | TOTAL | 2676
PV | 43 | 41 | AVG. RPM DOWNHOLE |  | 172 - 184 |  | DEPTH OUT (M) |  |  |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.41 | 0.091552 |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  | 650 - 766 |  | METERAGE (M) |  | 293 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RIG TANK | 65740
GEL ST. | 17/40 | 15/38 | PRESSURE (PSI) |  | 2900 - 3900 |  | RPM SURF. |  | 100 |  | PONY NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 4.65 | 1.0383 |  | CAMP TANK | 25979
WL (ml/30 min) | 5.5 | 5.4 | TORQ. ON-BTM (KLB-FT) |  | 4 - 8 |  | RPM BTM. |  | 172 - 185 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 17454
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 4 |  | WOB (TON) |  | 6 - 12 |  | 11 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 101.55 | 22.676 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 150 |  | AVG. ROP (M/HR) |  | 3.3497 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 91719
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 87.47 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | WATER (LTR)
PH | 9.8 | 10 | SLACK-OFF WT. (TON) |  | 145 |  | K-REVS IN 24 HRS |  | 220.37 |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.17864 |  | RIG STORAGE | 485000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 965.26 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP STORAGE | 75000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 45.5 | [12 empty] | CONSUMED | 232700
KCl (mg/l) | 45760.8 | 45760.8 | JAR | 186.9 | STAB - 1 | 186.9 | JET VELOCITY (M/SEC) |  | 71.17 | [12 empty] | RECEIVED | 257700
CHLORIDES (mg/l) | 24500 | 25000 | 5 1/2" HWDPS | 186.9 | STAB - 2 | 100.47 | TFA (IN²) |  | 1.0354 | [12 empty] | TOTAL | 560000
HARDNESS (mg/l) | 400 | 380 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 3.179 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 186.9 | SPSA | 100.47 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 259.64 |  |  | MPCL | 9
OIL % | 2.4 | 2.4 | BHA ROT. HRS |  | 23.86 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 30 |  |  | MPCL SERV | 26
SOLIDS % | 37.22 | 37.1 | ON BOTTOM HRS |  | 20.07 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 15.5 | 15 | CIRC. HRS |  | 23.56 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 2984 |  | 0.93 |  | 282.95 |  |  | 0.34 |  | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 71209.8719 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3013 |  | 1.13 |  | 279.3 |  |  | 0.22 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6406275.553 | SHAKER-3 | 1 X 140 | 2 X 140 |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3041 |  | 1.31 |  | 274.15 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 32.18% | MUD CLEANER | 3 X 170 | [6 empty] | 3070 |  | 1.22 |  | 274.23 |  |  | 0.09 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3059 | 425/425/425 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3059 | 500/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3059 | 575/575/575 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  | 28 |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43658 | 43658.7083 | 17 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE FROM 3028M TO 3074M & OBSERVED DECREASE IN MUD FLOW OUT. STOPPED DRILLING & RECORDED TOTAL 28 BBL LOSS.
43658.7083 | 43658.7188 | 0.25 | DRL | PT-P | FC | OBSERVED WELL FOR STATIC LOSS, NO LOSS.
43658.7188 | 43658.7917 | 1.75 | DRL | PT-P | CS | REDUCED FLOW RATE FROM 766 GPM TO 650 GPM & CIRCULATED FOR GEOLOGICAL SAMPLE OF 3074M, OBSERVED NO DYNAMIC LOSS.
43658.7917 | 43659 | 5 | DRL | PT-P | DM | RESUMED DRILLING & DRILLED 12 1/4" HOLE FROM 3074M TO 3083M. DURING DRILLING INCREASED FLOW RATE FROM 650 GPM TO 755 GPM IN INCREMENTS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43659 | 43659.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4" HOLE FROM 3083M TO 3097M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 3028M TO 3074M & OBSERVED DECREASE IN MUD FLOW OUT, STOPPED DRILLING & RECORDED 28 BBL LOSS. CIRCULATED @ REDUCED FLOW RATE OF 650 GPM, OBSERVED NO DYNAMIC LOSS. DRILLED 12 1/4" HOLE FROM 3074M TO 3083M. DURING DRILLING INCREASED FLOW RATE FROM 650 GPM TO 755 GPM IN INCREMENTS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE. CONDUCT WIPER TRIP.
REMARKS |  |  | ADDING DIESEL IN MUD SYSTEM @ 0.5 BBL/HR. CONT'D DRILLING WITH 02 MUD PUMPS WHILE BREAKDOWN/REPAIR OF 3RD MUD PUMP.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14