## DDR#72
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 72
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD/IKRAMULLAH/AHSEN/MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3187 / 3187 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 71.9792
RIG REP.: |  | JAVED MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 3204 / 3204 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 61
2019-07-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 10 |  | BHA NO. |  |  | 18 | IN (M) |  | 2790 |  | OUT (M) |  |  | STRING (BBL) | 221
CHECK TIME | 14:30 | 23:59 | MD @ 00:00HR (M) |  | 3187 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1209
DEPTH, MD (M) | 3166 | 3187 | TVD @ 00:00HR (M) |  | 3187 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 853
MW IN (SG) | 2.1 | 2.1 | DAILY PROGRESS (M) |  | 61 |  | TYPE |  | TK66M |  | M/MOTOR (S. STAB) |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.32 | 2.3044 |  | ACT. SYS (BBL) | 2283
MW OUT (SG) | 2.1 | 2.1 | INST. ROP (M/HR) |  | 2.5 |  | SERIAL NO. |  | E243361 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 748
ECD (SG) | 2.14 | 2.14 | AVG. ROP (M/HR) |  | 2.87 |  | IADC CODE |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.39 | 0.53368 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | 162 | 162 | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.62 | 0.13845 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 68 | 66 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2790 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | TOTAL | 3031
PV | 42 | 43 | AVG. RPM DOWNHOLE |  | 175 - 183 |  | DEPTH OUT (M) |  |  |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.41 | 0.091552 |  | DIESEL (LTR)
YIELD POINT | 31 | 29 | FLOWRATE (GPM) |  | 685 - 755 |  | METERAGE (M) |  | 397 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RIG TANK | 82272
GEL ST. | 16/41 | 15/38 | PRESSURE (PSI) |  | 3100 - 3900 |  | RPM SURF. |  | 100 |  | PONY NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 4.65 | 1.0383 |  | CAMP TANK | 24483
WL (ml/30 min) | 5.8 | 5.5 | TORQ. ON-BTM (KLB-FT) |  | 4 - 8 |  | RPM BTM. |  | 172 - 185 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 15998
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 4 |  | WOB (TON) |  | 6 - 12 |  | 11 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 101.55 | 22.676 |  | RECEIVED | 47828
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 152 |  | AVG. ROP (M/HR) |  | 3.2141 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 106755
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 123.52 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | WATER (LTR)
PH | 9.5 | 10 | SLACK-OFF WT. (TON) |  | 150 |  | K-REVS IN 24 HRS |  | 229.79 |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.17864 |  | RIG STORAGE | 490000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1356.11 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 45.3 | [12 empty] | CONSUMED | 185200
KCl (mg/l) | 46714.2 | 45760.8 | JAR | 230.18 | STAB - 1 | 230.18 | JET VELOCITY (M/SEC) |  | 70.89 | [12 empty] | RECEIVED | 225200
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 230.18 | STAB - 2 | 143.75 | TFA (IN²) |  | 1.0354 | [12 empty] | TOTAL | 570000
HARDNESS (mg/l) | 360 | 380 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 3.142 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 230.18 | SPSA | 143.75 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 259.64 |  |  | MPCL | 8
OIL % | 2.4 | 2.5 | BHA ROT. HRS |  | 23.83 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 30 |  |  | MPCL SERV | 24
SOLIDS % | 37.5 | 37.3 | ON BOTTOM HRS |  | 21.29 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 15.5 | 15.5 | CIRC. HRS |  | 23.56 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 30" CONDUCTOR |  |  | 37 | 3070 |  | 1.22 |  | 274.23 |  |  | 0.09 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 71536.8704 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3097 |  | 1.48 |  | 273.31 |  |  | 0.29 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6550118.7117 | SHAKER-3 | 1 X 140 | 2 X 140 |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3127 |  | 1.38 |  | 269.85 |  |  | 0.13 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 32.91% | MUD CLEANER | 3 X 170 | [6 empty] | 3156 |  | 1.46 |  | 265.34 |  |  | 0.14 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 755
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3145 | 600/550/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3145 | 650/625/650 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3145 | 700/720/700 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43660 | 43661 | 24 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE FROM 3126M TO 3187M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR EACH CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43661 | 43661.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4" HOLE FROM 3187M TO 3204M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 3126M TO 3187M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE. POOH TO SURFACE TO CHANGE BHA.
REMARKS |  |  | CONT'D DRILLING WITH 02 MUD PUMPS WHILE BREAKDOWN/REPAIR OF 3RD MUD PUMP.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7