## DDR#75
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 75
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-03-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / AHSEN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3262 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 74.5833
RIG REP.: |  | SARDAR NAEEM / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 3262 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2018-03-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5RR2 |  | BHA NO. |  |  | 11 | IN (M) |  | 3262 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 3262 |  | SIZE (IN) |  | 12-1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1578
DEPTH, MD (M) |  | 3262 | TVD @ 00:00HR (M) |  | 3262 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12-1/4" |  |  | 6-5/8 REG |  | 0.36 | 0.1 |  | PITS (BBL) | 952
MW IN (SG) |  | 2.15 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 10.49 | 3.1 |  | ACT. SYS (BBL) | 2530
MW OUT (SG) |  | 2.15 | INST. ROP (M/HR) |  | 0 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.58 | 0.2 |  | RESV. SYS (BBL) | 979
ECD (SG) |  | 2.17 | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 2.48 | 0.5 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.66 | 0.2 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 3262 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.45 | 1.8 |  | TOTAL | 4109
PV |  | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.48 | 0.1 |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | PONY NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 4.32 | 1.1 |  | RIG TANK | 94000
GEL ST. |  | 8/36 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.74 | 12.4467 |  | CAMP TANK | 16500
WL (ml/30 min.) |  | 5.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 9.16 | 2.0454 |  | CONSUMED | 4500
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.84 | 6.2166 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.94 | 0.2099 |  | TOTAL | 110500
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.09 | 4.1749 |  | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 131990
KCl (mg/l) |  | 44311 | JAR | 0 | NMDC | 0 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 181990
CHLORIDES |  | 20000 | 5" HWDPS | 0 | STAB - 1 | 0 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 395000
CALCIUM |  | 160 | 8" DCS | 0 | STAB - 2 & 3 |  | HSI | [14 empty] | POB
OIL% |  | 3 | 9 1/2" DCS |  | SPSA | 0 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 178.59 |  |  | MPCL | 4
DIESEL % |  | 2 | BHA ROT. HRS |  | 0 |  | BIT No. 5RR1 |  | 1/2/WT/A/X/I/NO/BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 17
SOLIDS % |  | 36.3 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. |  | 15 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 140 | 2 X 80 |  | 20" SURFACE CASING |  |  | 594 | 3129 |  | 0.8 |  | 293.48 |  |  | 0.14 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 42600 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3158 |  | 0.74 |  | 292.96 |  |  | 0.06 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6279450.9596 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3186 |  | 0.53 |  | 296.27 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 34.79% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3219 |  | 0.45 |  | 272.34 |  |  | 0.2 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 168
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-28 | 2018-03-14 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3193 |  | 450/590 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3193 |  | 450/590 |  | CHINJI | 342
FIRE DRILL | 2018-02-09 | 2018-03-11 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3193 |  | 450/590 |  | KAMLIAL | 1255
PIT DRILL | 2018-02-21 | 2018-03-07 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-03 | 2018-03-17 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-03-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | - | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-02-16 | 2018-03-18 | NEXT BOP TEST DATE |  | 2018-03-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | - | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43164 | 43164.0729 | 1.75 | DRL | PT-P | POOH | POOH 12.25" BIT FROM 2749M TO 2336M (INSIDE 13-3/8" CSG SHOE).
43164.0729 | 43164.0833 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC.
43164.0833 | 43164.3021 | 5.25 | DRL | PT-P | POOH | POOH 12.25" BIT FROM 2336M TO 179M (BHA TOP).
43164.3021 | 43164.3125 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC.
43164.3125 | 43164.375 | 1.5 | DRL | PT-P | BHA | POOH TO SURFACE WHILE L/DOWN COMPLETE BHA FOR INSPECTION.
43164.375 | 43164.4792 | 2.5 | DRL | PT-P | BHA | BROKE OUT BIT AND L/DOWN SLB PERFORMANCE TOOLS.
43164.4792 | 43164.6458 | 4 | DRL | NPT-UP | RR | WORKED ON TDS HYD PUMP. REPLACED TDS MANUAL IBOP & SAVER SUB.
43164.6458 | 43164.8333 | 4.5 | DRL | PT-P | BOPT | PJSM. M/UP & RIH TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP & IBOP @ 300 PSI/5000 PSI FOR 5/10 MIN - OK. P/TESTED LOWER PIPE RAM BOP (5" RAMS), UPPER PIPE RAM BOP (VARIABLE - 4.5" TO 7"), BLIND RAM BOP, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE & KILL LINE CHECK VALVE @ 300/6500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE/STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG & SET WEAR BUSHING.
43164.8333 | 43164.9375 | 2.5 | DRL | NPT-UP | RR | WORKED ON TDS. REPLACED TDS LUBRICATION PUMP.
43164.9375 | 43165 | 1.5 | DRL | PT-P | BHA | P/UP & M/UP 12.25" TRI-CONE BIT, 9-5/8" MUD MOTOR, ST. STAB & SPSA.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43165 | 43165.0625 | 1.5 | DRL | PT-P | BHA | SET MUD MOTOR BEND TO 1.5°, INSTALLED MWD TOOL & ADJUSTED TOOLFACE OFFSET. SHALLOW FUNCTION TESTED MUD MOTOR & MWD @ 650 GPM & 1150 PSI - OK. BROKE OUT 12.25" TRI-CONE BIT.
43165.0625 | 43165.2083 | 3.5 | DRL | PT-P | BHA | P/UP, M/UP & RIH 12.25" PDC BIT (RR2) WITH NEW INSPECTED BHA & SLB PERFORMANCE TOOLS TO 178M. WHILE RIH P/UP BHA SINGLE BY SINGLE FROM CATWALK.
43165.2083 | 43165.25 | 1 | DRL | PT-P | RIH | RIH FROM 178M TO 638M. WHILE RIH, FILLED UP STRING WITH MUD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE & SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 12.25" PDC BIT
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE & L/DOWN COMPLETE BHA FOR INSPECTION. WORKED ON TDS. PRESSURE TESTED BOP STACK. P/UP & M/UP SLB DIRECTIONAL TOOLS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM & DRILL AHEAD.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14