## DDR#75
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 75
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3238 / 3238 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 74.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 3238 / 3238 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2 METER
2019-07-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 10 |  | BHA NO. |  |  | 18 | IN (M) |  | 2790 |  | OUT (M) |  |  | STRING (BBL) | 215.5
CHECK TIME | 7:00 | 23:59 | MD @ 00:00HR (M) |  | 3238 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1238.1
DEPTH, MD (M) | 3236 | 3238 | TVD @ 00:00HR (M) |  | 3238 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 835
MW IN (SG) | 2.21 | 2.21 | DAILY PROGRESS (M) |  | 2 |  | TYPE |  | TK66M |  | M/MOTOR (S. STAB) |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.32 | 2.3044 |  | ACT. SYS (BBL) | 2288.6
MW OUT (SG) | 2.20+ | 2.21 | INST. ROP (M/HR) |  | 2.3 |  | SERIAL NO. |  | E243361 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 2150
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.27 |  | IADC CODE |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.39 | 0.53368 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.62 | 0.13845 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 75 | 57 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2790 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | TOTAL | 4438.6
PV | 49 | 48 | AVG. RPM DOWNHOLE |  | 171 |  | DEPTH OUT (M) |  |  |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.41 | 0.091552 |  | DIESEL (LTR)
YIELD POINT | 33 | 26 | FLOWRATE (GPM) |  | 650 |  | METERAGE (M) |  | 448 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RIG TANK | 95439
GEL ST. | 24/46 | 17/38 | PRESSURE (PSI) |  | 3150 |  | RPM SURF. |  | 100 |  | PONY NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 4.65 | 1.0383 |  | CAMP TANK | 22252
WL (ml/30 min) | 8 | 5.8 | TORQ. ON-BTM (KLB-FT) |  | 4-10 |  | RPM BTM. |  | 171 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 11161
CT ( in/32) | 3 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 0 - 1 |  | WOB (TON) |  | 8 |  | 11 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 101.55 | 22.676 |  | RECEIVED | 47870
ALK (MUD) | 0.2 | 0.4 | STRING WT. (TON) - ROT |  | 148 |  | AVG. ROP (M/HR) |  | 2.3 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 117691
ALK (FILT.) | 0.1/1.2 | 0.3/1.9 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 138.61 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | WATER (LTR)
PH | 8.5 | 9.6 | SLACK-OFF WT. (TON) |  | 146 |  | K-REVS IN 24 HRS |  | 9.08 |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.17864 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1521.28 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP STORAGE | 76000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 44 | [12 empty] | CONSUMED | 104000
KCl (mg/l) | 38134 | 45761 | JAR | 252.94 | STAB - 1 | 252.94 | JET VELOCITY (M/SEC) |  | 61.12 | [12 empty] | RECEIVED | 84000
CHLORIDES (mg/l) | 22000 | 24500 | 5 1/2" HWDPS | 252.94 | STAB - 2 | 166.51 | TFA (IN²) |  | 1.0354 | [12 empty] | TOTAL | 476000
HARDNESS (mg/l) | 490 | 510 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.1 | [12 empty] | POB
PENETREX % | 1.5 | 2 | 8" DCS | 252.94 | SPSA | 166.51 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 259.64 |  |  | MPCL | 7
OIL % | 1.5 | 2 | BHA ROT. HRS |  | 0.88 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 30 |  |  | MPCL SERV | 25
SOLIDS % | 40.84 | 41.07 | ON BOTTOM HRS |  | 0.88 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 15 | 14.5 | CIRC. HRS |  | 19.9 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 X 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3127 |  | 1.38 |  | 269.85 |  |  | 0.13 |  | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 73489 | SHAKER-2 | 3 X 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3156 |  | 1.46 |  | 265.34 |  |  | 0.14 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6768843.7394 | SHAKER-3 | 3 X 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3185 |  | 1.56 |  | 261.18 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 34% | MUD CLEANER | 3 X 170 | [6 empty] | 3213 |  | 1.58 |  | 268.85 |  |  | 0.23 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 343
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3238 | 270/220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3238 | 320/310 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3238 | 420/400 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43663 | 43663.2396 | 5.75 | DRL | NPT-UP | WC | CONT'D KILLING OPERATION. TOTAL STROKES PUMPED = 18300, MWIN = 2.21 SG & MWOUT = 2.20+ SG. CASING PRESSURE REDUCED TO ZERO AFTER 12600 STROKES. OPENED ANNULAR BOP & CHECKED STRING FREE.
43663.2396 | 43663.25 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43663.25 | 43663.5417 | 7 | DRL | NPT-UP | CIR | CIRCULATED TO CONDITION & HOMOGENIZE MUD.
43663.5417 | 43663.5625 | 0.5 | DRL | NPT-UP | RW | HARD REAMED DOWN FROM 3233M TO 3236M.
43663.5625 | 43663.6146 | 1.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 3236M TO 3238M. OBSERVED HIGH ERRATIC TORQUE WHILE DRILLING @ 3238M.
43663.6146 | 43663.6354 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL FLOWING @ 5 BPH.
43663.6354 | 43663.7396 | 2.5 | DRL | NPT-UP | WC | SHUT IN & OBSERVED WELL. RECORDED SIDP = 180 PSI & SICP = 200 PSI. ROTATED STRING INTERMITTENTLY.
43663.7396 | 43663.7812 | 1 | DRL | NPT-UP | WC | CIRCULATED STRING VOLUME BY 2.21 SG MUD THRU CHOKE @ 50 SPM TO RECONFIRM PRESSURES.
43663.7812 | 43663.8021 | 0.5 | DRL | NPT-UP | WC | SHUT IN & OBSERVED WELL. RECORDED SIDP = 190 PSI & SICP = 210 PSI.
43663.8021 | 43664 | 4.75 | DRL | NPT-UP | WC | CIRCULATED WITH 2.21 SG MUD @ 50 SPM (DRILLER'S METHOD 1ST CIRCULATION). ROTATED STRING INTERMITTENTLY.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43664 | 43664.1042 | 2.5 | DRL | NPT-UP | WC | CONT'D CIRCULATING WITH 2.21 SG MUD @ 50 SPM (DRILLER'S METHOD 1ST CIRCULATION). MWIN = 2.21 SG & MWOUT = 2.20+ SG. SHUT IN WELL. ROTATED STRING INTERMITTENTLY.
43664.1042 | 43664.1667 | 1.5 | DRL | NPT-UP | WC | RECORDED CASING PRESSURE AT 100 PSI. BLED OFF CASING PRESSURE.
43664.1667 | 43664.25 | 2 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.22 SG MUD AT 650 GPM TO HOMOGENIZE MUD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DIRECT CIRCULATION IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | KILLED WELL WITH 2.21 SG MUD. FOUND WELL STATIC. CIRCULATED TO HOMOGENIZE AND CONDITION MUD. DRILLED FROM 3236M TO 3238M. FLOW CHECKED. OBSERVED WELL FLOWING. SHUT IN WELL AND RECORDED SIDP & SICP. CIRCULATED THROUGH CHOKE (DRILLER'S METHOD 1ST CIRCULATION).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE TO HOMOGENIZE & CONDITION MUD TO STABLE WELL. FLOW CHECK & WIPER TRIP TO CHECK HOLE CONDITION.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7