## DDR#76
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 76
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3238 / 3238 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 75.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 3238 / 3238 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-07-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 10 |  | BHA NO. |  |  | 18 | IN (M) |  | 2790 |  | OUT (M) |  |  | STRING (BBL) | 215.5
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1238.1
DEPTH, MD (M) | 3238 | 3238 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 845
MW IN (SG) | 2.23 | 2.23 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TK66M |  | M/MOTOR (S. STAB) |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.32 | 2.3044 |  | ACT. SYS (BBL) | 2298.6
MW OUT (SG) | 2.23 | 2.23 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E243361 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 2134
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.39 | 0.53368 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.62 | 0.13845 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 57 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2790 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | TOTAL | 4432.6
PV | 48 | 49 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.41 | 0.091552 |  | DIESEL (LTR)
YIELD POINT | 26 | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RIG TANK | 131893
GEL ST. | 18/40 | 18/41 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | PONY NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 4.65 | 1.0383 |  | CAMP TANK | 21548
WL (ml/30 min) | 5.7 | 5.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 12035
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 11 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 101.55 | 22.676 |  | RECEIVED | 47785
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 148 |  | AVG. ROP (M/HR) |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 153441
ALK (FILT.) | 0.4/2.1 | 0.4/2.1 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  |  |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | WATER (LTR)
PH | 9.6 | 9.8 | SLACK-OFF WT. (TON) |  | 146 |  | K-REVS IN 24 HRS |  |  |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.17864 |  | RIG STORAGE | 394000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 158700
KCl (mg/l) | 45761 | 45761 | JAR | 252.94 | STAB - 1 | 252.94 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 161700
CHLORIDES (mg/l) | 24500 | 24500 | 5 1/2" HWDPS | 252.94 | STAB - 2 | 166.51 | TFA (IN²) | [14 empty] | TOTAL | 479000
HARDNESS (mg/l) | 480 | 490 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 252.94 | SPSA | 166.51 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 259.64 |  |  | MPCL | 7
OIL % | 2.3 | 2.5 | BHA ROT. HRS |  |  |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 30 |  |  | MPCL SERV | 26
SOLIDS % | 41.48 | 41.38 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 14.5 | 14.5 | CIRC. HRS |  | 17.86 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 X 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3127 |  | 1.38 |  | 269.85 |  |  | 0.13 |  | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 57564 | SHAKER-2 | 3 X 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3156 |  | 1.46 |  | 265.34 |  |  | 0.14 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6826407.7394 | SHAKER-3 | 3 X 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3185 |  | 1.56 |  | 261.18 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 34.29% | MUD CLEANER | 3 X 170 | [6 empty] | 3213 |  | 1.58 |  | 268.85 |  |  | 0.23 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.23SG) | [5 empty] | MAASP (PSI) | 309
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3233 | 210/200/180 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3233 | 310/270/240 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-06-13 | 2019-07-13 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3233 | 400/380/386 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-06-13 | 2019-07-13 | NEXT BOP TEST DATE |  | 2019-07-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43664 | 43664.1042 | 2.5 | DRL | NPT-UP | WC | CONT'D CIRCULATING WITH 2.21 SG MUD @ 50 SPM (DRILLER'S METHOD 1ST CIRCULATION). MWIN = 2.21 SG & MWOUT = 2.20+ SG. SHUT IN WELL. ROTATED STRING INTERMITTENTLY.
43664.1042 | 43664.1667 | 1.5 | DRL | NPT-UP | WC | RECORDED CASING PRESSURE AT 100 PSI. BLED OFF CASING PRESSURE.
43664.1667 | 43664.25 | 2 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.22 SG MUD AT 650 GPM TO HOMOGENIZE & CONDITION MUD.
43664.25 | 43664.2708 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL TRICKLING.
43664.2708 | 43664.3646 | 2.25 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.23 SG MUD AT 650 GPM TO HOMOGENIZE & CONDITION MUD.
43664.3646 | 43664.3854 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL STATIC.
43664.3854 | 43664.5625 | 4.25 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.23 SG MUD AT 650 GPM TO HOMOGENIZE & CONDITION MUD.
43664.5625 | 43664.6042 | 1 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL TRICKLING.
43664.6042 | 43664.6979 | 2.25 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.23 SG MUD AT 650 GPM TO HOMOGENIZE & CONDITION MUD.
43664.6979 | 43664.7083 | 0.25 | DRL | NPT-UP | FC | B/O STAND TO CHECK FOR U-TUBING & FLOW CHECKED. OBSERVED WELL TRICKLING.
43664.7083 | 43664.875 | 4 | DRL | NPT-UP | CIR | DIRECT CIRCULATED WITH 2.23 SG MUD TREATED WITH DEFOAMER AT 650 GPM.
43664.875 | 43664.8958 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL TRICKLING.
43664.8958 | 43665 | 2.5 | DRL | NPT-UP | WT | POOH FOR WIPER TRIP. OBSERVED TIGHT SPOT @3158M. ATTEMPTED TO CLEAR BY RECIPROCATION. PUMPED OUT FROM 3158M TO 3147M. WHILE POOH, OBSERVED SWABBING AND TIGHT HOLE, PUMPED OUT FROM 3147M TO 3002M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43665 | 43665.2292 | 5.5 | DRL | NPT-UP | WT | CONT'D PUMPING OUT FROM 3002M TO 2602M (BACK REAMED FROM 2834M TO 2818M, 2716M TO 2707M). POOH ON ELEVATORS FROM 2602M TO 2402M (INSIDE CSG SHOE).
43665.2292 | 43665.25 | 0.5 | DRL | NPT-UP | WT | RIH FROM 2402M TO 2492M. OBSERVED COMPRESSION, REAMED DOWN TO 2498M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D CIRCULATING THROUGH CHOKE (DRILLER'S METHOD 1ST CIRCULATION). SHUT IN AND OBSERVED WELL. OBSERVED CSG PRESSURE BUILD UPTO 100 PSI. DIRECT CIRCULATED TO HOMOGENIZE AND CONDITION MUD. POOH FOR WIPER TRIP UPTO 3002M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM. CIRCULATE BOTTOMS UP AND ANALYZE MUD SAMPLES. STABLIZE THE WELL ACCORDINGLY.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7