## DDR#77
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 77
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3251 / 3251 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 76.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 3251 / 3251 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 13 METER
2019-07-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 10 |  | BHA NO. |  |  | 18 | IN (M) |  | 2790 |  | OUT (M) | 3251 |  | STRING (BBL) | 114.2
CHECK TIME | 6:30 | 23:59 | MD @ 00:00HR (M) |  | 3251 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1347.3
DEPTH, MD (M) | 3238 | 3251 | TVD @ 00:00HR (M) |  | 3251 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 |  |  | PITS (BBL) | 806
MW IN (SG) | 2.23 | 2.24 | DAILY PROGRESS (M) |  | 13 |  | TYPE |  | TK66M |  | M/MOTOR (S. STAB) |  |  | 9.625 | 7.875 |  | 6 5/8 REG |  | 10.32 | 2.3044 |  | ACT. SYS (BBL) | 2267.5
MW OUT (SG) | 2.23 | 2.24 | INST. ROP (M/HR) |  | 1.7 |  | SERIAL NO. |  | E243361 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | RESV. SYS (BBL) | 2198
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.6539 |  | IADC CODE |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.39 | 0.53368 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.62 | 0.13845 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 62 | 69 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 2790 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | TOTAL | 4465.5
PV | 48 | 50 | AVG. RPM DOWNHOLE |  | 176 |  | DEPTH OUT (M) |  | 3251 |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.41 | 0.091552 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  | 690 |  | METERAGE (M) |  | 461 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RIG TANK | 123378
GEL ST. | 15/37 | 18/42 | PRESSURE (PSI) |  | 3600-3800 |  | RPM SURF. |  | 100 |  | PONY NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 4.65 | 1.0383 |  | CAMP TANK | 20841
WL (ml/30 min) | 5.7 | 5.8 | TORQ. ON-BTM (KLB-FT) |  | 4-8 |  | RPM BTM. |  | 176 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 9222
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  | - |  | WOB (TON) |  | 8 |  | 11 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 101.55 | 22.676 |  | RECEIVED
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  | 148 |  | AVG. ROP (M/HR) |  | 3.1474 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 144219
ALK (FILT.) | 0.3/2.1 | 0.4/2.1 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 146.47 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.92 | 6.2345 |  | WATER (LTR)
PH | 9.6 | 9.8 | SLACK-OFF WT. (TON) |  | 146 |  | K-REVS IN 24 HRS |  | 83.47 |  | X/O |  |  | 7.875 | 2.875 |  | 6 5/8 REG |  | 0.8 | 0.17864 |  | RIG STORAGE | 390000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1604.5 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP STORAGE | 78000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 46.9 | [12 empty] | CONSUMED | 105500
KCl (mg/l) | 43854 | 45761 | JAR | 260.8 | STAB - 1 | 260.8 | JET VELOCITY (M/SEC) |  | 65.19 | [12 empty] | RECEIVED | 94500
CHLORIDES (mg/l) | 24500 | 25000 | 5 1/2" HWDPS | 260.8 | STAB - 2 | 174.37 | TFA (IN²) |  | 1.0354 | [12 empty] | TOTAL | 468000
HARDNESS (mg/l) | 460 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.6 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 260.8 | SPSA | 174.37 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 259.64 |  |  | MPCL | 7
OIL % | 2.3 | 2.2 | BHA ROT. HRS |  | 7.86 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 30 |  |  | MPCL SERV | 25
SOLIDS % | 41.48 | 41.97 | ON BOTTOM HRS |  | 7.86 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 15.5 | 15.5 | CIRC. HRS |  | 14.28 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3127 |  | 1.38 |  | 269.85 |  |  | 0.13 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 61426.1 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3156 |  | 1.46 |  | 265.34 |  |  | 0.14 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6887833.8394 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3185 |  | 1.56 |  | 261.18 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 34.6% | MUD CLEANER | 3 x 170 | [6 empty] | 3213 |  | 1.58 |  | 268.85 |  |  | 0.23 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.23SG) | [5 empty] | MAASP (PSI) | 275
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3242 | 280/300/300 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3242 | 390/390/390 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3242 | 490/490/490 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-07-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43665 | 43665.2292 | 5.5 | DRL | NPT-UP | WT | CONT'D PUMPING OUT FROM 3002M TO 2602M (BACK REAMED FROM 2834M TO 2818M, 2716M TO 2707M). POOH ON ELEVATORS FROM 2602M TO 2402M (INSIDE CSG SHOE).
43665.2292 | 43665.4062 | 4.25 | DRL | NPT-UP | WT | RIH FROM 2402M TO 3103M. (WASHED / REAMED DOWN FROM 2492M TO 2498M, 2831M TO 2860M, 2947M TO 3003M & 3090M TO 3103M).
43665.4062 | 43665.4271 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED. OBSERVED WELL TRICKLING.
43665.4271 | 43665.4583 | 0.75 | DRL | NPT-UP | WT | RIH FROM 3103M TO 3234M.
43665.4583 | 43665.5625 | 2.5 | DRL | NPT-UP | CIR | CIRCULATED AT 650 GPM. REDUCED CIRCULATION RATE TO 400 GPM, 1000 STROKES BEFORE BOTTOMS UP. OBSERVED MIN MWOUT = 1.88 SG.
43665.5625 | 43665.8854 | 7.75 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE FROM 3238M TO 3251M. WHILE DRILLING, INCREASED MW TO 2.24 SG.
43665.8854 | 43665.9167 | 0.75 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED WELL STATIC.
43665.9167 | 43665.9375 | 0.5 | DRL | PT-P | SP | SPOTTED 40 BBL HI VIS, HI WEIGHTED PILL OF 2.30 SG AT BOTTOM.
43665.9375 | 43666 | 1.5 | DRL | PT-P | POOH | POOH. WHILE POOH, OBSERVED TIGHT SPOTS IN INTERVAL 3238M-3158M. CLEARED THE SAME WITH RECIPROCATION. OBSERVED SWABBING AND TIGHT HOLE. PUMPED OUT FROM 3158M TO 3116M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43666 | 43666.1771 | 4.25 | DRL | PT-P | POOH | CONT'D PUMPING OUT FROM 3116M TO 3030M (BACK REAMED FROM 3081-3080M). POOH FROM 3030M TO 2398M (INSIDE CSG SHOE) ON ELEVATORS.
43666.1771 | 43666.1875 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43666.1875 | 43666.25 | 1.5 | DRL | PT-P | POOH | CONT'D POOH FROM 2398M TO 2000M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONDUCTED WIPER TRIP TO CSG SHOE. CIRCULATED & HOMOGENIZED MUD. DRILLED 12 1/4" HOLE FROM 3238M TO 3251M & INCREASED MW TO 2.24 SG. FLOW CHECKED, WELL STATIC. POOH TO 3116M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. L/D BHA FOR INPSECTION. P/T BOP STACK. RIH WITH 12 1/4" PDC BIT & DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7