## DDR#78
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 78
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3251 / 3251 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 77.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 3251 / 3251 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-07-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1575.7
DEPTH, MD (M) | 3251 | 3251 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 598
MW IN (SG) | 2.24 | 2.24 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 2173.7
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 2185
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG) | 0
µ FUNNEL (SEC) | 72 | 72 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 4358.7
PV | 51 | 52 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 28 | 28 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 116499
GEL ST. | 18/44 | 18/44 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 20131
WL (ml/30 min) | 5.8 | 5.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 7589
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 136630
ALK (FILT.) | 0.4/2.0 | 0.4/2.0 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.8 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 320000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 75000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 233300
KCl (mg/l) | 45761 | 45761 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 160300
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 395000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 7
OIL % | 2.2 | 2.2 | BHA ROT. HRS |  |  |  | BIT NO. 10 |  | 1-1-WT-A-X-I-NO-BHA |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 31
SOLIDS % | 41.97 | 41.97 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 15 | 15 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3127 |  | 1.38 |  | 269.85 |  |  | 0.13 |  | MWD |  | TOTAL | 123
DAILY WELL COST (US$) |  | 41656.375 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3156 |  | 1.46 |  | 265.34 |  |  | 0.14 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6926237.2144 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3185 |  | 1.56 |  | 261.18 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 34.79% | MUD CLEANER | 3 x 170 | [6 empty] | 3213 |  | 1.58 |  | 268.85 |  |  | 0.23 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.23SG) | [5 empty] | MAASP (PSI) | 275
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3242 | 280/300/300 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3242 | 390/390/390 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3242 | 490/490/490 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-07-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43666 | 43666.1771 | 4.25 | DRL | PT-P | POOH | CONT'D PUMPING OUT FROM 3116M TO 3030M (BACK REAMED FROM 3081-3080M). POOH FROM 3030M TO 2398M (INSIDE CSG SHOE) ON ELEVATORS.
43666.1771 | 43666.1875 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43666.1875 | 43666.25 | 1.5 | DRL | PT-P | POOH | POOH FROM 2398M TO 1993M.
43666.25 | 43666.2708 | 0.5 | DRL | NPT-UP | RR | WORKED ON TRIP TANK PUMP.
43666.2708 | 43666.4375 | 4 | DRL | PT-P | POOH | POOH FROM 1993M TO 260M (TOP OF BHA).
43666.4375 | 43666.4479 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED WELL STATIC.
43666.4479 | 43666.6979 | 6 | DRL | PT-P | BHA | POOH BHA FROM 260M TO SURFACE. L/D BHA SINGLE BY SINGLE FOR INSPECTION. FOUND STABS PARTIALLY BALLED UP.
43666.6979 | 43666.7083 | 0.25 | DRL | NPT-UP | RR | DISMANTLED & N/D BELL NIPPLE.
43666.7083 | 43666.7396 | 0.75 | DRL | PT-P | WB | HELD PJSM, P/UP AND M/UP COMBINATION TOOL ASSY, RETRIEVED WEAR BUSHING. (MEANWHILE REPAIRED BELL NIPPLE IN WELDER SHOP)
43666.7396 | 43666.9167 | 4.25 | DRL | PT-P / NPT-UP | BOPT | RIH 3 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE VALVES @ 400/4000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") & LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD IBOP, MANUAL IBOP AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 400/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG AND RACKED BACK 3 STANDS. (WHILE BOP P/T, FOUND KILL LINE CO-FLEXIP HOSE PLUGGED, REMOVED THE HOSE AND CLEARED THE SAME)
43666.9167 | 43666.9375 | 0.5 | DRL | NPT-UP | WB | M/U COMBINATION TOOL ASSY & INSTALLED WEAR BUSHING. L/D COMBINATION TOOL ASSY.
43666.9375 | 43667 | 1.5 | DRL | NPT-UP | RR | INSTALLED BELL NIPPLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43667 | 43667.0312 | 0.75 | DRL | NPT-UP | RR | P/U & RIH 5 1/2" DP STD. CLOSED ANNULAR AND FLUSHED KILL LINE THROUGH CHOKE MANIFOLD. OPENED ANNULAR AND P/T KILL LINE CONNECTION AT 1000 PSI, OK. R/B DP STD. FUNCTION TESTED BLIND RAM.
43667.0312 | 43667.1667 | 3.25 | DRL | NPT-UP | RR | FILLED BELL NIPPLE AND OBSERVED LEAKAGE FROM RISER NUT. PERFORMED REMEDIAL WORK ON BELL NIPPLE LEAKAGE BUT NO SUCCESS. WELDED THE SAME.
43667.1667 | 43667.25 | 2 | DRL | PT-P | BHA | P/U & M/U POWER DRIVE WITH RR 12 1/4" PDC BIT + STRING STAB + SPSA. INSTALLATION OF MWD TOOLS INSIDE SPSA IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | INSTALLATION OF MWD TOOLS INSIDE SPSA IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. L/D BHA FOR INPSECTION. P/T BOP STACK. WORKED ON BELL NIPPLE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 12 1/4" PDC BIT WITH POWER DRIVE & MWD DOWN TO BOTTOM. DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7