## DDR # 08
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 8
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / MEHDI / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 595 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 7.5833
RIG REP.: |  | JAVED IQBAL / KHALID |  |  | MD/TVD @ 06:00HRS: |  | 595 (SECTION TD) | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2017-12-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 2RR | 2 | BHA No. |  |  | 2 | IN (M) |  | 595 |  | OUT (M) | 595 |  | STRING (BBL) | 665
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 26 | 26 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 544
DEPTH, MD (M) | 595 | 595 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER | BAKER | 26"PDC BIT |  |  | 26 |  |  | 7 5/8 REG |  | 0.57 |  |  | PITS (BBL) | 852
MW IN (SG) | 1.12 | 1.12 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD509S | TD509S | BITSUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 1.08 | 0.5 |  | ACT. SYS (BBL) | 2061
MW OUT (SG) | 1.12 | 1.12 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5278922 | 5278922 | NMDC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.43 | 2 |  | RESV. SYS (BBL) | 1007
ECD (SG) | - | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S423 | S423 | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.34 | 8.18 |  | KILL MUD (BBL) | -
FL TEMP. °F | - | - | AVG. WOB (TON) |  |  |  | NOZZLES |  | 9X14 | 9X14 | 1X11" DCS |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.2 | 1 |  | KILL MW (SG) | -
µ FUNNEL (SEC) | 62 | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 47 | 47 | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.23 | 4.11 |  | TOTAL | 3068
PV | 14 | 12 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 595 |  | 1X11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.12 | 1 |  | DIESEL (LTR)
YIELD POINT | 20 | 20 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 548 |  | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 1.99 | 17.95 |  | RIG TANK | 113900
GEL ST. | 13/27 | 8/16 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 6X9.5" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 55.58 | 0.3 |  | CAMP TANK | 19400
WL (ml/30 min.) | 10 | 10 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X-OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 1.15 |  | CONSUMED | 6700
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | D.JAR |  |  | 8 | 3.125 |  | 6 5/8 REG |  | 5.15 | 6.22 |  | RECEIVED | 0
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 3X8" DCs |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 27.85 | 0.17 |  | TOTAL | 133300
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X-OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 10.3 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 15 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.41 |  |  | RIG STORAGE | 200000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 281332
NaCl (mg/l) | 495 | 660 | JAR | 99.53 | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 236332
CHLORIDES | 300 | 400 | 5" HWDPS | 86.23 | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 255000
CALCIUM | 150 | 140 | 8" DCS | 99.5 | STAB - 2 |  | HSI | [14 empty] | POB
OIL% | 2 | 2 | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 266.62 |  |  | MPCL | 4
SAND % | - | - | BHA ROT. HRS |  | 131.34 |  | BIT No. 2 |  | 1/2/WT/A/X/I/NO/TD |  | BHA WT. IN MUD (TON) | [7 empty] | 45 |  |  | MPCL SERV | 29
SOLIDS % | 4.98 | 4.99 | ON BOTTOM HRS |  | 110.16 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 30 |  |  | SECURITY | -
M.B.T. | 20 | 20 | CIRC. HRS |  | 133.63 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  | 594 | 496 |  | 1.01 |  | 132.42 |  |  |  |  | EMS |  | TOTAL | 124
DAILY WELL COST (US$) |  | 214387.8656 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 525 |  | 1.26 |  | 139.45 |  |  |  |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 1991128.6693 | SHAKER-3 | 1 X 80 | 2 X 50 |  | 9 5/8" PRODUCTION CSG |  |  |  | 554 |  | 1.44 |  | 142.41 |  |  |  |  | EMS |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 11.03% | MUD CLEANER | 3 X 200 |  |  | 7" LINER |  |  |  | 583 |  | 1.06 |  | 135.73 |  |  |  |  | EMS |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI | 342
FIRE DRILL | 26-12-2017 |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43097 | 43097.0312 | 0.75 | DRL | PT-P | BHA | CONT'D RIH FROM 125M TO 266M. FOUND HOLE IN GOOD CONDITION.
43097.0312 | 43097.0833 | 1.25 | DRL | PT-P | RIH | CONT'D RIH FROM 266M TO 595M. PRECAUTIONARY WASH DOWN LAST STAND. FOUND HOLE IN GOOD CONDITION.
43097.0833 | 43097.1458 | 1.5 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE AND CONDITION & HOMOGENEOUS MUD.
43097.1458 | 43097.1979 | 1.25 | DRL | PT-P | POOH | POOH FROM 595M TO 266M (TOP OF BHA). FOUND HOLE IN GOOD CONDITION.
43097.1979 | 43097.4167 | 5.25 | DRL | PT-P | BHA | POOH FROM 266M TO SURFACE. FOUND HOLE IN GOOD CONDITION. CLEANED BIT AND STABS. L/D 26" BIT + 3 X 26" STABS + 2 X 11" DC JNTS.
43097.4167 | 43097.4583 | 1 | DRL | PT-P | RU | CHANGED TDS LINKS. R/U W/F CSG FILLING TOOL & TRS EQUIPMENT. HOLD PJSM.
43097.4583 | 43097.9792 | 12.5 | DRL | PT-P | RC | P/U & M/U 20" SHOE TRACK (FLOAT SHOE + 2" CSG JNT + 20" FC + 20" CSG JNT) AND RIH TO 24 M. CHECKED FLOATS - OK. CONT'D RIH 20" CASING (133 PPF - BTC - K-55) FROM 24M TO 594M (CASING SHOE DEPTH). MADE UP CIRCULATING HEAD AND PRECAUTIONARY WASHED DOWN LAST CASING JOINT.
43097.9792 | 43098 | 0.5 | DRL | PT-P | CIR | CIRCULATED THROUGH CIRCULATING HEAD. MEANWHILE RIG DOWN W/F CSG FILLING TOOL & TRS EQUIPMENT.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43098 | 43098.125 | 3 | DRL | PT-P | RIH | P/U & M/U STAB IN STINGER ASSEMBLY AND RIH DP FROM SURFACE TO 570M.
43098.125 | 43098.1562 | 0.75 | DRL | PT-P | RIH | M/U CIRCULATING HEAD WITH 5" DP AND STAB IN STINGER IN FLOAT COLLAR WITH CIRCULATION @ 581M WITH 5 TON COMPRESSION. CONFIRM STAB IN BY RETURNS AT SHAKERS. OBSV'D NO FLOW B/W 5" X 20" ANNULUS.
43098.1562 | 43098.25 | 2.25 | DRL | PT-P | CIR | PREPARING MIX FLUID FOR CEMENT JOB MEANWHILE CIRCULATING TO CONDITION & REDUCE MUD RHEOLOGY.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHINJI (100% CLAYSTONE)
OPERATIONS AT 06:00 HRS |  |  | PREPARING MIX FLUID FOR CEMENT JOB MEANWHILE CIRCULATING TO CONDITION & REDUCE MUD RHEOLOGY.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | COMPLETED CONDITION TRIP AND RIH 20" CASING TO 594M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM CEMENTING JOB & WOC.
REMARKS