## DDR#81
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 81
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-03-12
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / AHSEN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3502 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 80.5833
RIG REP.: |  | SARDAR NAEEM / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 3524 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 62
2018-03-11 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5RR2 |  | BHA NO. |  |  | 11 | IN (M) |  | 3262 |  | OUT (M) |  |  | STRING (BBL) | 212
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 3502 |  | SIZE (IN) |  | 12-1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1398
DEPTH, MD (M) | 3472 | 3502 | TVD @ 00:00HR (M) |  | 3502 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12-1/4" |  |  | 6-5/8 REG |  | 0.36 | 0.1 |  | PITS (BBL) | 996
MW IN (SG) | 2.15 | 2.15 | DAILY PROGRESS (M) |  | 62 |  | TYPE |  | MMD65DMH |  | MUD MOTOR |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 10.49 | 3.1 |  | ACT. SYS (BBL) | 2606
MW OUT (SG) | 2.15 | 2.15 | INST. ROP (M/HR) |  | 3.5 |  | SERIAL NO. |  | 12932459 |  | FLOAT SUB |  |  | 8-1/16" | 2-15/16" |  | 6-5/8 REG |  | 0.58 | 0.2 |  | RESV. SYS (BBL) | 1062
ECD (SG) | 2.17 | 2.17 | AVG. ROP (M/HR) |  | 2.76 |  | IADC CODE |  | M323 |  | STRING STAB |  |  | 12-1/4" | 3" |  | 6-5/8 REG |  | 2.48 | 0.5 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 159.8 | 159.8 | AVG. WOB (TON) |  | 4 - 8 |  | NOZZLES |  | 6 x 16/32" |  | LOWER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.66 | 0.2 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 64 | 62 | AVG. RPM SURFACE |  | 80 - 100 |  | DEPTH IN (M) |  | 3262 |  | SLIM PULSE |  |  | 8-15/16" | 3" |  | 6-5/8 REG |  | 9.45 | 1.8 |  | TOTAL | 4268
PV | 34 | 37 | AVG. RPM DOWNHOLE |  | 145 - 165 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 0.48 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 32 | 31 | FLOWRATE (GPM) |  | 610 |  | METERAGE (M) |  | 240 |  | PONY NMDC |  |  | 7-7/8" | 2-7/8" |  | 6-5/8 REG |  | 4.32 | 1.1 |  | RIG TANK | 105000
GEL ST. | 18/43 | 15/38 | PRESSURE (PSI) |  | 3500-3700 |  | RPM SURF. |  | 80 - 100 |  | 6 X 8" DCS |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 55.74 | 12.4467 |  | CAMP TANK | 29500
WL (ml/30 min.) | 6 | 6 | TORQ. ON-BTM (KLB-FT) |  | 7 - 9 |  | RPM BTM. |  | 145 - 165 |  | D.JAR |  |  | 8" | 3-1/4" |  | 6-5/8 REG |  | 9.16 | 2.0454 |  | CONSUMED | 12500
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 5 - 6 |  | WOB (TON) |  | 4 - 8 |  | 3 X 8" DC'S |  |  | 8" | 2-13/16" |  | 6-5/8 REG |  | 27.84 | 6.2166 |  | RECEIVED | 32000
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 145 |  | AVG. ROP (M/HR) |  | 2.0287 |  | X/O |  |  | 8-1/4" | 3" |  | 6-5/8 REG |  | 0.94 | 0.2099 |  | TOTAL | 134500
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 147 |  | BIT ROT HRS. |  | 118.3 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.09 | 4.1749 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 143 |  | K-REVS IN 24 HRS |  | 226 | [12 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1184 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 39.12 | [12 empty] | CONSUMED | 250690
KCl (mg/l) | 38134 | 38134 | JAR | 123.4 | NMDC | 123.4 | JET VELOCITY (M/SEC) |  | 49.8 | [12 empty] | RECEIVED | 250690
CHLORIDES | 18000 | 18000 | 5" HWDPS | 123.4 | STAB - 1 | 123.4 | TFA (IN²) |  | 1.18 | [12 empty] | TOTAL | 340000
CALCIUM | 180 | 180 | 8" DCS | 123.4 | STAB - 2 & 3 |  | HSI |  | 1.3 | [12 empty] | POB
OIL% | 3 | 3 | 9 1/2" DCS |  | SPSA | 123.4 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 178.59 |  |  | MPCL | 4
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 123.4 |  | BIT No. 5RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 17
SOLIDS % | 36.88 | 36.88 | ON BOTTOM HRS |  | 118.32 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. | 12.5 | 12.5 | CIRC. HRS |  | 129.34 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 140 | 2 X 80 |  | 20" SURFACE CASING |  |  | 594 | 3417 |  | 0.57 |  | 157.22 |  |  | 0.21 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 48187 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3445 |  | 0.38 |  | 149.41 |  |  | 0.15 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 6608652 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3478 |  | 0.51 |  | 138.13 |  |  | 0.14 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 36.62% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 168
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-28 | 2018-03-14 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3492 |  | 580/680 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3492 |  | 580/680 |  | CHINJI | 342
FIRE DRILL | 2018-03-09 | 2018-04-08 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 | [5 empty] | KAMLIAL | 1255
PIT DRILL | 2018-02-21 | 2018-03-14 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-03 | 2018-03-17 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-03-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 22 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-02-16 | 2018-03-18 | NEXT BOP TEST DATE |  | 2018-03-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 22 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43170 | 43171 | 24 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE IN ROTARY MODE FROM 3440M TO 3502M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43171 | 43171.25 | 6 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE IN ROTARY MODE FROM 3502M TO 3524M. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE & SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 3440M TO 3502M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14