## DDR#84
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 83.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-07-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3511 / 3511 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 83.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 3527 / 3527 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 65 METER
2019-07-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 11 RR |  | BHA NO. |  |  | 19 | IN (M) |  | 3251 |  | OUT (M) |  |  | STRING (BBL) | 234.8
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 3511 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1345.2
DEPTH, MD (M) | 3465 | 3511 | TVD @ 00:00HR (M) |  | 3511 |  | MANUFACTURER |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 850
MW IN (SG) | 2.26 | 2.26 | DAILY PROGRESS (M) |  | 65 |  | TYPE |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.22 | 0.94232 |  | ACT. SYS (BBL) | 2430
MW OUT (SG) | 2.26 | 2.26 | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | 5293592 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RESV. SYS (BBL) | 2336
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 3.3453 |  | IADC CODE |  | M223 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.72 | 0.16077 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 170 | 170 | AVG. WOB (TON) |  | 8 - 10 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.34 | 0.075922 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 76 | 75 | AVG. RPM SURFACE |  | 130 - 140 |  | DEPTH IN (M) |  | 3251 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.46 | 2.1124 |  | TOTAL | 4766
PV | 50 | 49 | AVG. RPM DOWNHOLE |  | 130 - 140 |  | DEPTH OUT (M) |  | - |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 32 | 31 | FLOWRATE (GPM) |  | 690 |  | METERAGE (M) |  | 260 |  | NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 9.12 | 2.0365 |  | RIG TANK | 98127
GEL ST. | 16/30 | 15/28 | PRESSURE (PSI) |  | 3500 - 3600 |  | RPM SURF. |  | 130 - 140 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | CAMP TANK | 15771
WL (ml/30 min) | 6.4 | 6.5 | TORQ. ON-BTM (KLB-FT) |  | 6 - 9 |  | RPM BTM. |  | 130 - 140 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 15001
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  | 4 - 5 |  | WOB (TON) |  | 8 - 10 |  | 9 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 82.9 | 18.5114 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 155 |  | AVG. ROP (M/HR) |  | 3.338 |  | D. JAR |  |  | 7.875 | 3.125 |  | 6 5/8 REG |  | 9.43 | 2.1057 |  | TOTAL | 113898
ALK (FILT.) | 0.4/2 | 0.4/2.1 | PICK-UP WT. (TON) |  | 175 |  | BIT ROT HRS. |  | 77.89 |  | 3 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 27.83 | 6.2144 |  | WATER (LTR)
PH | 9.5 | 9.8 | SLACK-OFF WT. (TON) |  | 145 |  | K-REVS IN 24 HRS |  | 155.05 |  | X/O |  |  | 7.625 | 3 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 430000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 604.65 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 74000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 46.9 | [12 empty] | CONSUMED | 202900
KCl (mg/l) | 47667 | 48620 | JAR | 92.96 | STAB - 1 | 92.96 | JET VELOCITY (M/SEC) |  | 64.43 | [12 empty] | RECEIVED | 258900
CHLORIDES (mg/l) | 26000 | 26000 | 5 1/2" HWDPS | 92.96 | STAB - 2 | 92.96 | TFA (IN²) |  | 1.03 | [12 empty] | TOTAL | 504000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.58 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 92.96 | SPSA | 92.96 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 239.05 |  |  | MPCL | 7
OIL % | 2 | 2.5 | BHA ROT. HRS |  | 21.76 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.7261 |  |  | MPCL SERV | 24
SOLIDS % | 42.64 | 42.65 | ON BOTTOM HRS |  | 19.43 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.4805 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 15 | CIRC. HRS |  | 21.13 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3399 |  | 2 |  | 144.91 |  |  | 0.3 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 77717.38 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3428 |  | 2.25 |  | 147.82 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7349885.1861 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3457 |  | 2.49 |  | 144.74 |  |  | 0.28 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 36.92% | MUD CLEANER | 3 x 170 | [6 empty] | 3485 |  | 2.48 |  | 145.05 |  |  | 0.02 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 206
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3412 | 450/450/500 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3412 | 550/550/550 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3412 | 620/620/620 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43672 | 43672.8125 | 19.5 | DRL | PT-P | DM | DRILLED 12 1/4'' HOLE FROM 3446M TO 3506M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT EACH CONNECTION.
43672.8125 | 43672.9167 | 2.5 | DRL | NPT-UP | RR | OBSERVED LEAKAGE IN WASHPIPE. POOH TO 3412M (R/B 4 STANDS). WHILE POOH, OBSERVED TIGHT SPOTS IN INTERVAL (3496M - 3462M). CLEARED THE SAME WITH RECIPROCATION. REPLACED WASHPIPE & P/T THE SAME THROUGH CIRCULATION (3600 PSI SPP). MEANWHILE CIRCULATED & ROTATED THE STRING. RIH FROM 3412M TO 3506M.
43672.9167 | 43673 | 2 | DRL | PT-P | DM | RESUMED DRILLING 12 1/4" HOLE FROM 3506M TO 3511M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-07-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43673 | 43673.25 | 6 | DRL | PT-P | DM | DRILLED 12 1/4'' HOLE FROM 3511M TO 3527M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 3446M TO 3506M. REPLACED THE WASHPIPE. DRILLED 12 1/4" HOLE FROM 3506M TO 3511M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE.
REMARKS |  |  | FLOW CHECKED @ 3464M, 3481M, 3488M & 3494M AFTER OBSERVING VARIATION IN ROP & PARAMETERS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14