## DDR#90
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 90
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAM ULLAH / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 3865 / 3865 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 89.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 3865 / 3865 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 52 METER
2019-08-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 11 RR |  | BHA NO. |  |  | 19 | IN (M) |  | 3251 |  | OUT (M) |  |  | STRING (BBL) | 259.4
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 3865 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1480.4
DEPTH, MD (M) | 3838 | 3865 | TVD @ 00:00HR (M) |  | 3865 |  | MANUFACTURER |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 889
MW IN (SG) | 2.26 | 2.26 | DAILY PROGRESS (M) |  | 52 |  | TYPE |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.22 | 0.94232 |  | ACT. SYS (BBL) | 2628.8
MW OUT (SG) | 2.26 | 2.25 | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | 5293592 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | RESV. SYS (BBL) | 2300
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.8921 |  | IADC CODE |  | M223 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.72 | 0.16077 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 181 | 181 | AVG. WOB (TON) |  | 8 - 10 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | L. SAVER SUB |  |  | 8.5 | 2.875 |  | 6 5/8 REG |  | 0.34 | 0.075922 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 55 | 57 | AVG. RPM SURFACE |  | 130 - 140 |  | DEPTH IN (M) |  | 3251 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 6 5/8 REG |  | 9.46 | 2.1124 |  | TOTAL | 4928.8
PV | 49 | 49 | AVG. RPM DOWNHOLE |  | 130 - 140 |  | DEPTH OUT (M) |  | - |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 36 | 41 | FLOWRATE (GPM) |  | 700-725 |  | METERAGE (M) |  | 614 |  | NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 9.12 | 2.0365 |  | RIG TANK | 105266
GEL ST. | 20/28 | 21/35 | PRESSURE (PSI) |  | 3600-3800 |  | RPM SURF. |  | 130 - 140 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | CAMP TANK | 11583
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  | 6 - 10 |  | RPM BTM. |  | 130 - 140 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 14263
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4 - 5 |  | WOB (TON) |  | 8 - 10 |  | 9 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 82.9 | 18.5114 |  | RECEIVED
ALK (MUD) | 0.7 | 0.8 | STRING WT. (TON) - ROT |  | 169 |  | AVG. ROP (M/HR) |  | 3.1805 |  | D. JAR |  |  | 7.875 | 3.125 |  | 6 5/8 REG |  | 9.43 | 2.1057 |  | TOTAL | 116849
ALK (FILT.) | 0.6/3.2 | 0.7/3.6 | PICK-UP WT. (TON) |  | 177 |  | BIT ROT HRS. |  | 193.05 |  | 3 X 8" DCS |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 27.83 | 6.2144 |  | WATER (LTR)
PH | 10 | 10.5 | SLACK-OFF WT. (TON) |  | 148 |  | K-REVS IN 24 HRS |  | 147 |  | X/O |  |  | 7.625 | 3 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 445000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1540.74 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 70000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 49.6 | [12 empty] | CONSUMED | 289600
KCl (mg/l) | 47667.5 | 47667.5 | JAR | 221.27 | STAB - 1 | 221.27 | JET VELOCITY (M/SEC) |  | 66.45 | [12 empty] | RECEIVED | 279600
CHLORIDES (mg/l) | 26000 | 26000 | 5 1/2" HWDPS | 221.27 | STAB - 2 | 221.27 | TFA (IN²) |  | 1.03 | [12 empty] | TOTAL | 515000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.78 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 221.27 | SPSA | 221.27 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 239.05 |  |  | MPCL | 5
OIL % | 3.2 | 3.2 | BHA ROT. HRS |  | 23.02 |  | BIT NO. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.7261 |  |  | MPCL SERV | 25
SOLIDS % | 42.46 | 42.66 | ON BOTTOM HRS |  | 17.98 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.4805 |  |  | SECURITY
M.B.T. (lb/bbl) | 15 | 12.5 | CIRC. HRS |  | 23.18 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 61
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3743 |  | 0.51 |  | 247.99 |  |  | 0.27 |  | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 94917.73 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3772 |  | 0.59 |  | 274.69 |  |  | 0.27 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7792102.5761 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3800 |  | 0.51 |  | 314.16 |  |  | 0.41 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 39.14% | MUD CLEANER | 3 x 170 | [6 empty] | 3828 |  | 0.68 |  | 290.53 |  |  | 0.32 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 206
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3827 | 250/245/240 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3827 | 345/345/340 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3827 | 430/400/380 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-07-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 21 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-03 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43678 | 43678.8438 | 20.25 | DRL | PT-P | DM | DRILLED 12 1/4" HOLE FROM 3813M TO 3865M. REAMED & RECORDED MWD SURVEY AT CONNECTION.
43678.8438 | 43678.9062 | 1.5 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP.
43678.9062 | 43678.9271 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED PRIOR TO POOH. OBSERVED WELL TRICKLING.
43678.9271 | 43679 | 1.75 | DRL | NPT-UP | CIR | RESUMED CIRCULATION TO HOMOGENIZE MUD COLUMN.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43679 | 43679.0417 | 1 | DRL | NPT-UP | CIR | CONT'D CIRCULATION TO HOMOGENIZE MUD COLUMN. RECEIVED MIN MWOUT - 2.21 SG.
43679.0417 | 43679.0938 | 1.25 | DRL | NPT-UP | WC | SHUT IN & OBSERVED WELL. RECORDED SIDP = 0 PSI & SICP = 80 PSI.
43679.0938 | 43679.25 | 3.75 | DRL | NPT-UP | WC | CIRCULATED WITH 2.26 SG MUD @ 40 SPM (DRILLER'S METHOD 1ST CIRCULATION). ROTATED STRING INTERMITTENTLY.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION THROUGH CHOKE IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 3813M TO 3865M. CIRCULATED BOTTOMS UP. OBSERVED WELL TRICKLING. CIRCULATED TO HOMOGENIZE MUD COLUMN.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | STABILIZE THE WELL. FLOW CHECK & POOH TO SURFACE FOR BHA INSPECTION.
REMARKS |  |  | FLOW CHECKED @ 3860M AFTER OBSERVING VARIATION IN PARAMETERS - WELL STATIC.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14