## DDR#94
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 94
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH / HAMZA / ADNAN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3865 / 3865 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 93.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 3865 / 3865 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-08-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 11 RR1 |  | BHA NO. |  |  | 20 | IN (M) |  | 3865 |  | OUT (M) |  |  | STRING (BBL) | 173
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1598.6
DEPTH, MD (M) | 3865 | 3865 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 747
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.27 | 0.95348 |  | ACT. SYS (BBL) | 2518.6
MW OUT (SG) |  | 2.27 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5293592 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.78 | 0.17417 |  | RESV. SYS (BBL) | 2365
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M223 |  | L. SAVER SUB |  |  | 8 | 2.875 |  | 7 5/8 REG |  | 0.62 | 0.13845 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  | 181 | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 x 15/32 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 8 5/8 REG |  | 9.34 | 2.0856 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 66 | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 3865 |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 9 5/8 REG |  | 0.41 | 0.091552 |  | TOTAL | 4883.6
PV | 41 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 8.25 | 2.8125 |  | 10 5/8 REG |  | 9.22 | 2.0588 |  | DIESEL (LTR)
YIELD POINT | 31 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 11 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 105546
GEL ST. | 17/28 | 12/22 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | PBL SUB |  |  | 8.25 | 3.5 |  | 12 5/8 REG |  | 3.46 | 0.77261 |  | CAMP TANK | 24785
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 9 X 8" DCS |  |  | 8 | 2.8125 |  | 13 5/8 REG |  | 83.13 | 18.5628 |  | CONSUMED | 5806
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 14 5/8 REG |  | 9.65 | 2.1548 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 15 5/8 REG |  | 27.92 | 6.2345 |  | TOTAL | 130331
ALK (FILT.) | 0.5/3 | 0.5/3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X/O |  |  | 7.625 | 2.875 |  | 16 5/8 REG |  | 0.8 | 0.17864 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.96 | 3.124 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 70000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 180000
KCl (mg/l) | 45760.8 | 45760.8 | JAR | 0 | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 155000
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 0 | STAB - 2 | 0 | TFA (IN²) |  | 1.03 | [12 empty] | TOTAL | 470000
HARDNESS (mg/l) | 480 | 480 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [14 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 0 | SPSA | 0 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.42 |  |  | MPCL | 7
OIL % | 3 | 3 | BHA ROT. HRS |  | 0 |  | BIT NO. 11 RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.5152 |  |  | MPCL SERV | 24
SOLIDS % | 42.69 | 42.89 | ON BOTTOM HRS |  | 0 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.1986 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | CIRC. HRS |  | 11.38 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3743 |  | 0.51 |  | 247.99 |  |  | 0.27 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 52577 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3772 |  | 0.59 |  | 274.69 |  |  | 0.27 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8009400 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3800 |  | 0.51 |  | 314.16 |  |  | 0.41 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 40.24% | MUD CLEANER | 3 x 170 | [6 empty] | 3828 |  | 0.68 |  | 290.53 |  |  | 0.32 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 206
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3827 | 250/245/240 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3827 | 345/345/340 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3827 | 430/400/380 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43682 | 43682.0312 | 0.75 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB, OK.
43682.0312 | 43682.1562 | 3 | DRL | PT-P | BHA | P/U & M/U INSPECTED BHA SINGLE BY SINGLE & RIH FROM 40M TO 237M.
43682.1562 | 43682.2292 | 1.75 | DRL | PT-P | RIH | RIH FROM 237M TO 808M. FILLED UP STRING AFTER 10 STANDS.
43682.2292 | 43682.2396 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION AFTER 20 STANDS.
43682.2396 | 43682.4062 | 4 | DRL | PT-P | RIH | CONT'D RIH FROM 808M TO 2380M.
43682.4062 | 43682.4792 | 1.75 | DRL | NPT-P | RS | SLIPPED & CUT DRILL LINE 34M. MEANWHILE CIRCULATED BOTTOMS UP.
43682.4792 | 43682.5 | 0.5 | DRL | PT-P | CIR | CONTINUED CIRCULATION.
43682.5 | 43682.5417 | 1 | DRL | NPT-UP | RR | MALFUNCTIONED CROWNO-MATIC / ACS. WORKED & FIXED THE SAME.
43682.5417 | 43682.5625 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43682.5625 | 43682.625 | 1.5 | DRL | PT-P | RIH | CONT'D RIH FROM 2380M TO 2623M. WHILE RIH, OBSERVED COMPRESSION @ 2623 M. ATTEMPTED TO CLEAR WITH STRING RECIPROCATION, FAILED. MAXIMUM WEIGHT APPLIED 15 TONS.
43682.625 | 43683 | 9 | DRL | NPT-UP | RW | REAMED DOWN FROM 2623M TO 2693M. OBSERVED HARD REAMING FROM 2675M TO 2700M ; WHILE REAMING DOWN RECORDED CHECKSHOT AT 2674M, 2655M AND 2679M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43683 | 43683.25 | 6 | DRL | NPT-UP | RW | CONT'D REAM DOWN FROM 2693M TO 2808M ; WHILE REAMING DOWN RECORDED CHECKSHOT AT 2705M, 2710M & 2736M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | REAMING DOWN IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | F/TESTED PBL SUB, OK. P/UP AND M/UP INSPECTED BHA COMPONENTS AND RIH FROM 40M TO 237M, CONT'D RIH FROM 237M TO 2380M, FILLED UP STRING EVERY 10 STDS, SLIPPED AND CUT D.LINE, CONT'D RIH DOWN TO 2623M, WASHED/REAMED DOWN FROM 2623M TO 2693M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE REAM / WASH DOWN TO BTM & RESUME DRILLING, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14