## DDR#96
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 96
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3866 / 3866 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 95.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 3875 / 3875 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1
2019-08-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  | 11 RR1 |  | BHA NO. |  |  | 20 | IN (M) |  | 3865 |  | OUT (M) |  |  | STRING (BBL) | 252
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 3866 |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1487.8
DEPTH, MD (M) | 3866 | 3866 | TVD @ 00:00HR (M) |  | 3866 |  | MANUFACTURER |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 865
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  | 1 |  | TYPE |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.27 | 0.95348 |  | ACT. SYS (BBL) | 2604.8
MW OUT (SG) |  | 2.27 | INST. ROP (M/HR) |  | 2.37 |  | SERIAL NO. |  | 5293592 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.78 | 0.17417 |  | RESV. SYS (BBL) | 2377
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M223 |  | L. SAVER SUB |  |  | 8 | 2.875 |  | 7 5/8 REG |  | 0.62 | 0.13845 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 181 | 181 | AVG. WOB (TON) |  | 10 |  | NOZZLES (1/32") |  | 6 x 15/32 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 8 5/8 REG |  | 9.34 | 2.0856 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 76 | 68 | AVG. RPM SURFACE |  | 118 |  | DEPTH IN (M) |  | 3865 |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 9 5/8 REG |  | 0.41 | 0.091552 |  | TOTAL | 4981.8
PV | 52 | 47 | AVG. RPM DOWNHOLE |  | 118 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 8.25 | 2.8125 |  | 10 5/8 REG |  | 9.22 | 2.0588 |  | DIESEL (LTR)
YIELD POINT | 29 | 27 | FLOWRATE (GPM) |  | 650 |  | METERAGE (M) |  | 1 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 11 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 116820
GEL ST. | 19/33 | 15/28 | PRESSURE (PSI) |  | 3485 |  | RPM SURF. |  | 118 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 12 5/8 REG |  | 3.46 | 0.77261 |  | CAMP TANK | 23490
WL (ml/30 min) | 5.5 | 5.8 | TORQ. ON-BTM (KLB-FT) |  | 5-6 |  | RPM BTM. |  | 118 |  | 9 X 8" DCS |  |  | 8 | 2.8125 |  | 13 5/8 REG |  | 83.13 | 18.5628 |  | CONSUMED | 8995
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 10 |  | D. JAR |  |  | 7.875 | 3 |  | 14 5/8 REG |  | 9.65 | 2.1548 |  | RECEIVED | 8000
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 165 |  | AVG. ROP (M/HR) |  | 12.5 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 15 5/8 REG |  | 27.92 | 6.2345 |  | TOTAL | 140310
ALK (FILT.) | 0.5/2.9 | 0.5/2.9 | PICK-UP WT. (TON) |  | 175 |  | BIT ROT HRS. |  | 0.08 |  | X/O |  |  | 7.625 | 2.875 |  | 16 5/8 REG |  | 0.8 | 0.17864 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | K-REVS IN 24 HRS |  | 0.57 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.96 | 3.124 |  | RIG STORAGE | 490000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 0.6 | [12 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 50 | [12 empty] | CONSUMED | 147500
KCl (mg/l) | 41947 | 40047.7 | JAR | 42.15 | STAB - 1 | 42.15 | JET VELOCITY (M/SEC) |  | 67.04 | [12 empty] | RECEIVED | 142500
CHLORIDES (mg/l) | 23000 | 22000 | 5 1/2" HWDPS | 42.15 | STAB - 2 |  | TFA (IN²) |  | 1.03 | [12 empty] | TOTAL | 575000
HARDNESS (mg/l) | 400 | 390 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  | 2.8 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 42.15 | SPSA | 42.15 | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.42 |  |  | MPCL | 5
OIL % | 3.2 | 3.3 | BHA ROT. HRS |  | 13.4 |  | BIT NO. 11 RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.5152 |  |  | MPCL SERV | 24
SOLIDS % | 43.06 | 42.99 | ON BOTTOM HRS |  | 0.1 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.1986 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | CIRC. HRS |  | 18.6 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  | 37 | 3772 |  | 0.59 |  | 274.69 |  |  | 0.27 |  | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 64597 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 3800 |  | 0.51 |  | 314.16 |  |  | 0.41 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8132624 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 3828 |  | 0.68 |  | 290.53 |  |  | 0.32 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 40.86% | MUD CLEANER | 3 x 170 | [6 empty] | 3858 |  | 0.78 |  | 278.9 |  |  | 0.61 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 206
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3827 | 250/245/240 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3827 | 345/345/340 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3827 | 430/400/380 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-07-19 | 2019-08-02 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 4 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43665 | 43684.0729 | 1.75 | DRL | NPT-UP | RW | REAMED DOWN FROM 3064M TO 3100M.
43684.0729 | 43684.125 | 1.25 | DRL | NPT-UP | RIH | RIH (ON ELEVATOR) FROM 3100M TO 3434M. OBSERVED OBSTRUCTION AT 3434M, ATTEMPTED TO CLEAR WITH STRING RECIPROCATION, NO SUCCESS.
43684.125 | 43684.3542 | 5.5 | DRL | NPT-UP | RIH | CONNECTED TDS, REAMED/WASHED DOWN FROM 3434M TO 3826M. OBSERVED CUT MUD WT ON SURFACE = 2.06 SG.
43684.3542 | 43684.375 | 0.5 | DRL | NPT-UP | SHUT | STOPPED PUMPS, CLOSED ANNULAR BOP TO SHUT IN THE WELL. RECORDED SIDPP = 0 PSI AND SICP = 0 PSI.
43684.375 | 43684.4375 | 1.5 | DRL | NPT-UP | CIR | OPENED WELL, RESUMED CIRCULATION TO HOMOGENIZE MUD TO 2.27 SP.GR.OBSERVED RETURN MUD SP.GR VARYING FROM 2.16 TO 2.20 SG.
43684.4375 | 43684.7083 | 6.5 | DRL | NPT-UP | WC | STOPPED PUMPS, CLOSED ANNULAR BOP TO SHUT IN THE WELL. RECORDED SIDPP = 0 PSI & SICP = 0 PSI. CIRCULATED 2.27 SP GR MUD THROUGH CHOKE @ 550 PSI CONSTANT SIDPP, MEANWHILE ROTATED STRING INTERMITTENTLY. CONT'D CIRCULATION TILL 2.25 + MUD SP GR. SURFACED (WITH FULL OPEN CHOKE & 700 PSI SIDPP. MIN CUT MUD = 2.20 SP. GR RECEIVED WHILE CIRCULATION THROUGH CHOKE)
43684.7083 | 43684.7292 | 0.5 | DRL | NPT-UP | CIR | OPENED WELL & OBSERVED WELL STATIC, RESUMED DIRECT CIRCULATION TO HOMOGENIZE MUD COLUMN.
43684.7292 | 43684.9792 | 6 | DRL | NPT-UP | RW | REAMED DOWN FROM 3826M TO BOTTOM AT 3865M. OBSERVED HARD REAMING AT 3830M-3835M, 3850M-3851M & 3859M TO 3863M. WHILE REAMING DOWN HOMOGENIZED MUD COLUMN IN / OUT = 2.27 SG / 2.27 SG.
43684.9792 | 43685 | 0.5 | DRL | PT-P | D | RESUMED DRILLING, DRILLED AHEAD 12 1/4'' HOLE FROM 3865M TO 3866M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43685 | 43685.25 | 6 | DRL | PT-P | D | CONT'D DRILLING 12 1/4'' HOLE FROM 3866M TO 3875M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D REAM DOWN FROM 3064M TO 3100M, RIH ON ELEVATOR FROM 3100M TO 3434M, OBSERVED OBSTRUCTION, REAMED DOWN FROM 3434M TO 3826M, OBSERVED CUT MUD WT OF 2.06 SG SURFACED, SHUT IN WELL , RECORDED SIDPP / SICPP = O PSI, OPENED WELL & CIRCULATED TO CHECK RETURN MUD SP GR, CLOSED ANNULAR BOP AND CIRCULATED 2.27 SG MUD THROUGH CHOKE (MIN CUT MUD WT RECEIVED 2.20 SG DURING CIRCULATION), DIRECT CIRCULATED AFTER 2.25 + SP GR SURFACED, CONT'D REAM DOWN FROM 3826M TO BTM AT 3865M MEANWHILE HOMOGENIZED MUD COLUMN, RESUMED DRILLING, DRILLED AHEAD 12 1/4'' HOLE FROM 3865M TO 3866M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4'' HOLE.
REMARKS |  |  | FLUSHED AND CLEANED ALL CHOKE MANIFOLD VALVES.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14