## DDR#97
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 97
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-03-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / TALHA SHAKIL |  |  | MD/TVD @ 00:00HRS: |  | 3951 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 96.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 3952 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 9
2018-03-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 6 |  |  |  |  | 12 | IN (M) |  | 3735 |  | OUT (M) |  |  | STRING (BBL) | 244
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 3951 |  | SIZE (IN) |  | 12-1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1572
DEPTH, MD (M) | 3951 | 3951 | TVD @ 00:00HR (M) |  | 3951 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 12-1/4" | 3-1/4" |  | 6-5/8 REG |  | 0.27 | 0.1 |  | PITS (BBL) | 1014
MW IN (SG) | 2.15 | 2.18 | DAILY PROGRESS (M) |  | 9 |  | TYPE |  | MDSiZ616 |  | BIT SUB |  |  | 9-5/8" | 3-1/4" |  | 6-5/8 REG |  | 1.04 | 0.4 |  | ACT. SYS (BBL) | 2830
MW OUT (SG) | 2.15 | 2.15 | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | JN 5197 |  | 2 X 8" DCS |  |  | 8-1/16" | 2-7/8" |  | 6-5/8 REG |  | 18.46 | 4.1221 |  | RESV. SYS (BBL) | 1081
ECD (SG) | 2.17 | 2.2 | AVG. ROP (M/HR) |  | 0.84 |  | IADC CODE |  | - |  | STRING STAB |  |  | 12-1/4" | 2-7/8" |  | 6-5/8 REG |  | 2.33 | 0.5 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 156.2 | 156.2 | AVG. WOB (TON) |  | 7-8 |  | NOZZLES |  | 6 x 18/32" |  | 1 X 8" DCS |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 9.27 | 2.07 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 61 | 65 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 3735 |  | STRING STAB |  |  | 8-15/16" | 2-7/8" |  | 6-5/8 REG |  | 2.33 | 0.5 |  | TOTAL | 4511
PV | 36 | 43 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  | - |  | 6 X 8" DCS |  |  | 8-1/4" | 2-7/8" |  | 6-5/8 REG |  | 55.66 | 12.4288 |  | DIESEL (LTR)
YIELD POINT | 32 | 32 | FLOWRATE (GPM) |  | 630-650 |  | METERAGE (M) |  | 216 |  | D.JAR |  |  | 8" | 3" |  | 6-5/8 REG |  | 9.17 | 1.5 |  | RIG TANK | 77500
GEL ST. | 22/42 | 22/42 | PRESSURE (PSI) |  | 3450-3600 |  | RPM SURF. |  | 100-120 |  | 3 X 8" DC'S |  |  | 8" | 2-7/8" |  | 6-5/8 REG |  | 27.85 | 6.2189 |  | CAMP TANK | 21500
WL (ml/30 min.) | 6 | 6 | TORQ. ON-BTM (KLB-FT) |  | 5-6 |  | RPM BTM. |  | 100-120 |  | X/O |  |  | 5" | 2-7/8" |  | 6-5/8 REG |  | 0.95 | 0.21 |  | CONSUMED | 14000
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-5 |  | WOB (TON) |  | 4-8 |  | 6 X 5" HWDPS |  |  | 5" | 3" |  | 4-1/2 IF |  | 56.17 | 4.1809 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 160 |  | AVG. ROP (M/HR) |  | 1.4188 | [12 empty] | TOTAL | 99000
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 165 |  | BIT ROT HRS. |  | 152.24 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 150 |  | K-REVS IN 24 HRS |  | 140 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1070 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 39.26 | [12 empty] | CONSUMED | 150440
KCl (mg/l) | 37180 | 37180 | JAR | 176.82 | NMDC |  | JET VELOCITY (M/SEC) |  | 41.6 | [12 empty] | RECEIVED | 205440
CHLORIDES | 17500 | 17500 | 5" HWDPS | 176.82 | STAB - 1 | 176.82 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 495000
CALCIUM | 180 | 180 | 8" DCS | 176.82 | STAB - 2 | 176.82 | HSI |  | 0.9 | [12 empty] | POB
OIL% | 4 | 4 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 183.5 |  |  | MPCL | 3
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 176.82 |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 14
SOLIDS % | 36.9 | 37.41 | ON BOTTOM HRS |  | 152.24 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. | 12.5 | 12.5 | CIRC. HRS |  | 190.11 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 X 140 | 2 X 140 |  | 20" SURFACE CASING |  |  | 594 | 3478 |  | 0.51 |  | 138.13 |  |  | 0.14 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 52881.4061 | SHAKER-2 | 2 X 140 | 2 X 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7436010.9858 | SHAKER-3 | 1 X 120 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3531 |  | 0.83 |  | 141.02 |  |  | 0.18 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 41.2% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3559 |  | 0.78 |  | 132.49 |  |  | 0.14 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 20
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-02-28 | 2018-03-28 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3951 |  | 725/885 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 3951 |  | 730/890 |  | CHINJI | 342
FIRE DRILL | 2018-03-16 | 2018-04-15 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-03-16 | 2018-04-06 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 | 2018-04-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-03-19 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 22 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-03-16 | 2018-04-15 | NEXT BOP TEST DATE |  | 2018-04-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 22 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43186 | 43186.5 | 12 | DRL | PT-P | D | DRILLED 12-1/4" HOLE FROM 3942M TO 3951M.
43186.5 | 43186.5833 | 2 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE PRIOR TO WIPER TRIP.
43186.5833 | 43186.5938 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43186.5938 | 43186.6875 | 2.25 | DRL | PT-P | WT | POOH / PUMPED OUT UPTO 3757M. OBSERVED TIGHT HOLE FROM 3951 TO 3927M. FAILED TO CLEAR WITH BACK REAMING. TDS STALLED FREQUENTLY. CLEARED TIGHT HOLE BY RECIPROCATING STRING. MAX OVER PULL APPLIED 30 TONS & BACK REAMED FROM 3827M TO 3818M.
43186.6875 | 43186.7083 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43186.7083 | 43186.7708 | 1.5 | DRL | PT-P | WT | RIH DOWN TO 3924M. WASHED DOWN FROM 3924M TO 3930M. OBSERVED LEAKAGE FROM WASHPIPE.
43186.7708 | 43186.9167 | 3.5 | DRL | NPT-UP | RR | PULLED BACK TO 3890M. REPLACED & P/TESTED WASHPIPE. MEANWHILE CIRCULATED THROUGH CIRCULATING HEAD. RIH DOWN TO 3930M.
43186.9167 | 43187 | 2 | DRL | PT-P | CIR | CIRCULATED TO INCREASE & HOMOGENIZE MUD WT TO 2.18 SG. MEANWHILE HARD REAMED FROM 3930M TO 3935M. OBSERVED HI TORQUE & TDS STALLED FREQUENTLY .
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-03-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43187 | 43187.1042 | 2.5 | DRL | PT-P | CIR | CIRCULATED TO INCREASE & HOMOGENIZE MUD WT TO 2.18 SG. MEANWHILE HARD REAMED FROM 3935M TO 3939M. OBSERVED TIGHT HOLE @ 3935-3936M (OBSERVED HI TORQUE & TDS STALLED FREQUENTLY WHILE REAMING).
43187.1042 | 43187.1458 | 1 | DRL | PT-P | RW | HARD REAMED FROM 3939M DOWN TO 3946M. OBSERVED TIGHT HOLE @ 3940-3942M. OBSERVED HI TORQUE & TDS STALLED FREQUENTLY WHILE REAMING.
43187.1458 | 43187.2292 | 2 | DRL | PT-P | RW | PULLED BACK TO 3920M. RIH DOWN TO 3935M. HARD REAMED FROM 3935M DOWN TO 3951M (BOTTOM). OBSERVED TIGHT HOLE @ 3935-3936M & @ 3940-3942M (OBSERVED HI TORQUE & TDS STALLED FREQUENTLY WHILE REAMING).
43187.2292 | 43187.25 | 0.5 | DRL | PT-P | D | RECORDED SCR & RESUMED DRILLING. DRILLED 12-1/4" HOLE DOWN TO 3952M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE & SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12-1/4" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12-1/4" HOLE FROM 3942 M TO 3951M. CIRCULATED TO CLEAN HOLE. PERFORMED WIPER TRIP & CLEARED TIGHT HOLE BY REAMING. CIRCULATED TO INCREASE MUD WEIGHT TO 2.18 SG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE TO HOMOGENIZE 2.18 SG MUD. REAM TIGHT HOLE & DRILL AHEAD.
REMARKS |  |  | AFTER INCREASING MUD WEIGHT TO 2.18SG, OVERALL HOLE CONDITION HAS IMPROVED EXCEPT TWO POINTS. FROM 3942M TO 3940M & FROM 3936M TO 3935M(BIT DEPTH). TDS STALLS & STRING HANGS DURING RECIPROCATING.
Formulas:
DHARIAN - 1 = [DATE]+28
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14