## DDR#98
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 98
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3927 | 3927 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 97.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 3937 | 3937 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 28
2019-08-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  |  | 11 RR1 |  | BHA NO. |  |  | 20 | IN (M) |  | 3865 |  | OUT (M) |  |  | STRING (BBL) | 258
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 3927 |  | SIZE (IN) |  |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1509.7
DEPTH, MD (M) | 3908 | 3927 | TVD @ 00:00HR (M) |  | 3927 |  | MANUFACTURER |  |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 854
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  | 28 |  | TYPE |  |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.27 | 0.95348 |  | ACT. SYS (BBL) | 2621.7
MW OUT (SG) |  | 2.27 | INST. ROP (M/HR) |  | 1.95 |  | SERIAL NO. |  |  | 5293592 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.78 | 0.17417 |  | RESV. SYS (BBL) | 2192
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.39 |  | IADC CODE |  |  | M223 |  | L. SAVER SUB |  |  | 8 | 2.875 |  | 7 5/8 REG |  | 0.62 | 0.13845 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 181.4 | 181 | AVG. WOB (TON) |  | 7 |  | NOZZLES (1/32") |  |  | 6 x 15/32 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 8 5/8 REG |  | 9.34 | 2.0856 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 63 | 66 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  |  | 3865 |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 9 5/8 REG |  | 0.41 | 0.091552 |  | TOTAL | 4813.7
PV | 44 | 42 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 8.25 | 2.8125 |  | 10 5/8 REG |  | 9.22 | 2.0588 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  | 710 |  | METERAGE (M) |  |  | 62 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 11 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 130154
GEL ST. | 17/25 | 23/29 | PRESSURE (PSI) |  | 3500-4100 |  | RPM SURF. |  |  | 115-135 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 12 5/8 REG |  | 3.46 | 0.77261 |  | CAMP TANK | 22174
WL (ml/30 min) | 5.3 | 5.3 | TORQ. ON-BTM (KLB-FT) |  | 5-9 |  | RPM BTM. |  |  | 115-135 |  | 9 X 8" DCS |  |  | 8 | 2.8125 |  | 13 5/8 REG |  | 83.13 | 18.5628 |  | CONSUMED | 15674
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  |  | 4-11 |  | D. JAR |  |  | 7.875 | 3 |  | 14 5/8 REG |  | 9.65 | 2.1548 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 169 |  | AVG. ROP (M/HR) |  |  | 1.9089 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 15 5/8 REG |  | 27.92 | 6.2345 |  | TOTAL | 152328
ALK (FILT.) | 0.5/2.9 | 0.5/2.8 | PICK-UP WT. (TON) |  | 177 |  | BIT ROT HRS. |  |  | 32.48 |  | X/O |  |  | 7.625 | 2.875 |  | 16 5/8 REG |  | 0.8 | 0.17864 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | K-REVS IN 24 HRS |  |  | 84.37 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.96 | 3.124 |  | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 238.11 | [12 empty] | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 48 | [12 empty] | CONSUMED | 302300
KCl (mg/l) | 41947.4 | 45760.8 | JAR | 86.23 | STAB - 1 | 86.23 | JET VELOCITY (M/SEC) |  |  | 64.37 | [12 empty] | RECEIVED | 307300
CHLORIDES (mg/l) | 23000 | 25000 | 5 1/2" HWDPS | 86.23 | STAB - 2 |  | TFA (IN²) |  |  | 1.03 | [12 empty] | TOTAL | 530000
HARDNESS (mg/l) | 390 | 380 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  |  | 2.54 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 86.23 | SPSA | 86.23 | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.42 |  |  | MPCL | 5
OIL % | 3.4 | 3.5 | BHA ROT. HRS |  | 20.75 |  | BIT NO. 11 RR1 |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.5152 |  |  | MPCL SERV | 25
SOLIDS % | 42.86 | 42.7 | ON BOTTOM HRS |  | 11.7 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.1986 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | CIRC. HRS |  | 20.99 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 3828 |  | 0.68 |  | 290.53 |  |  | 0.32 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 65314 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 3858 |  | 0.78 |  | 278.9 |  |  | 0.61 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8274648 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 3887 |  | 1.25 |  | 235.24 |  |  | 0.9 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 41.57% | MUD CLEANER | 3 x 170 | [7 empty] | 3913 |  | 1.44 |  | 209.56 |  |  | 1.05 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3931 | 400/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3931 | 500/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3931 | 625/600/625 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 9 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43686 | 43686.1562 | 3.75 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3899M TO 3908M. RECORDED CHECKSHOT AT 3894M. OBSERVED INCL; 1.45°, AZM; 229.04° SCHL POWER DRIVE FAILED TO STEER IN DESIRED DIRECTION.
43686.1562 | 43686.2292 | 1.75 | DRL | NPT-UP | CIR | CIRCULATED FOR BOTTOMS UP, KEPT CIRCULATING TILL SHAKERS CLEAN.
43686.2292 | 43686.2396 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43686.2396 | 43686.375 | 3.25 | DRL | NPT-UP | RW | PUMPED OUT OF HOLE FROM 3908M TO 3682M. TIGHT SPOTS @3860M;3800 M;3783M; & AT 3682 M CLEARED WITH STRING RECIPROCATION.
43686.375 | 43686.3958 | 0.5 | DRL | NPT-UP | E/C | DOWN LINKED ANTI JAMMING COMMANDS TO PD.
43686.3958 | 43686.5312 | 3.25 | DRL | NPT-UP | RIH / RW | RESUMED RIH & RIH FROM 3682M TO 3908M. (DURING RIH CLEARED TIGHT SPOTS @ 3702M;@ 3711M & AT 3719 M WITH STRING RECIPROCATION. REAMED TIGHT HOLE FROM 3726M TO 3754M; WASHED DOWN FROM 3755 M TO 3784M; RIH ON ELEVATORS FROM 3784M TO 3812 M. REAMED DOWN FROM 3812 M TO 3908M)
43686.5312 | 43686.5729 | 1 | DRL | NPT-UP | E/C | DOWN LINKED PD ON POWER-V MODE PRIOR DRILLING.
43686.5729 | 43687 | 10.25 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED 12 1/4'' HOLE FROM 3908M TO 3927M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION. (RECORDED CHECKSHOT AT 3907M, OBSERVED PD STEERING IN DESIRED DIRECTION)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43687 | 43687.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3927M TO 3937M. RECORDED CHECKSHOT AT 3920M, OBSERVED INCL : 1.22°, AZM : 205.87
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4'' HOLE FROM 3899M TO 3908M, RECORDED CHECKSHOT & OBSERVED PD NOT WORKING PROPERLY, CIRCULATED FOR BTMS UP, FLOW CHECKED, WELL STATIC, PUMPED OUT FROM 3908M TO 3682M, PERFORMED ANTI JAMMING ON PD, RIH BACK TO BTM, DOWNLINKED PD, RESUMED DRILLING, DRILLED 12 1/4'' HOLE FROM 3908M TO 3927M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14