## DDR#99
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 99
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 3968 | 3968 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 98.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 3981 | 3981 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 41
2019-08-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  |  | 11 RR1 |  | BHA NO. |  |  | 20 | IN (M) |  | 3865 |  | OUT (M) |  |  | STRING (BBL) | 260
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 3968 |  | SIZE (IN) |  |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1526.3
DEPTH, MD (M) | 3945 | 3968 | TVD @ 00:00HR (M) |  | 3968 |  | MANUFACTURER |  |  | BAKER HUGHES |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.41 | 0.2 |  | PITS (BBL) | 821
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  | 41 |  | TYPE |  |  | TD606FX |  | POWER DRIVE PD |  |  | 9 | 5.125 |  | 6 5/8 REG |  | 4.27 | 0.95348 |  | ACT. SYS (BBL) | 2607.3
MW OUT (SG) | 2.27 | 2.27 | INST. ROP (M/HR) |  | 1.71 |  | SERIAL NO. |  |  | 5293592 |  | FLOAT SUB |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 0.78 | 0.17417 |  | RESV. SYS (BBL) | 2228
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.05 |  | IADC CODE |  |  | M223 |  | L. SAVER SUB |  |  | 8 | 2.875 |  | 7 5/8 REG |  | 0.62 | 0.13845 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 183.2 | 183.2 | AVG. WOB (TON) |  | 8 |  | NOZZLES (1/32") |  |  | 6 x 15/32 |  | SPSA (SLIMPULSE) |  |  | 8.5 | 5 |  | 8 5/8 REG |  | 9.34 | 2.0856 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 57 | 55 | AVG. RPM SURFACE |  | 130 |  | DEPTH IN (M) |  |  | 3865 |  | U. SAVER SUB |  |  | 8.25 | 2.875 |  | 9 5/8 REG |  | 0.41 | 0.091552 |  | TOTAL | 4835.3
PV | 41 | 40 | AVG. RPM DOWNHOLE |  | 130 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 8.25 | 2.8125 |  | 10 5/8 REG |  | 9.22 | 2.0588 |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  | 710 |  | METERAGE (M) |  |  | 103 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 11 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 140292
GEL ST. | 16/22 | 17/24 | PRESSURE (PSI) |  | 3700-4000 |  | RPM SURF. |  |  | 120-130 |  | PBL SUB |  |  | 8.25 | 3.5 |  | 12 5/8 REG |  | 3.46 | 0.77261 |  | CAMP TANK | 21470
WL (ml/30 min) | 5.2 | 5.2 | TORQ. ON-BTM (KLB-FT) |  | 4-7 |  | RPM BTM. |  |  | 120-130 |  | 9 X 8" DCS |  |  | 8 | 2.8125 |  | 13 5/8 REG |  | 83.13 | 18.5628 |  | CONSUMED | 15566
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  |  | 4-8 |  | D. JAR |  |  | 7.875 | 3 |  | 14 5/8 REG |  | 9.65 | 2.1548 |  | RECEIVED | 25000
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 169 |  | AVG. ROP (M/HR) |  |  | 1.9623 |  | 3 X 8" DCS |  |  | 8 | 2.875 |  | 15 5/8 REG |  | 27.92 | 6.2345 |  | TOTAL | 161762
ALK (FILT.) | 0.5/2.9 | 0.5/2.9 | PICK-UP WT. (TON) |  | 177 |  | BIT ROT HRS. |  |  | 52.49 |  | X/O |  |  | 7.625 | 2.875 |  | 16 5/8 REG |  | 0.8 | 0.17864 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | K-REVS IN 24 HRS |  |  | 157.28 |  | 9 X 5.5" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.96 | 3.124 |  | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 395.39 | [12 empty] | CAMP STORAGE | 65000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 50.2 | [12 empty] | CONSUMED | 284400
KCl (mg/l) | 45760.8 | 44807.5 | JAR | 109.34 | STAB - 1 | 109.34 | JET VELOCITY (M/SEC) |  |  | 67.23 | [12 empty] | RECEIVED | 299400
CHLORIDES (mg/l) | 25000 | 24500 | 5 1/2" HWDPS | 109.34 | STAB - 2 |  | TFA (IN²) |  |  | 1.03 | [12 empty] | TOTAL | 545000
HARDNESS (mg/l) | 380 | 380 | 9 1/2" DCS |  | STAB - 3 |  | HSI |  |  | 2.8 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 109.34 | SPSA | 109.34 | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.42 |  |  | MPCL | 5
OIL % | 3.5 | 3.6 | BHA ROT. HRS |  | 23.11 |  | BIT NO. 11 RR1 |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 26.5152 |  |  | MPCL SERV | 24
SOLIDS % | 42.7 | 43.12 | ON BOTTOM HRS |  | 20.01 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.1986 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | CIRC. HRS |  | 23.45 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 3913 |  | 1.44 |  | 209.56 |  |  | 0.72 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 66564 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 3944 |  | 0.17 |  | 203.5 |  |  | 1.23 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8341212 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 41.9% | MUD CLEANER | 3 x 170 | [18 empty] | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 3931 | 400/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 3931 | 500/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 3931 | 625/600/625 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 23 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43687 | 43687.6354 | 15.25 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3927M TO 3955M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION. (RECORDED CHECKSHOT AT 3920M, OBSERVED INCL : 1.22°, AZM : 205.87)
43687.6354 | 43687.6667 | 0.75 | DRL | NPT-UP | RR | WHILE B/OUT TDS FOR CONNECTION, OBSERVED DP/TDS CONNECTION OVER TORQUED. SAVER SUB TOP CONNECTION BROKE OUT FROM TDS. DISMANTLED PIPE HANDLER ASSY & B/OUT DP CONNECTION WITH MANUAL TONGS. TIGHTENED SAVER SUB & ASSEMBLED PIPE HANDLER ASSY.
43687.6667 | 43687.8958 | 5.5 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3955M TO 3964M. OBSERVED INCREASE IN FLOW OUT.
43687.8958 | 43687.9062 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43687.9062 | 43688 | 2.25 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3955M TO 3968M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43688 | 43688.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 12 1/4'' HOLE FROM 3968M TO 3981M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4'' HOLE FROM 3927M TO 3968M, WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION. (RECORDED CHECKSHOT AT 3920M, OBSERVED INCL : 1.22°, AZM : 205.87).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14